KITAGWENDA DISTRICT LOCAL GOVERNMENT

DISTRICT DEVELOPMENT PLAN IV 2025/26-2029/30

February 2026

FIGURE 1.1 MAP OF UGANDA SHOWING KITAGWENDA DISTRICT

# Table of Contents

Table of Contents	3

LIST OF TABLES	4

CHAPTER TWO: SITUATION ANALYSIS	Error! Bookmark not defined.

2.0	Introduction	Error! Bookmark not defined.

CHAPTER 3: LOCAL GOVERNMENT DEVELOPMENT PLAN IV STRATEGIC DIRECTION	Error! Bookmark not defined.

3.1	LOCAL GOVERNMENT DEVELOPMENT PLAN IV DIRECTION	46

3.2	STRATEGIC DIRECTION	46

3.3	Alignment of LGDP Objectives and strategies to the NDPIV programmes.	46

3.4	LGDP Development results and targets	47

3.5	LGDP programmes	49

CHAPTER FOUR	88

4.1 Financing framework	88

4.2	Costs of the Plan Period (2025/26-2029/30)	88

4.3 Resource Mobilization Strategy	92

CHAPTER FIVE: INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTING THE PLAN	94

5.1 Implementation Arrangements	94

5.2 Institutional Arrangements	95

5.3 Coordination and Partnership Frameworks	96

CHAPTER SIX: COMMUNICATION AND FEEDBACK STRATEGY	98

6.1 Communication Strategy	98

6.2 Communication Plan	100

6.3 Roles/Responsibilities of Stakeholders in LG Communication and Feedback	100

CHAPTER SEVEN: RISKS MANAGEMENT AND MITIGATION MEASURES	102

7.1 Risks Management and Anticipated Impacts	102

CHAPTER EIGHT: MONITORING, EVALUATION AND LEARNING	104

8.1 Monitoring and Evaluation (M&E) Framework	104

8.2 M&E Roles and Responsibilities of Key Actors	104

8.3 Major Monitoring and Evaluation Events	105

8.4 M&E Roles and Responsibilities of Key Actors	105

8.5 Major Monitoring and Evaluation Reporting Events	107

LIST OF TABLES

Table 1.1: Kitagwenda DDP IV Formulation Process	Error! Bookmark not defined.

Table 2.17: Staffing structure and staffing level by functions	33

Table 3.1: Alignment of LGDP Objectives and Strategies with the NDPIV	46

Table 3.2: LGDP Development Results and Targets	47

Table 3.3: Agro-Industrialization programme Results and Targets	49

Table 3.4: Tourism Development Programme Results and Targets	54

Table 3.5: Natural Resource, Environment, Climate Change, Land and water management Programme Results and Targets	56

Table 3.6: Manufacturing Programme Results and Targets	58

Table 3.7: Human Capital Development Programme Results and Targets	59

Table 3.8: Private Sector Development Programme Results and Targets	70

Table 3.9: Integrated Transport Infrastructure and services Programme Results and Targets	71

Table 3.10: Sustainable Energy Development Programme Results and Targets	74

Table 3.11: Sustainable Urbanization and Housing Programme Results and Targets	75

Table 3.12: Digital Transformation Programme Results and Targets	76

Table 3.13: Public Sector Transformation Programme Results and Targets	78

Table 3.14: Development plan implementation Programme Results and Targets	80

Table 3.15: Governance and security Programme Results and Targets	82

Table 3.16: Legislation, Oversight and Representation Programme Results and Targets	83

Table 3.17: Regional Development Programme Results and Targets	85

Table 4.1: Financing Framework	88

Table 4.2: Summary Costs of the Interventions	88

Table 4.3: Cost of Projects	91

List of Figures

List of acronyms

FOREWARD

This District Development Plan has been developed in full alignment with the Fourth National Development Plan (NDP IV) 2025/26–2029/30, whose overarching focus is Sustained Industrialization, Job Creation, and Shared Prosperity. Guided by national planning frameworks, the District Vision, Mission, and Strategic Objectives have been harmonized to ensure that Kitagwenda meaningfully contributes to Uganda’s long-term transformation agenda, the National Vision 2040, and international commitments such as the Sustainable Development Goals (SDGs) 2030, Africa Agenda 2063, and the East African Community Vision 2050. The plan similarly reflects the aspirations of the National Resistance Movement Manifesto 2026–2031, particularly the drive to increase household incomes, build strong human capital, and modernize rural economies.

Kitagwenda District is endowed with significant development potential. Our fertile agricultural landscape, favorable climate, vibrant livestock sector, and rich water resources including Lake George and associated wetlands position the district as a promising hub for Agro-industrialization and fisheries development. The district also boasts tourism assets such as the scenic hilly terrain, and proximity to Queen Elizabeth National Park, which present opportunities for sustainable tourism and community-based enterprises. Yet, like many rural districts in Uganda, we continue to face challenges including low agricultural productivity, high youth unemployment, limited value addition, infrastructure gaps, and environmental pressures resulting from land degradation and climate variability.

This plan therefore places strong emphasis on agricultural modernization, expanding irrigation, strengthening farmer organizations, promoting Agro-processing, and improving market access. It also prioritizes the enhancement of human capital through better health services, improved education outcomes, and skilling of the youth for meaningful employment. Investments in transport infrastructure, ICT connectivity, digital learning, and resilience-building against climate change form a critical part of our strategy under NDP IV. Furthermore, the plan underscores the need for effective natural resource management to protect wetlands, hillsides, communal grazing lands, and other ecosystems that support livelihoods in Kitagwenda.

I therefore call upon all stakeholders to support the district in turning these strategies into tangible results. By working together, we can unlock the district’s economic potential, create jobs, uplift household livelihoods, and enhance the overall quality of life of our people. I commend the District Planning Office for steering the planning process, and appreciate the technical guidance from the National Planning Authority, and the dedicated support from the Office of the Chief Administrative Officer.

With collective effort and continued government commitment, I am confident that Kitagwenda District will achieve meaningful and sustainable transformation for present and future generations.

Mushemeza Ismail Kabanda

Chairperson LCV

ACKNOWLEDGEMENT

It is a great honour to present the District Development Plan for Kitagwenda, prepared in alignment with the Fourth National Development Plan (NDP IV) and Uganda Vision 2040. The formulation of this plan has been an inclusive and consultative process, reflecting the aspirations, challenges, and unique development opportunities of Kitagwenda District. The plan integrates priorities identified during stakeholder engagements held across the District, and it draws on national strategic guidance aimed at accelerating socio-economic transformation.

On behalf of the leadership of Kitagwenda District, I convey our heartfelt appreciation to all stakeholders who contributed to the development of this plan. Special recognition goes to the District Technical Planning Committee whose commitment and expertise shaped the consolidation of sector priorities; the Senior Assistant Secretaries and Town Clerks whose input ensured that the needs of Lower Local Governments were accurately captured; and all District and Lower Local Government Councilors and Executive Committee members for providing policy direction and timely approvals. We further appreciate the contributions of Development Partners, Civil Society Organizations, Community Based Organizations, and the local communities whose insights, technical support, and collaboration enriched the planning process.

Over the next five years, Kitagwenda District will prioritize strengthening service delivery systems, enhancing community participation in development initiatives, expanding local economic opportunities, improving transparency and accountability, and fostering strong public private partnerships. These commitments are consistent with the NDP IV objectives of creating a skilled and productive population, promoting agro-industrialization, and improving governance and service delivery.

This plan is intended to guide District investments and resource allocation over the planning period and provides a detailed framework for implementing sector priorities that will improve the wellbeing of the people of Kitagwenda. I therefore call upon all leaders, stakeholders, Development Partners, and the community to embrace this plan and use it as the guiding document for advancing the development agenda of Kitagwenda District.

Dalili R. K. Moses

CHIEF ADMINISTRATIVE OFFICER.

# EXECUTIVE SUMMARY

This Kitagwenda Local Government Development Plan Four (LGDP IV) is the fourth in a series of six DDPs that will guide the district in delivering the aspirations articulated in the District Vision 2040. The LGDP IV (2025/26 – 2029/30) is anchored on the progress made, challenges encountered, lessons learnt and best practices from previous planning and implementation experiences of LGDPI, LGDPII and LGDPIII. The Plan defines the broad direction for the district and sets key objectives and targets for the sustainable socioeconomic transformation of the district.

The key achievements that have been registered during the implementation of the previous plans include the following:

- The district has been able to maintain 66% of its road network from 60% and the LLGs 68% from 63% in the last five years.

- The district has been able to reduce the average walking distance to the safe water points from 1km to 0.5 km; there was increase in performance in improved water use from 85% to 97.3% in the last 5 years.

- Reduction of walking distance to health facilities from 10km to 6km by construction of more health units.

- Under Agro- industrialization Crop production increased by an average from 20% to 26% in the last five years and this can be attributed to the Micro-Scale Irrigation program implemented within the period.

- Under Natural Resources, Environment, Climate Change, Land and Water Management; afforestation/reforestation rate increased from 10.1% to 11.6%; Wetland restoration increased from 44% to 59 %; compliance to physical planning increased from 8% to 12%; annual local revenue collected increased from 0.65% to 0.68% contributing to improved service delivery.

- Under Private Sector Development, Annual growth rate of the local businesses registered grew from 1.5% to 3%.

- Under Community Mobilization and Mind-set Change: Adult literacy rate increased from 20% to 24% and annual average   reported cases of domestic violence increased from 43% to 48% due to more awareness created; Increase of awareness and adherence of workers’ rights from 30% to 50%.

- Increased water access in the district from 59% in the FY 2020/21 to 63% by the end of FY 2023/24. Two Hundred Twenty-six (226) out of the three hundred and fifty-six (356) villages have access to at least an improved water source

- There has been improved access to education at all levels overtime. Primary education access has increased to 89% only 11% of the parishes has no government aided primary school.

- Primary school’s net enrolment increased to 40,288 from 37,634 in 2019, representing a percentage increase of 8.07%.

- Staffing Levels in Primary and Secondary Schools improved up to 69.13%, administrative staffing improved up to 100% from 33.3% in 2029.

- Access to secondary education has improved up to 54% and this can be attributed to the grant aiding of Rugarama secondary school in Kakasi subcounty and, construction of Kanara Seed Secondary School reducing on the number of sub counties without secondary schools to six out of thirteen Entities.

However, there are still several limiting factors and challenges, including but not limited to the following:

Inadequate staffing in most departments undermines service delivery; The local revenues collections are still low to support service delivery, poor and inadequate education and health services and facilities; poor road network; limited access to electricity and internet connectivity; continued poor mind set in workers and  communities; Procurement delays; reliance on rain fed agriculture; animal and crop pests and diseases; destruction of biomass wetland degradation is still high; poor waste management continues being a concern; unemployment, child abuse, teenage pregnancy, gender violence and inequality continue to reign.

Some lessons have been learnt and considered while developing the LGDPIV from the implementation of the previous three plans, including:

- Participatory planning enhances project and programme ownership;

- Integration of planning and budgeting improves efficiency

- Data-driven approaches support performance tracking;

- Multi-stakeholder coordination is vital for enhancement of results, which should include; strengthening the working relationship with development partners to enable effective implementation of programmes and avoidance of duplication and strengthening the coordination within the different departments in the district.

- Breaking down the silo approach to planning, budgeting and implementation through the introduction of a program approach that brings together all stakeholders necessary to address a particular development issue propels transformation;

- Multisectoral implementation of the GBV program and incorporation the cultural, religious institutions and the private sector has reduced the GBV cases in the community;

- Orientation of the politician on gender and equity budgeting improves equitable allocation of resources in all sectors;

- Heavy reliance on funding from Central government leads to several projects not being implemented.

- Regular supply of essential medicines improves the essential health care

- Improved Sanitation and Hygiene are key players in Disease prevention.

Highlights of the Development Plan IV

The district intends to fulfill the understated broad intentions of this development plan four; vision, mission, theme, goal, objectives through effective coordination, Monitoring, Reporting and Evaluation, of its implementation by all relevant stake holders. This Development Plan IV strategic direction is in harmony with that of the National development plan four.

District Vision: A prosperous Kitagwenda population, leading to improved quality lives by 2040.

Mission Statement: To promote Change for Development and good Governance to the Kitagwenda community.

District Development Plan IV Goal: “Achieve higher household incomes and employment for sustainable socio-economic transformation’’.

Theme: “Sustainable Industrialization for inclusive growth, employment and sustainable wealth creation”

Its strategic objectives as adopted from the NDPIV are:

- Sustainably increase production, productivity and value addition in agriculture, industry, tourism, minerals, oil & gas, ICT   and financial services.

- Enhance human capital development along the entire life cycle.

- Strengthen private sector capacity to drive growth and create jobs.

- Build and maintain strategic sustainable infrastructure in transport, housing, energy, water, industry and ICT.

- Strengthen good governance, security and the role of the state in development.

The District Development Plan IV Adopted Programmes

Kitagwenda district has adopted/adapted these relevant National Development IV programs to support its present course to development attainment: Agro-Industrialization, Tourism Development, Private sector development, Natural Resource Environment, Climate Change management; Transport Interconnectivity, Sustainable Urban Development, Human Capital, Public Sector Transformation, Regional Development, Development Plan Implementation, Legislation oversight and Representation.

High level interventions for the plan include: Construction of Out Patient Departments (OPD) and Expansion of Maternity wards in 4 Health facilities and up grading two HCII to HCIII; provision of staff accommodation for health staff and teachers; provision of hygiene facilities and tap water for health facilities; completion of administrative headquarters at district and LLGs for office space; development of district and LLGs detailed physical development plans;  construction of two seed secondary schools, procurement of ICT equipment and training; construction of small irrigation schemes; Land titling; and connecting HH and small businesses on the national grid Upgrading all the major District roads.

NDPIV/National Level Projects

A number of projects for Kitagwenda district were highlighted in the NDPIV. These will be majorly implemented by the Ministry of Transport and they include:

- Upgrading of Nsika–Ibanda –Kabujogera-Mashoro–Rwenjaza/Kyambura (204km)

Expected development plan outcomes: If the development challenges are addressed the following results shall be observed:

- Improved transport infrastructure enhancing access to services, markets, and economic opportunities.

- Expanded electricity access supporting business growth, education, health services, and improved household welfare.

- Better internet connectivity improving communication, e-governance, digital learning, and financial inclusion.

- Positive community mindset change increasing participation, innovation, and sustainability of development programs.

- Strengthened governance and administration improving coordination, accountability, and service delivery efficiency.

- Improved education infrastructure leading to higher enrolment, better learning outcomes, and a skilled workforce.

- Enhanced health infrastructure improving access to quality care, disease control, and population wellbeing.

- Increased agricultural productivity through irrigation, climate-smart farming, and control of pests and diseases.

- Environmental sustainability through conservation, improved waste management, and climate resilience.

- Reduced poverty and unemployment through job creation, gender equality, youth empowerment, and inclusive economic growth.

Funding of the development Plan

This plan shall be funded by funds from Central government transfers, locally raised revenue, monetary and non-monetary budget and off budget partnership contributions by the Private sector and donors.  Local communities are also expected to contribute through facility committees and asset donations like land for infrastructure development.

Plan cost: The plan is expected to cost 360,743,900,000 of which 352,5500,000 is from central government mobilization, 2,250,000,000 from locally raised revenue and 5,200,000,000 from donors.

Implementation and Co-ordination of the plan:

This plan implementation shall be premised on the adopted five NDPIV strategic objectives and shall be delivered through the district adopted NDPIV programs for alignment requirement. The implementation of its programs will take the course of the planning cycle every year; Planning, Budgeting, Implementation and Monitoring and Evaluation. It will also focus on all activities undertaken by HLG, LLGs and development partners to realize the district development aspirations.

Risk Management: Management of risks is important for the successful implementation of the Plan. Five major categories (Administrative, Financial, Governance, Environmental and Operational) of anticipated risks that may threaten plan implementation and the realization of its goal and vision have been highlighted on page 103 and their root causes, and suggested mitigation measures are laid out.

Communication and Feedback Strategy: The communication strategy in chapter six (6) of the LGDPIV provides avenues for internal communication and feedback for the plan.  It highlights the key stakeholders and their specific roles, including the target audiences and their interests including their key messages.

Monitoring and Evaluation Arrangements: The Monitoring and Evaluation Process highlighted out in chapter eight (8) of this plan will be used to determine the relevance, efficiency, effectiveness, impact and sustainability of the different programmes implemented during the development plan period: A set of interrelated components (persons, tools, equipment etc.) working together to produce the required development evidence. The district intends to use simple methods of collecting data and sharing information about the development plan implementation with all the stake holders participating at relevant stages.

CHAPTER ONE: INTRODUCTION

1.1 Background and Development Context

The Kitagwenda District Development Plan IV (2025/2026–2029/2030) has been developed in line with the constitutional and legal mandates provided under Article 190 of the 1995 Constitution of the Republic of Uganda and Section 36 of the Local Governments Act, Cap 243. These legal frameworks empower District Councils to formulate comprehensive and integrated development plans that reflect national priorities. This Plan is anchored within the Comprehensive National Development Planning Framework (CNDPF) and adheres to the Local Government Development Planning Guidelines (2020) issued by the National Planning Authority (NPA).

The District Development Plan IV is aligned with Uganda Vision 2040, the Fourth National Development Plan (NDP IV), and global development frameworks such as the Sustainable Development Goals (SDGs). It also incorporates priorities from key government flagship programmes, notably the Parish Development Model (PDM), and is structured using a Programme-Based Planning approach to enhance alignment between local and national development priorities.

1.2 Key Achievements from the Previous Plan (2020/21–2024/25)

A review of past performance in Kitagwenda District reveals significant progress in urban development, social services, and infrastructure improvement. Kitagwenda’s strategic location along the River Nile and its status as a tourism and industrial hub have influenced its development trajectory.

Significant strides have been made in agriculture and this has remained the backbone of the district economy, with over 2,000 farming households supported through the Parish Development Model (PDM), Operation Wealth Creation (OWC), and micro-scale irrigation projects. Farmers received improved seeds, livestock, and training in value addition and climate-smart agriculture. In addition, small-scale enterprises were supported with entrepreneurship training, market linkages, and financial inclusion initiatives.

Infrastructure development registered remarkable progress during the implementation period. The District rehabilitated and maintained over 300 kilometres of community and district roads, greatly enhancing accessibility to markets, health facilities, and schools. Access to safe water improved significantly, with coverage increasing from approximately 65% in FY 2020/21 to about 78% in FY 2024/25, following the construction and rehabilitation of various water sources. Furthermore, several education and health infrastructure projects were completed, including the construction of classroom blocks, latrines, and maternity wards, thereby improving the quality and reach of essential public services across the District.

Access to education and health services improved significantly. Primary school enrollment and performance in national exams rose due to improved staffing and learning facilities. The health sector recorded progress in maternal and child health, immunization coverage, and disease control. Vulnerable groups such as women, youth, and persons with disabilities benefited from government livelihood programmes including UWEP, YLP, and special grants for PWDs, while the elderly continued to receive support under the SAGE programme.

Access to secondary education has improved up to 54% by Grant aiding of Rugarama secondary school in Kakasi subcounty and, construction of Kanara Seed Secondary School reducing on the number of sub counties without secondary schools to six out of thirteen Lower Local Governments in the District.

Community based services.

The table below further summarizes tracked service outcomes and indicators over the previous plan period.

| MDPIII Programme | Service Outcomes | Service Outcome Indicators | Baseline | FY 2019/20 | FY 2020/21 | FY 2021/22 | FY 2022/23 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Agro-Industrialization | Urban agriculture productivity | Growth in urban marketed produce (e.g., from Walukuba estates) | 2.50% | 2.60% | 2.80% | 3.00% | 3.20% |
|  | Farmer participation in value chains | Growth in membership of urban farmer groups (e.g., Wanyange Urban Farmers Assoc.) | 2.80% | 3.00% | 3.20% | 3.50% | 3.70% |
|  | Urban extension access | % of urban farmers contacted by extension workers | 3% | 3.20% | 3.40% | 3.50% | 3.60% |
| Natural Resources, Environment, Climate Change, Land and Water Management | Urban water supply | % of urban population within 500m of improved water source | 64% | 66.00% | 67.00% | 67.00% | 68.00% |
|  | Urban water functionality | % of urban water sources functional (e.g., Bugembe, Mpumudde) | 85% | 86% | 87% | 88% | 89% |
|  | Urban drainage | % of drainage channels desilted and maintained (e.g., in CBD) | 1% | 1.50% | 2% | 2.50% | 3% |
|  | Urban sanitation | % of households with access to improved sanitation | 70% | 72% | 75% | 80% | 84% |
|  | Water quality | % of urban water sources tested for quality | 35% | 36% | 38% | 40% | 45% |
|  | Urban school sanitation | Pupil-to-latrine stance ratio in UPE schools | 60:01:00 | 50:01:00 | 40:01:00 | 30:01:00 | 25:01:00 |
|  | Urban water compliance | % of water points meeting national standards | 92% | 94% | 95% | 96% | 97% |
|  | Urban greening | % increase in tree cover in town areas (e.g., along Clive Road West) | 8% | 9% | 10% | 12% | 14% |
|  | Wetland protection | Area of wetlands restored (e.g., in Masese zone) (Ha) | 5 | 5 | 6 | 7 | 8 |
|  | Wetland regulation | No. of wetland action plans developed | 0 | 1 | 1 | 2 | 2 |
| Private Sector Development | Urban business growth | Annual growth in registered urban businesses | 3.10% | 3.40% | 3.70% | 4.20% | 4.50% |
| Integrated Transport Infrastructure and Services | Urban road condition | % of District roads in fair-to-good condition | 60% | 63% | 65% | 70% | 75% |
|  | Community access | % of informal roads maintained | 55% | 58% | 60% | 63% | 65% |
|  | Urban access | % of access roads in good condition | 20% | 22% | 25% | 30% | 35% |
| Human Capital Development | Primary education | Numeracy proficiency | 58% | 60% | 62% | 68% | 72% |
|  |  | Literacy rate | 61% | 65% | 70% | 78% | 81% |
|  |  | Gross enrolment | 85% | 88% | 89% | 91% | 93% |
|  |  | PLE Performance Index | 82% | 83% | 85% | 86% | 88% |
|  |  | Completion rate | 67% | 70% | 73% | 78% | 82% |
|  | Secondary education | UCE pass rate | 75% | 77% | 80% | 83% | 85% |
|  |  | Enrolment | 78% | 80% | 83% | 85% | 87% |
|  |  | Completion rate | 73% | 76% | 78% | 81% | 84% |
|  | Skills development | Vocational training pass rate (e.g., at Kitagwenda Vocational Institute) | 82% | 83% | 85% | 87% | 89% |
|  |  | Enrolment in TVET | 70% | 75% | 78% | 81% | 85% |
|  |  | Training performance index | 80% | 82% | 85% | 87% | 88% |
|  | Primary health | OPD Utilization | 1 | 1.2 | 1.3 | 1.5 | 1.6 |
|  |  | DPT3 Immunization | 95% | 96% | 98% | 97% | 99% |
|  |  | Villages with functional VHTs | 72 | 75 | 80 | 85 | 90 |
|  | In-patient healthcare | Urban facility-based mortality | 5/1000 | 4.5 | 4 | 3.5 | 2.5 |
|  |  | % of patients discharged successfully | 95% | 96% | 97% | 98% | 99% |
|  | Epidemic control | HIV knowledge among youth | 85% | 88% | 90% | 95% | 98% |
|  |  | Malaria-related admissions | 0.20% | 0.30% | 0.40% | 0.60% | 1.00% |
|  |  | TB case detection and cure rate | 78% | 80% | 85% | 88% | 91% |
|  | Maternal health | % deliveries in public facilities | 60% | 65% | 72% | 78% | 85% |
|  |  | Average ANC visits | 20,000 | 21,500 | 23,000 | 25,000 | 26,000 |
| Community Mobilization and Mindset Change | Community empowerment | Adult literacy rate | 22% | 23% | 24% | 25% | 26% |
|  |  | % orphaned children supported | 12% | 13% | 14% | 15% | 16% |
|  |  | % of persons with disabilities | 2.50% | 2.60% | 2.80% | 3.00% | 3.20% |
|  |  | Child abuse cases | 45 | 47 | 48 | 50 | 52 |
|  |  | Domestic violence cases | 52 | 53 | 54 | 56 | 58 |
|  | Custody & corrections | Urban recidivism rate | 2% | 1.50% | 1% | 1% | 1% |
| Governance and Security | Urban planning | No. of approved building plans | 20 | 22 | 25 | 30 | 35 |
|  |  | LGFC Governance Score | 10 | 10 | 10 | 10 | 10 |
|  | Staffing | % of approved positions filled | 65% | 68% | 70% | 72% | 75% |
| Public Sector Transformation | Revenue generation | Share of locally generated revenue | 4% | 4.50% | 5% | 5.50% | 6% |
|  |  | Budget absorption rate | 85% | 87% | 89% | 92% | 95% |
|  | Planning compliance | NDP compliance score | 75% | 77% | 80% | 80% | 85% |
|  | Audit performance | % unqualified audit opinions | 95% | 96% | 98% | 98% | 100% |

1.3. Key Outstanding Development Issues /Challenges

Despite notable progress, Kitagwenda District continues to face several development challenges that must be addressed in this planning cycle:

- Phasing Out of Support to Private Schools: The withdrawal of government support to private USE schools has increased pressure on government-owned secondary schools.

- Decline in Locally Raised Revenue: Creation of new Town Councils and Sub-Counties reduced the district’s share of local revenue.

- Inadequate Central Government Funding: Most transfers are conditional, limiting flexibility in addressing local priorities.

- Poor Road Conditions: Predominantly loam soils result in high maintenance costs and poor durability of roads.

- Human Resource Gaps: Inadequate staffing in health, education, and town councils continues to affect service delivery.

- Cultural Constraints and Gender Inequality: Traditional beliefs hinder women’s participation in decision-making, access to services, and economic empowerment.

- Overreliance on Rain-fed Agriculture: Limited irrigation and changing weather patterns increase food insecurity and poverty.

- Environmental Degradation: Encroachment on natural resources is driven by poverty and high population growth.

- High Population Growth and Dependency Ratios: A young population increases demand for social services and limits savings and investment.

- Decline in Key Development Grants: Transition from LGMSD to DDEG saw a drop in funds, hampering infrastructure development.

- Inadequate Monitoring and Supervision: Weak coordination in monitoring, especially in agriculture, reduced the impact of programs like Operation Wealth Creation (OWC).

1.4.  Key Lessons Learnt from Implementation of the Previous Plan

The implementation of the previous development cycle provided key lessons that are essential for the success of the new planning period:

- Public-Private Partnerships play a pivotal role in the achievement of development objectives. Strengthening collaboration with private actors improves resource mobilization and service delivery.

- Baseline Data Development is necessary to monitor and track performance across sectors.

- Capacity Building: There is a strong need for continuous capacity building in project appraisal, monitoring, and implementation among technical staff.

- Human Resource Management: Timely recruitment and deployment of Parish Chiefs and other critical staff is essential for effective planning and coordination at the local level especially for the success of key government programs like the Parish Development Model.

1.5 Formulation Process and Approach

The formulation of the Kitagwenda District Development Plan IV (2025/26–2029/30) followed a participatory, inclusive, and structured process in line with the Planning Call Circular issued by the National Planning Authority (NPA). The process began with the dissemination of planning guidelines and was guided by the Local Government Development Planning Guidelines (2020).

Consultations were held at all planning levels - from village to district - involving Lower Local Governments, Technical Planning Committees, Civil Society Organizations, the Private Sector, and community representatives. The District Planning Unit coordinated the collection, review, and integration of data and priorities from various stakeholders into the final Plan. Special emphasis was placed on ensuring gender responsiveness and integrating cross-cutting issues.

Community priorities were captured through the collection of Local Lower Government (LLG) proposals between October and November 2024. Sub-county chiefs, working closely with the District Planning Unit, facilitated consultations at parish and sub-county levels to ensure that grassroots perspectives informed the development plan. These proposals were reviewed and integrated into the District Development Plan to promote ownership and local relevance.

Technical consolidation of inputs was undertaken through Sector Working Group sessions and District Technical Planning Committee (DTPC) meetings held between November and December 2024. Heads of Departments (HODs) reviewed sector priorities, assessed feasibility, ensured cross-sectoral coordination, and harmonized interventions to avoid duplication and enhance impact.

Political oversight and endorsement formed a critical stage of the process. Between January and February 2025, draft proposals were presented to the District Executive Committee (DEC) and Council Committees for scrutiny, guidance, and policy alignment. This ensured that the plan reflected political priorities and enjoyed leadership support before final approval.

Stakeholder validation was achieved through the District Budget Conference and planning workshop, where key stakeholders including development partners, civil society organizations, private sector actors, and community representatives reviewed the draft plan. Their feedback helped refine priorities, strengthen accountability, and enhance transparency.

Finally, the development planning process culminated in the approval and submission of the finalized District Development Plan to the National Planning Authority (NPA) and the Ministry of Finance, Planning and Economic Development (MoFPED). The District Planning Unit coordinated this stage to ensure compliance with statutory requirements, adherence to planning standards, and timely submission.

The process prioritized stakeholder ownership, inclusion, and alignment with both local realities and national priorities. It also took into account emerging development issues such as urbanization, climate change, youth unemployment, and digital transformation.

1.6. Structure of the Plan

The Kitagwenda District Development Plan IV (LGDP IV) is structured to comprehensively present the district’s development aspirations, priorities, and implementation strategies. The plan begins with a preamble, which provides an overview of the purpose, scope, and guiding principles that inform the entire document. This is followed by an acknowledgement section that recognizes the contributions of individuals, institutions, and partners who played a key role in developing the plan. To support better understanding of the content, the plan includes a list of figures and maps that offer visual and geographic representations of relevant data and context. A list of acronyms is also provided to define abbreviations and key terminologies used throughout the document for clarity and consistency.

Chapter One: The main chapters of the plan begin with this chapter, which introduces the District by presenting its background and contextual information. This chapter highlights key development achievements, ongoing challenges, and the lessons drawn from previous planning cycles. It also explains the plan formulation process and the extent of stakeholder engagement involved.

Chapter Two: This Chapter presents a comprehensive situation analysis that examines the District’s geographical features, demographic trends, socio-economic dynamics, environmental conditions, and governance systems. This analysis serves as a baseline for prioritizing interventions.

Chapter Three: This chapter defines the strategic direction of the District by articulating its vision, mission, development objectives, and goals. This chapter also demonstrates how these elements align with the broader frameworks of the National Development Plan IV and Uganda Vision 2040. It further identifies thematic focus areas and the priority programmes to be pursued.

Chapter Four:  This chapter discusses the financing and costing framework, providing projections of financial resources, identifying potential funding sources, and outlining strategies for resource mobilization along with the costing of planned interventions.

Chapter Five: This chapter lays out the implementation arrangements by describing the institutional structures and coordination mechanisms that will operate at both District and Division levels. It clearly defines the roles of different actors, including government institutions, civil society, the private sector, and development partners.

Chapter Six: This chapter presents the communication and feedback strategy, emphasizing the importance of effective stakeholder engagement, timely information dissemination, and the establishment of responsive feedback channels to support plan implementation.

Chapter Seven: This introduces the risk management framework by identifying potential risks that may hinder implementation and proposing corresponding mitigation measures to strengthen resilience and adaptability.

Chapter Eight: This chapter outlines the Monitoring, Evaluation, and Learning (MEL) framework, detailing how progress will be tracked and assessed. This chapter describes the indicators to be used, the reporting schedules, and the learning mechanisms that will support continuous improvement and adaptive management.

Annexes: The plan concludes with annexes that provide additional technical documentation. These include detailed project profiles, results frameworks, performance targets, costing and implementation matrices, and other supporting materials that complement and enrich the main text of the plan.

CHAPTER TWO: SITUATION ANALYSIS

2.1 Geographical Location, Land Area, and Population

Geographical Location & Topography

Kitagwenda District, located in the Western Region of Uganda, became operational in 2019 after being curved out of Kamwenge District. It covers approximately 870 km² and borders Rubirizi to the west, Ibanda to the east, Kamwenge to the south, and Lake George to the northwest. The administrative headquarters is in Kitagwenda Town Council Town Council, which serves as the main commercial hub.

Kitagwenda is situated on gently rolling hills and valleys of the western rift valley escarpment with elevations ranging between 1,300–3800 metres above sea level and this includes the flat Great Western Lift Valley that hosts Queen Elizabeth National Park. The hills are short with wide valleys. The district is traversed by rivers such as Mpanga river, and it hosts part of Lake George Ramsar Site, which is globally recognized for biodiversity.

While the district is predominantly rural, its proximity to Queen Elizabeth National Park and Lake George has introduced opportunities for fisheries, tourism, and related service industries

Figure 1.2. Topographic Map of Kitagwenda District.

Land Area

The district spans approximately 870 km², with fertile volcanic soils around the rift valley and savannah grasslands supporting mixed farming and pastoralism.

Population

Kitagwenda District’s population increased from 143,786 in 2014 to 184,947 in 2024 (NPHC 2024), representing 29% growth over ten years. Of the 2024 population, 96,534 are males and 88,413 are females, with 77,544 children aged 0–14, 99,398 people aged 15–64, and 8,005 elderly (65+). This youthful structure means that 42% of the population is below 15 years, reflecting high dependency and growing pressure on education, health, and social services. Urban centres such as Kitagwenda TC have also expanded rapidly, registering over 24,000 residents in 2024.

The district faces several development challenges driven by these demographic dynamics. The rising school age population demands more classrooms, teachers, and learning materials, while health facilities struggle to keep pace with increasing maternal, child, and adolescent health needs. With over 70% of households dependent on agriculture, issues such as land fragmentation, low productivity, limited value addition, and environmental depletion persist. This population growth has increased the strain on water systems, rural–urban infrastructure, and sanitation, while youth unemployment and underemployment remain high due to inadequate skilling and limited non-farm opportunities.

Nevertheless, Kitagwenda’s population offers opportunities for socio-economic transformation. The large working-age population nearly 54% of all residents presents potential for a demographic dividend if harnessed through skilling, enterprise development, and expansion of agro-industrial value chains

Population Density

Population density in Kitagwenda district stands at approximately 274 persons/km² derived from a total population of about 184,947 people distributed across the district’s land area. The distribution, however, varies significantly across lower local governments. Kitagwenda Town Council, with about 24,135 people, and Kabujogera Town Council, with 14,672 people, are among the most densely populated areas due to urban concentration, while rural sub-counties such as Ruhunga (6,437 people) and Rwenjaza (10,719 people) have much lower population concentrations.

Table 2.1: Distribution of population, Land area and population density by Sub-County/ Town Council

| No. | Sub-county/Town council | Population by Sex |  |  | Land area (km²) | Population Density (persons/km²) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Male | Female | Total |  |  |
| 1 | Buhanda S/C | 8,999 | 8,607 | 17,606 | 95 | 192 |
| 2 | Bukurungo T/C | 3,767 | 3,418 | 7,185 | 15 | 832 |
| 3 | Kabujogera T/C | 7,579 | 7,093 | 14,672 | 8 | 900 |
| 4 | Kakasi S/C | 6,755 | 6,726 | 13,481 | 65 | 243 |
| 5 | Kanara S/C | 9,671 | 8,758 | 18,429 | 120 | 233 |
| 6 | Kicheche S/C | 7,655 | 6,436 | 14,091 | 70 | 236 |
| 7 | Kitagwenda T/C | 12,888 | 11,247 | 24,135 | 10 | 850 |
| 8 | Mahyoro S/C | 5,405 | 4,982 | 10,387 | 42 | 256 |
| 9 | Mahyoro T/C | 9,136 | 7,983 | 17,119 | 7 | 971 |
| 10 | Ntara S/C | 6,817 | 6,586 | 13,403 | 80 | 256 |
| 11 | Nyabbani S/C | 8,984 | 8,299 | 17,283 | 50 | 256 |
| 12 | Ruhunga S/C | 3,408 | 3,029 | 6,437 | 60 | 237 |
| 13 | Rwenjaza S/C | 5,470 | 5,249 | 10,719 | 55 | 245 |
|  | TOTAL | 96,534 | 88,413 | 184,947 | 677 | 274 |

Fertility Rate & Demographics

The district’s Total Fertility Rate (TFR) is estimated at 5.9 children per woman, slightly above the national average. The population is youthful, with nearly 52% below 18 years, which places pressure on social services like education and health.

2.3. Labour Force & Economic Activity

Agriculture is the backbone of Kitagwenda’s economy, employing over 75% of households. The major food crops include bananas, maize, beans, cassava, and sweet potatoes, while cash crops include coffee and cotton. Livestock rearing, especially cattle, goats, and poultry is widespread, with pastoral activity being common in Kanara and Manyoro

The district also benefits from fisheries on Lake George, with species such as tilapia and catfish supporting both local consumption and cross-border trade.

Tourism potential exists due to proximity to Queen Elizabeth National Park and Mpanga River Gorge, though it remains underdeveloped.

Table 2.2: Major Economic Activities in Kitagwenda

| Economic Activity | Share of Population (%) | Key Examples / Notes |
| --- | --- | --- |
| Crop Farming | 65 | Cofee, Bananas, beans, cassava, maize |
| Livestock Rearing | 20 | Cattle, goats, poultry |
| Fisheries | 7 | Lake George landing sites |
| Trade & Commerce | 5 | Kitagwenda Town Council Nyabani SC, Kabujogera, Kanara trading centers |
| Tourism & Services | 3 | Queen Elizabeth NP, Mpanga Gorge |

2.4. Migration Patterns

Population movements in Kitagwenda are mainly intra-district, with people moving between rural areas and growth centers such as Kabujogera and Nyabani. Fishing communities around Mahyoro TC and Bukurungo TC also attract migrants from neighboring districts due to fishing opportunities on Lake George. However, there is limited outward migration since most residents depend on agriculture and local natural resources for livelihood.

The population by Age and Sex (Thousands)

Children 0-14 years

3.2%

Economically productive age 15-64 years

Elderly 65+ years

49.9%

46.9%

Life Standard Indicators

Table 2.2: Selected Development Indicators (2024, Kitagwenda District)

| Indicator | Status (Appx) |
| --- | --- |
| Total Fertility Rate (per woman) | 5.9 |
| Primary school attendance (age 6–12) (%) | 82% |
| Adult illiteracy rate (10+ years) (%) | 69% |
| Share of households using Tadooba (paraffin) | 55% |
| Access to electricity (%) | 16% |
| Households using wood fuel for cooking (%) | 85% |
| Households with unimproved toilet facilities (%) | 34% |
| Subsistence farming households (%) | 74% |
| Households dependent on earned income (%) | 19% |
| Households receiving remittances (%) | 8% |
| Mobile phone ownership among households (%) | 67% |
| Radio ownership among households (%) | 62% |

Livelihood Patterns

In Kitagwenda District, subsistence agriculture remains the predominant livelihood activity, dominated by smallholder farmers. The main crops grown include bananas (matooke), beans, cassava, sweet potatoes, maize, and groundnuts. Coffee is the major cash crop across the district. Livestock farming is widely practiced, with cattle, goats, sheep, and poultry forming an important source of income and nutrition. The open grasslands in Kanara and Mahyoro support cattle keeping, including both indigenous breeds and crossbreeds.

Fishing is a major livelihood in Kitagwenda, particularly in Mahyoro and Bukurungo Town Councils along Lake George, where communities rely on fishing. This makes the district unique compared to many inland rural districts.  Non-agricultural activities include bricklaying, charcoal burning, quarrying, and local brewing, which provide supplementary income. In semi-urban centres like Nyabani Town Council, Kabujogera, and Kanara trading centres, there is a growing informal economy in boda-boda transport, mobile money, petty trade, and tailoring. Youth and women dominate small-scale businesses in local markets, though access to affordable credit remains a major barrier. Land fragmentation caused by inheritance practices is a growing problem, reducing productivity. Meanwhile, youth migration to larger towns like Ibanda, Mbarara, and Kampala reduces agricultural labour availability.

Table 2.3: Household Livelihood Activities in Kitagwenda District

| Livelihood Activity | % of Households |
| --- | --- |
| Subsistence crop farming | 63.4 |
| Commercial crop farming | 11.2 |
| Subsistence livestock farming | 9.1 |
| Commercial livestock farming | 2.3 |
| Fishing | 4.8 |
| Self-employment (non-agric.) | 6.7 |
| Formal employment | 1.5 |
| Remittances | 1 |
| Others | 0.5 |

Human Settlement Patterns

Kitagwenda District is predominantly rural, with over 85% of the population residing in scattered homesteads. Settlements reflect clan-based and agricultural land use patterns.

Housing

Housing in Kitagwenda exhibits a rural–urban divide. In rural areas such as Nkoma, Kabujogera, and Magoma, most households live in semi-permanent houses made of mud and wattle, with thatched or iron sheet roofs.

In contrast, Nyabani Town Council and Kabujogera trading centre have seen modest growth in permanent housing, with brick-walled and cemented structures increasing. However, this growth lags behind the population, leading to mushrooming of informal settlements with limited infrastructure.

Solid waste disposal remains poor, especially in urbanizing areas. Waste is often dumped in open spaces and wetlands, leading to hygiene-related diseases like typhoid and dysentery. Access to piped water and sanitation remains a challenge in both urban and rural areas, with over 30% of households still using unimproved toilets.

2.2 Potentials, Opportunities, Challenges and Constraints (POCC) Analysis

2.2.1 Agriculture

Kitagwenda District has high agricultural potential owing to its fertile soils, reliable rainfall, and vast savannah grasslands. The major food crops grown include bananas, beans, cassava, groundnuts, sweet potatoes, and maize, while coffee remains the leading cash crop. Kitagwenda District is majorly a coffee producing district currently, 18,956 households are actively engaged in coffee production on 26,414 acres, achieving an annual yield of 21,195.379 tonnes.  Livestock rearing-particularly cattle, goats, and poultry also plays a critical role in household food security and income. The presence of Lake George provides opportunities for both fishing and irrigation farming, offering a comparative advantage over many inland districts.

Despite this potential, agriculture in the district continues to face notable challenges. Land fragmentation is reducing farm sizes and limiting economies of scale. High post-harvest losses, pests and diseases, and the generally low adoption of modern farming technologies constrain productivity. Although the District received significant support in the form of value addition facilities, the full potential of these investments has not yet been realized as facilities in Kanara, Bukurungo, Buhanda, and Kabujogera remain largely nonfunctional due to the lack of electricity, which is essential for operating the major equipment in these facilities.

Agricultural extension coverage is poor, with high farmer-to-extension worker ratios leaving most farmers without adequate technical support. Nonetheless, the district is well positioned to benefit from government programmes such as the Parish Development Model (PDM) and Emyooga, which are designed to enhance access to inputs, promote value addition, and support commercialization. In addition, Kitagwenda’s location provides emerging market access through neighboring urban centres such as Ibanda, FortPortal and Kasese, which can absorb surplus produce and create new income streams for farmers.

2.2.2 Tourism

Tourism in Kitagwenda remains largely underdeveloped despite its considerable potential, given the district’s strategic location in the Albertine Rift Valley. Kitagwenda borders Queen Elizabeth National Park and hosts part of the Lake George Ramsar Site, which is internationally recognized for its aquatic biodiversity and birdlife. River Mpanga and its gorge are habitat to the famous Cycads, a species only found in Kitagwenda in the whole world, if harnessed, can draw eco-tourists. The district also has cultural heritage sites, hills, clan shrines, and traditional festivals including: - Mpanga Gorge, Kagazi hills, Mpanga falls, Nshonda hills, Kasoya-kitomi Forest Reserve, Kyambura game Reserve, Dura quarry among others that could be developed into cultural tourism products.

There are several opportunities to harness tourism for local economic growth. Government programs under the Uganda Tourism Board (UTB) and the Ministry of Tourism, Wildlife and Antiquities can support the district in product development, promotion, and capacity building. The presence of NGOs and development partners such as Joint Effort to save the Environment (JESE), Eco-trust, working in conservation and livelihoods provides room for partnerships in eco-tourism projects. Additionally, the expansion of road networks under the NDP IV and the parish development model can enhance accessibility to tourism sites. The growing domestic tourism culture in Uganda presents a ready market for community-based tourism experiences within Kitagwenda.

Opportunities also exist to promote eco-tourism activities such as bird watching, fishing village experiences, and nature walks, while cultural tourism linked to clan traditions and heritage could help diversify the district’s offerings. However, tourism growth is hampered by several challenges including: - poor infrastructure especially feeder roads leading to tourist sites, limited accommodation facilities, and low investment from the private sector. There is also inadequate documentation and promotion of tourism attractions, making the district less known to both local and international tourists. Environmental degradation, especially encroachment on wetlands and forests, poses threats to scenic and ecological attractions. Furthermore, limited local capacity in hospitality, tour guiding, and marketing restricts the ability of communities to benefit from tourism value chains. Without deliberate investment, the district risks underutilizing one of its most strategic comparative advantages.

2.2.3 Minerals, Oil, and Gas

The district is endowed with a number of mineral resources as per aero survey carried out. Exploration has discovered Gold in Kitaka, Tin and Iron along the Kasyoha - Kitomi forest composite. There are also prospects oil and gas in the part of Mahyoro, Ntara, and Kanara which are parts of the Albertine graben. Kitagwenda does not host large-scale mineral or petroleum resources. Nonetheless, artisanal extraction of clay and sand for brick making and construction is widespread, particularly in Ntara and Kabujogera, while stone quarrying provides seasonal employment for local communities. These small scale activities contribute to household incomes but also pose environmental risks if not well managed.

Energy access in the district remains low, with only about 6.9% percent of households connected to the national grid. The vast majority of households rely on firewood and charcoal for cooking, a practice that has accelerated deforestation and placed increasing pressure on natural resources. Although renewable energy options such as solar and biogas are slowly emerging, they remain largely unaffordable and inaccessible for most households. This situation continues to entrench reliance on unsustainable energy sources while limiting opportunities for modern industrial and agro-processing development.

2.2.4 Science, Technology, Innovation, and ICT

The penetration of information and communication technology in Kitagwenda is gradually improving. Mobile phone coverage is widespread across most trading centres, with mobile money services driving financial inclusion and providing an essential link to markets. Radio ownership is also limited as the district has no resisted radio station, the people depend on radio stations in Kamwenge, Ibanda and FortPortal to get information. Youth in the district have increasingly turned to ICT-related businesses such as phone repair, Sale of electronic devices, and digital financial services, reflecting the sector’s potential for employment creation.

However, ICT development in the district continues to face significant constraints. Computer access is very limited, digital literacy is low, and high internet costs remain prohibitive, particularly for rural populations. ICT training facilities are few, and public schools rarely have functional computer laboratories. The district is not connected to the National ICT backbone, which hampers opportunities for e-governance and improved service delivery These gaps have constrained the integration of ICT into education, health, and agricultural extension services. Yet, the opportunities remain significant.

Expanding ICT hubs, strengthening youth skilling programmes, and integrating mobile technology into service delivery could transform how the district provides extension, education, and financial services. In particular, e-learning platforms could complement classroom teaching, while ICT-supported extension could reach farmers in remote communities with timely information.

2.3 Economic Infrastructure and Services

2.3.1 Water for Production

Kitagwenda District has high potential for water for production, supported by the presence of Lake George, River Mpanga, over 46 wetlands, and valley tanks. These natural resources provide opportunities for small-scale irrigation, livestock watering, and aquaculture, especially in Kanara, Nyabbani, Ntara Sub-County and the greater Mahyoro.

Despite these resources, the district remains heavily dependent on rain fed agriculture, which is increasingly unreliable due to climate variability. Uptake of irrigation technology is very low. While a few farmers across the district have benefited from government support under programmes such as UGIFT-Micro Scale irrigation and the Parish Development Model (PDM), coverage remains minimal. In addition, the absence of organized water user committees and weak maintenance of existing facilities limit sustainability of water for production infrastructure.

Table 2.4: Status of Irrigation Infrastructure and Support Services.

| Indicator | Status |
| --- | --- |
| Number of micro-scale irrigation facilities | 56 (Across the District) |
| Main water sources for irrigation | Wetlands, River Mpanga, Lake George, River, valley tanks, wetlands |
| Extension workers dedicated to irrigation | Inadequate staffing of extension workers |
| Farmers trained in efficient irrigation use | Very few |

2.3.2 Roads and Transport (DUCAR)

Kitagwenda District has a total road network of 157 kilometers, of which 105 km are earth roads and 52 km are murram surfaced. Despite efforts by the District and Central Government to maintain road connectivity, the general condition of the road infrastructure remains poor. Currently, over 51% of the road network is in poor condition, making transport difficult, especially during the rainy seasons.

The district’s hilly terrain and heavy rainfall have worsened drainage problems, leading to frequent road washouts and blockages. The most affected hilly areas include Kinyamugara in Kicheche Sub-county, Kitaka in Kakasi Sub-County, Nsinda, Kichwamba and Rwentuha in Kitagwenda TC, Nganiko in Nyabbani S/C, and the western rift valley escarpment, where the steep slopes accelerate surface runoff and erosion.

There are several hotspots within the network such as: - Ryengoma, Kihogo, Rwesigire, Rwamusambo, and Kakinga that regularly experience severe damage where cross-drain culverts are swept away or frequently choked. These problems are largely caused by high siltation, accumulation of debris at culvert entrances, flooding of streams, and the rapid formation of gullies due to uncontrolled runoff. The situation is particularly worse in the sub-counties of Kicheche, Kakasi, Mahyoro, Buhanda, and Ruhunga, where roads have become almost impassable during wet seasons. Poor drainage design and inadequate maintenance further exacerbate these challenges, limiting accessibility to key social and economic areas.

The district receives about UGX 1.2 billion annually for road maintenance, which is insufficient given the terrain and heavy use. The District Engineering Department is under-equipped as the district lacks a service van/pickup for effective monitoring and supervision of road works, Roller, tippers and water bouser, and maintenance delays for the available equipment is also are common.

Table 2.5: Road Infrastructure Coverage and Status in Kitagwenda

| Road Type | Total Length (km) | Status |
| --- | --- | --- |
| District Roads |  |  |
| Community Access Roads |  |  |
| Urban Roads |  |  |

2.3.3 Energy

The main household energy sources in Kitagwenda are firewood and charcoal, with over 90% of rural households using firewood and charcoal being common in trading centres like Nyabani, Kabujogera, and Kanara. Kerosene lamps remain a major source of lighting in remote villages without electricity.

Electricity access has improved slightly under the Rural Electrification Programme, with connections in centres like Nyabani, Kabujogera, and Kanara, but coverage remains at about 18% of households with no connection in some parts Kakasi and Ruhunga S/C. Uptake is limited due to high connection costs, low incomes, and inadequate last mile distribution infrastructure.

Solar energy adoption is gradually growing, with households acquiring small home systems for lighting and phone charging, though coverage is still low. Heavy dependence on biomass is contributing to deforestation, especially around Lake George wetlands and across the district.

Table 2.6: Household Energy Use in Kitagwenda

| Energy Source | Usage (%) |
| --- | --- |
| Firewood (Rural) | 90% |
| Charcoal (Urban) | 38% |
| Kerosene (Lighting) | 28% |
| Electricity Access (Households) | 18% |
| Solar (Private providers) | Low but growing |

2.3.4 ICT Infrastructure and Services

ICT services in Kitagwenda are moderately developed. MTN and Airtel provide mobile coverage across most trading centres such as Nyabani, Kabujogera, and Kanara, supporting mobile money services, phone charging businesses, and small ICT-based enterprises.

However, remote sub-counties like Bukurungo and Mahyoro face weak or inconsistent signal strength, limiting access to digital services. While mobile phone ownership is widespread, smartphone usage and internet access remain low due to high costs.

The District ICT office is under resourced, and most schools lack functional computer labs. Digital literacy is especially low among rural youth and women. As a result, ICT is not yet fully integrated into education, agriculture extension, and local government service delivery.

Potential exists to improve ICT penetration through public–private partnerships, investments in ICT labs in secondary schools, and establishment of community ICT centres in Nyabani and Kabujogera.

2.3.5 Financial Services

Access to financial services in Kitagwenda is limited. Kitagwenda Town Council and Kanara S/C host a few SACCOs and microfinance institutions, but most rural residents depend on Village Savings and Loan Associations (VSLAs), rotating savings groups (ROSCAs), and cooperative societies.

Formal banking coverage is very low, with residents often traveling to Ibanda or Kamwenge for commercial bank services. Mobile banking and agent banking are slowly spreading through different centres but their impact is constrained by low financial literacy and poor telecom connectivity in rural areas. Youth and women entrepreneurs face challenges in accessing affordable credit due to lack of collateral and high interest rates. This limits investment in agro-processing, fisheries, and small-scale businesses despite growing demand for financial services.

Table 2.7: Financial Services Access Indicators

| Indicator | Status |
| --- | --- |
| Number of SACCOs and MFIs | Moderate - concentrated in Kitagwenda Town Council |
| Access to formal banking (rural) | Very low |
| Financial literacy among population | Low |
| Common alternative | Village Savings and Loan Associations (VSLAs) |

2.5 Social Infrastructure and Services

2.5.1 Education

Kitagwenda District follows Uganda’s national education framework, encompassing Early Childhood Development (ECD), primary, secondary, and BTVET. Progress has been made in expanding access, especially in Nyabani Town Council and Kabujogera, but remote sub-counties like Nkoma and Magoma continue to face challenges in infrastructure, teacher shortages, and long travel distances for learners.

At the primary level, Kitagwenda has 92 schools, with 68 government-aided, 8 community-based, and 15 privately owned. Rural schools face overcrowding, shortage of teachers’ houses, inadequate latrines, and limited access to safe water.

Table 2.12: Distribution of Schools by Category and Ownership – Kitagwenda

| Category | Government | Private | Total |
| --- | --- | --- | --- |
| ECD | 68 | 114 | 182 |
| Primary | 68 | 24 | 92 |
| Secondary | 8 | 14 | 22 |
| BTVET | 2 | 1 | 3 |
| Total | 146 | 153 | 299 |

The education sector in the district faces several challenges despite some commendable achievements. The current pupil enrollment stands at 41,577 learners, comprising 19,941 females and 21,636 males. The pupil–teacher ratio of 1:71 indicates a significant shortage of teachers, which affects effective learning and individual attention. Similarly, the pupil–textbook ratio of 1:10 and pupil–desk ratio of 1:6 reveal inadequacies in essential learning and seating materials, while the pupil–stance ratio of 1:55 highlights congestion in school sanitation facilities. Although the pass rate is relatively high at 94.5%, the completion rate remains low at only 31%, with a worrying dropout rate of 40%.

2.5.2 Health and Nutrition

Health services are delivered through a network of public, PNFP, and private health facilities. Kitagwenda has 1 HC IV (Ntara HCIV), 7 HC IIIs, and 15 HC IIs, with no general hospital within the district. Most referrals are made to Ibanda Hospital and Fort Portal Regional Referral Hospital.

The district has an estimated 39,956 women of childbearing age (15–49 years), contributing to about 9,890 pregnancies and 9,494 annual deliveries, as well as 8,505 children under one year, indicating significant demand for maternal and child health services. Despite this need, access to healthcare remains a challenge, with 4 entities including: - Ruhunga S/C, Kicheche S/C, Mahyoro S/C and Ntara S/C out of the 13 administrative units lacking public health facilities highlighting critical gaps in service delivery and the need for targeted health infrastructure investment across the district.

Table 2.14: Distribution of Health Facilities by Level and Ownership

| Facility | Govt | PNFP | PFP | NGO | Total |
| --- | --- | --- | --- | --- | --- |
| General Hospital | 0 | 0 | 0 | 0 | 0 |
| HC IV | 1 | 0 | 0 | 0 | 1 |
| HC III | 6 | 1 | 0 | 0 | 7 |
| HC II | 12 | 2 | 2 | 0 | 15 |
| Total | 19 | 2 | 2 | 0 | 23 |

Malaria is the leading cause of outpatient visits, followed by respiratory infections, diarrhoea, and skin diseases. Non-communicable diseases such as hypertension and diabetes are also increasing in trading centres.

Table 2.15: Top 10 Causes of OPD Attendance

| No | Condition | Male | Female | Total | % |
| --- | --- | --- | --- | --- | --- |
| 1 | Malaria | 18,200 | 21,900 | 40,100 | 39% |
| 2 | Respiratory Infections | 7,600 | 9,200 | 16,800 | 16% |
| 3 | Diarrhoea | 2,300 | 2,700 | 5,000 | 5% |
| 4 | Gastrointestinal | 2,800 | 3,400 | 6,200 | 6% |
| 5 | Skin Diseases | 1,400 | 2,200 | 3,600 | 3% |
| 6 | Hypertension | 740 | 1,400 | 2,140 | 2% |
| 7 | UTIs | 620 | 1,200 | 1,820 | 2% |
| 8 | Intestinal Worms | 880 | 770 | 1,650 | 2% |
| 9 | Diabetes | 370 | 660 | 1,030 | 1% |
| 10 | Injuries/Accidents | 610 | 520 | 1,130 | 1% |
| Total | 35,920 | 43,650 | 79,570 | 100% |  |

Challenges include drug stockouts, inadequate health workers, shortage of ambulances, and long distances to facilities. Maternal health services are constrained by insufficient equipment and under-staffing.

2.5.3 Water, Sanitation and Hygiene (WASH)

Access to safe water in Kitagwenda is estimated to be at 66.5% (District water dept.). Greater Nyabbani, Mahyoro and Ntara sub counties are still water stressed and are the sub counties below the district water average of 65.5%. The district is promoting partnership collaborations in partnership with Midwest Umbrella is implementing Ntara-Kichwamba piped water supply system to serve a population of 16,634 in Ntara sub county and neighboring communities.

River and lake surface water are the most reliable sources that can supply sufficient water to these communities of which require expensive technology to invest in. This has remained a challenge considering the small budget allocated to the District and limited support partners in the district.

Functionality water systems in the district stands at 75.0% as per Ministry of Water and Environment Sector MIS website. This low functionality is attributed to: - Elapsed service life span of some WASH facilities and negligence and breach of duty of care of water user committees, local councils and community members

Table 2.16: Water access by Sub-county

| No. | Sub counties | % Water Access based on MWE MIS database | Estimated % Water Access |
| --- | --- | --- | --- |
| 1 | Buhanda & Kakaasi | 95 | 78 |
| 2 | Kanara | 84 | 82 |
| 3 | Kicheche and Ruhunga | 95 | 70 |
| 4 | Mahyoro | 69 | 42 |
| 5 | Ntara | 95 | 67 |
| 6 | Nyabbani and Rwenjaza | 61 | 49 |
| 7 | Kitagwenda Town Council | Data not available | Data not available |
| 8 | Kabujogera Town Council | Data not available | Data not available |
| 9 | Mahyoro Town Council | Data not available | Data not available |
| 10 | Bukulungo Town Council | Data not available | Data not available |
|  | Access | 83 | 66.5 |

Sanitation

The district is likely to face challenges related to poor latrine coverage, unsafe water use, and weak hygiene practices, especially in underserved communities. The absence of nearby health facilities in some entities limits regular community sensitization on sanitation, increasing the risk of waterborne and hygiene-related diseases.  The latrine coverage in the district is 90.16% and handwashing coverage is 52.2%. The ODF coverage in the district stands at 31,2% with 111 villages affected by ODF.

A number of activities have been carried out to improve the situation with support from UNICEF, new funding from Conditional Grant (Hygiene and Sanitation Grant) and also with support from our Development Partners like, JESE, HEWASA.

The District has geographical challenges specifically in the low land areas of the rift valley and along the lake shores. Traditional latrines have failed due to highly collapsible soils and highwater table. In addition, the migratory nature of the fishing community requires consistent engagement with the households to maintain good sanitation and hygiene behavior. However, lined pit latrines are highly promoted at institutional level and HPMAs have acquired skills and equipment for manual pit emptying and sludge management.

The District anticipates to access the Faecal Sludge Treatment plant constructed at Ishongororo in the nearby district of Ibanda currently under construction for disposal of sludge. However, the mechanical emptying and transport facilities for human waste such as cesspool emptiers are still a major challenge affecting management of waste in the entire district. Despite the management of selected areas by NWSC or Umbrella Authority as water supply and sewerage areas, the district still lacks a sewerage management plant in the main Town Councils.

The District has got many rural growth centers which have attracted a big business community leading to generation of solid WASTE. These communities require to be supported technically and financially to be able to effectively manage their WASTES.

Table 2.16: Sanitation Status by Sub-county

| Sub county | Latrine Coverage % | Hand washing coverage % | ODF coverage % of villages that are ODFs |
| --- | --- | --- | --- |
| Kanara Sub County | 86% | 57% | 8 villages (33.3%) |
| Nyabbani Sub County | 96% | 50% | 14 villages (36.8%) |
| Rwenjaza Sub County | 90% | 65% | 4 villages (25%) |
| Kitagwenda TC | 90% | 70% | 2 villages (7.1%) |
| Ntara Sub County | 87.2% | 62.4% | 3 villages (15.5%) |
| Buhanda Sub County | 92% | 90% | 12 villages (46.1) |
| Kabujogera TC | 91.4% | 78% | 12 villages (44.2%) |
| Kicheche Sub County | 93.4% | 63% | 13villages (37.1%) |
| Ruhunga Sub County | 92% | 70% | 19 villages (100 %) |
| Mahyoro sub county | 81.3% | 66.3% | 1village (2.4%) |
| Bukurungo TC | 92.5% | 86% | 6villages (36.6%) |
| Kakasi Sub County | 87.5% | 55% | 5villages (14.3%) |
| Mahyoro TC | 89.4% | 90% | 12villages (52%) |
| District Average | 90.16% | 52.2% | 111villages (31.2%) |

2.5.4 Social Protection and Community Mobilization

National programmes like SAGE, UWEP, and YLP operate in the district, but coverage is limited by low awareness, delayed funding, and weak follow-up mechanisms. Fishing communities in Mahyoro TC and Bukurungo TC have high demand for social support but remain underserved.

Rapid population growth (about 2.6% per annum) and emerging urbanization in Nyabani and Kabujogera and Kitagwenda TC are placing pressure on education, health, and social services. Many facilities remain inaccessible to PWDs, limiting inclusivity.

Staffing and Institutional Capacity

The approved staffing structure for Kitagwenda stands at about 1,150 positions, but only 760 are filled, translating to a staffing level of 66%. Critical shortages exist in health, engineering, planning, Health and Education including the newly created Lower Local Governments. Many Heads of Departments serve in acting capacity, undermining stability and coordination.

Attrition is high, with health workers and teachers often leaving for better-paying opportunities in urban districts. At the lower government level, many parishes lack CDOs and extension workers, which weakens implementation of the Parish Development Model (PDM).

Local Revenue Position

Local revenue in Kitagwenda District remains relatively low compared to total district financing, with the district heavily dependent on central government transfers. For instance, in FY 2023/24, locally raised revenue was projected at about UGX 718 million out of a total budget exceeding UGX 21.9 billion, indicating that local revenue contributes only a small share of overall funding.

However, the district has made efforts to improve local revenue performance through reforms such as the introduction of the Integrated Revenue Administration System (IRAS) and expansion of revenue sources like property tax to sub-counties, which were previously untapped. These measures have begun to enhance efficiency and slightly improve collections, but overall performance remains constrained by the district’s predominantly rural economy, where about 80% of the population depends on agriculture, limiting taxable income. Strengthening local revenue will therefore require broadening the tax base, formalizing businesses, and investing in local economic development to increase household incomes and revenue potential.

Governance and Fiscal Management

Governance in Kitagwenda is constrained by understaffing, limited financing, and weak community participation. Most sub-county councils struggle to hold regular meetings due to limited facilitation, weakening accountability.The Administration Department, headed by the Chief Administrative Officer (CAO), coordinates service delivery but faces major challenges in supervision due to inadequate transport, weak ICT systems, and constrained operational budgets.

Despite the critical role it plays, the department is constrained by logistical gaps, limited funding, and staffing shortages, which compromise its capacity to enforce laws, supervise service units, and provide timely technical support to lower local governments.

Table 1: Staffing structure and staffing level by functions

| POSITION | ESTABLISHMENT | FILLED | VACANT |
| --- | --- | --- | --- |
| CAO's OFFICE |  |  |  |
| Chief Administrative Officer | 1 | 1 | 0 |
| Personal Secretary | 1 | 1 | 0 |
| Driver | 1 | 1 | 0 |
| ADMINISTRATION |  |  |  |
| Deputy Chief Administrative Officer | 1 | 1 | 0 |
| Principal Assistant Secretary | 1 | 0 | 1 |
| Principal Human Resource Officer | 1 | 1 | 0 |
| Senior Assistant Secretary | 2 | 2 | 0 |
| Assistant Secretary | 1 | 1 | 0 |
| Senior IT Officer | 1 | 1 | 0 |
| Information tech officer | 1 | 0 | 1 |
| Senior Records Officer | 1 | 1 | 0 |
| Senior Human Resource Officer | 1 | 1 | 0 |
| Human Resource Officer | 1 | 1 | 0 |
| Records Officer | 1 | 0 | 1 |
| Information Officer | 1 | 1 | 0 |
| Assistant Records Officer | 1 | 1 | 0 |
| Senior Office Supervisor | 1 | 0 | 1 |
| Office Supervisor | 1 | 1 | 0 |
| Cameraman | 1 | 1 | 0 |
| Stenographer Secretary | 2 | 1 | 1 |
| Pool Stenographer | 3 | 0 | 3 |
| Office Typist | 1 | 1 | 0 |
| Office Attendant | 3 | 2 | 1 |
| Senior Procurement Officer | 1 | 1 | 0 |
| Procurement Officer | 1 | 1 | 0 |
| STATUTORY |  |  |  |
| Principal Human Resource Officer | 1 | 1 | 0 |
| Senior Assistant Secretary | 1 | 0 | 1 |
| Stenographer Secretary | 1 | 0 | 1 |
| Assitant Records Officer | 1 | 0 | 1 |
| Driver | 1 | 0 | 1 |
| Office Typist | 2 | 1 | 1 |
| office Attendant | 3 | 2 | 1 |
| FINANCE |  |  | 0 |
| Chief Finance Officer | 1 | 1 | 0 |
| Senior Accountant | 1 | 1 | 0 |
| Senior Finance Officer | 1 | 1 | 0 |
| Finance Officer | 1 | 1 | 0 |
| Accountant | 1 | 1 | 0 |
| Senior Accounts. Assistant. | 5 | 3 | 2 |
| Assistant Inventory Mgt Officer | 1 | 0 | 1 |
| Accounts Assistant | 2 | 0 | 2 |
| Office Typist | 1 | 0 | 1 |
| office Attendant | 1 | 1 | 0 |
| Driver | 1 | 1 | 0 |
| PLANNING |  |  |  |
| District Planner | 1 | 1 | 0 |
| Senior Planner | 1 | 0 | 1 |
| Planner | 1 | 1 | 0 |
| Assistant Statistical Officer | 1 | 1 | 0 |
| Office Typist | 1 | 1 | 0 |
| Office Attendant | 1 | 1 | 0 |
| Driver | 1 | 0 | 1 |
| EDUCATION |  |  |  |
| District Education Officer | 1 | 1 | 0 |
| Senior Education Officer | 1 | 1 | 0 |
| Senior inspector schools | 1 | 1 | 0 |
| Sports Officer | 1 | 1 | 0 |
| Inspector of Schools | 5 | 5 | 0 |
| Education Officer (Special Needs) | 1 | 1 | 0 |
| Office Typist | 1 | 1 | 0 |
| Office Attendant | 1 | 1 | 0 |
| Driver | 1 | 1 | 0 |
| TRADE, INDUSTRY & LED |  |  |  |
| District Commercial Officer | 1 | 1 | 0 |
| Principal Commercial Officer | 1 | 0 | 1 |
| Senior Commercial Officer | 1 | 0 | 1 |
| Commercial Officer | 1 | 1 | 0 |
| Tourism Officer | 1 | 0 | 1 |
| Wildlife Officer | 1 | 0 | 1 |
| PRODUCTION |  |  |  |
| District Production & Mkt Off | 1 | 1 | 0 |
| Principal Agricultural Officer | 1 | 0 | 1 |
| Principal Veterinary Officer | 1 | 1 | 0 |
| Principal Fisheries Officer | 1 | 0 | 1 |
| Principal Entomologist | 1 | 0 | 1 |
| Senior Agricultural Officer | 1 | 0 | 1 |
| Senior Veterinary Officer | 1 | 1 | 0 |
| Sen. Fisheries Officer | 1 | 1 | 0 |
| Senior Agricultural Engineer | 1 | 1 | 0 |
| Animal Husbandry Officer | 1 | 0 | 1 |
| Vermin Control Officer | 1 | 1 | 0 |
| Agricultural Engineer | 1 | 0 | 1 |
| Laboratory Technician | 1 | 1 | 0 |
| Assistant Inventory Officer | 1 | 0 | 1 |
| Laboratory Attendant | 1 | 0 | 1 |
| Agricultural Officer | 3 | 3 | 0 |
| Assistant Agricultural Officer | 3 | 3 | 0 |
| Assistant Veterinary Officer | 4 | 3 | 1 |
| Fisheries Officer | 3 | 3 | 0 |
| Fisheries Officer (Aqua culture) | 1 | 1 | 0 |
| Entomologist | 1 | 0 | 1 |
| Entomological Attendat | 1 | 0 | 1 |
| Stenographer Secretary | 1 | 0 | 1 |
| Stores Assistant | 1 | 0 | 1 |
| Office Typist | 1 | 0 | 1 |
| Office Attendant | 2 | 1 | 1 |
| WORK & TECHNICAL DEPT |  |  |  |
| District Engineer | 1 | 0 | 1 |
| Senior Civil Eng. | 1 | 0 | 1 |
| Supt. Of Works | 1 | 0 | 1 |
| Sen Asst. Eng. Officer | 1 | 1 | 0 |
| Sen. Water Officer | 1 | 1 | 0 |
| Civil Engineer | 1 | 1 | 0 |
| Asst. Eng. Officer | 1 | 1 | 0 |
| Asst. Eng. Officer (Water) | 1 | 1 | 0 |
| Asst. Eng. Officer (DECh) | 1 | 1 | 0 |
| Pool Stenographer | 1 | 0 | 1 |
| Bore hole maint. Tech. | 1 | 0 | 1 |
| Health Assistant | 1 | 0 | 1 |
| Office Typist | 2 | 2 | 0 |
| Office Attendant | 2 | 1 | 1 |
| Driver | 6 | 6 | 0 |
| Machine Operator | 4 | 2 | 2 |
| NATURAL RESOURCE |  |  |  |
| District Natural Resource Officer | 1 | 1 | 0 |
| Senior Land Management Officer | 1 | 1 | 0 |
| Senior Environment Officer | 1 | 1 | 0 |
| Environment Officer | 1 | 0 | 1 |
| Staff Surveyor | 1 | 1 | 0 |
| Forest Officer | 1 | 1 | 0 |
| Land Mgt Officer | 1 | 0 | 1 |
| Physical Planner | 1 | 1 | 0 |
| Assistant Forestry Oficer | 1 | 0 | 1 |
| Senior Accounts Assistant | 1 | 1 | 0 |
| Forest Ranger | 2 | 2 | 0 |
| Driver | 1 | 1 | 0 |
| AUDIT |  |  |  |
| Principal Internal Auditor | 1 | 1 | 0 |
| Internal Auditor | 2 | 1 | 1 |
| Stenographer Secretary | 1 | 1 | 0 |
| office Attendant | 1 | 1 | 0 |
| COMMUNITY BASED |  |  |  |
| Dist. Comm Development Officer | 1 | 1 | 0 |
| Sen. Comm. Dev't Officer | 1 | 1 | 0 |
| Sen. Prob & Welfare Officer | 1 | 0 | 1 |
| Labour Officer | 1 | 1 | 0 |
| Office Typist | 1 | 0 | 1 |

Staffing, Administration, and Supervision

Low staffing levels in Kitagwenda District are closely linked to high attrition, especially among health workers and engineers, who are drawn to better opportunities in larger urban centres and at national-level agencies. Budget constraints have further limited the District’s ability to make internal transfers, effect promotions, or equip public officers with adequate tools and workspaces-eroding staff morale and productivity.

At the lower local government (LLG) levels-parishes and villages-several administrative units are not fully functional due to the absence of critical personnel such as Extension workers and Community Development Officers (CDOs). This has undermined rollout of community-facing programmes, notably the Parish Development Model (PDM), where limited technical backstopping and coordination capacity at the grassroots persist. Monitoring and supervision of decentralized service delivery remain constrained by inadequate transport and facilitation for field visits. This affects timely reporting and enforcement of service standards. In several sub-counties, leadership struggles to convene regular council meetings due to tight operational budgets-weakening local-level planning, citizen feedback, and accountability.

2.6 Environmental Situation

Kitagwenda District is increasingly experiencing environmental stress arising from rapid population growth, expansion of farming into fragile ecosystems, and unregulated exploitation of natural resources. Located within the Albertine Rift agro-ecological zone, Kitagwenda hosts a mix of savannah, wetlands, and aquatic ecosystems around Lake George.

There are several hills and streams in the district that are fertile and favours banana and coffee growing especially in the areas of Kigoto, Kagazi, Nganiko, Kikondo, Nsinda and other escarpments sloping to Lake George and valleys and plains that make a beautiful scenery across the district. The district lies at an altitude ranging from 1,300- 3,800 meters above sea level. It is crossed by the equator through Lake George and Kitagwenda Town Council.

The climatic description of Kitagwenda is based on Western Region climatic zone. It receives bimodal rainfall (March-May and August-November) estimated at 700-1,400mm annually with temperatures ranging from 20-25 degrees delicious. August- November is the main production season for agricultural activities.

The vegetation of Kitagwenda is typically savannah grassland, shrubs and some pockets of forests with black loam soils, sandy and clay as the main soil types on which all flora and fauna survive. Thick tropical forest cover remains intact in Kakasi Forest Reserve, (Uganda Wildlife Authority), Kitomi-Kasyoha Forest Reserve (NFA), otherwise most of the natural forests which were not under government ownership were depleted and are farmlands. Natural vegetation remains intact in Queen Elizabeth National Park. It’s important to note that River Mpanga and Lake George are synonymous with ecological balance in regard to all flora and fauna and potential tourism assets where cycads, hydro power generation and fish breeding are key strategic areas of environmental protection by all agents of government to ensure that there is sustainable development in the area. It is important to note that Lake George is a Ramseur Site and deserves high priority protection as an international asset.

2.6.1 Forests

Kitagwenda hosts several local forest reserves and community-managed woodlots that play a vital role in biodiversity conservation and community livelihoods. However, these are under threat from illegal logging, charcoal production, and agricultural encroachment.

Women and children often walk long distances to collect firewood, leading to loss of study time and exposure to risks. Degradation of these forests has led to loss of biodiversity, hotter local climates, and changes in rainfall distribution.

2.6.2 Wetlands

Kitagwenda District is endowed with over 46 wetlands in 3 wetland systems of River Mpanga, Dura and Lake George Ramsar site. The total land area of wetlands cover is 2327.6 ha of wetlands of these 966.16 representing 41.5% are still intact while the rest representing 58.5% are degraded. Restoration of degraded wetlands has been undertaken and 5 out of 46 wetlands covering 68kms and representing 10.8% of the total wetlands have been demarcated with concrete pillars.

Kitagwenda’s wetlands are critical for water purification, groundwater recharge, and fisheries. However, pressure from farming, brick-making, sand/clay extraction, and settlement has threatened their sustainability. Encroachment is worsened by weak enforcement of regulations and pollution from trading centres. Communities that depend on wetlands for fishing, grazing, and vegetable growing are increasingly vulnerable.

2.6.3 Waste Management

Solid and liquid waste management is a growing challenge in Kitagwenda, particularly in Nyabani, Kabujogera, and Kanara trading centres. Rising populations and economic activity have increased waste volumes, but the district lacks adequate collection and disposal systems.

Table 2.20: Stakeholders in Solid Waste Management

| People Involved | Activities | Challenges Faced |
| --- | --- | --- |
| Business Communities | Generate waste | Unregulated dumping, few skips/bins |
| Schools, Health Units, Churches | Generate waste | Poor segregation, inadequate collection |
| Municipal & Subcounty LGs | Collect & dispose | Poor equipment, limited budgets |
| Individual Households | Dispose waste | Burning, open dumping, low awareness |

Liquid waste is also problematic. Most residents rely on pit latrines and septic tanks, which flood during rainy seasons. Wastewater from fish markets, garages, and lodges in Kabujogera and Kanara is often discharged untreated into wetlands and open drains.

Figure 1: Organization Chart for District

District

Executive

Committee (DEC)

Internal Audit

Education and Sports

Council and Statutory Bodies

Administration (PAS, PHRO)

Planning

Natural Resources and Environment

Production and Marketing

Community-Based Services

Health

Works and Technical Services

Trade, Industry and LED

Sub-county Chiefs/Town Clerks

Parish Chiefs

Villages

Chief Administrative Office (CAO)

District

Deputy CAO

Finance

2.8 Synthesis of Development Issues for Kitagwenda District

The Kitagwenda district development issues can be described as follows: -

- Agriculture is the backbone of Kitagwenda’s economy, engaging over 75% of households, mainly in subsistence farming. However, productivity remains low due to: - Limited access to improved seeds and breeds, over-reliance on traditional tools, Low adoption of irrigation despite proximity to Lake George, River Mpanga, and the many wetlands in the District. Only 58 farmers have adopted the micro-scale irrigation.

- Post-harvest losses are high due to poor storage, minimal value addition, and lack of aggregation centres. Most farmers sell produce immediately after harvest at low farm-gate prices. Agro-processing is limited, with weak cooperatives, low access to agri-financing, and poor feeder roads restricting market access.

- Kitagwenda has strong potential for eco-tourism and cultural tourism, however these remain underdeveloped due to:- Poor access roads to potential sites,limited investment in lodges, signage, sanitation, and ICT connectivity, minimal promotion and weak coordination among stakeholders and Limited local capacity in guiding, crafts, and hospitality.

- Environmental degradation is intensifying and the drivers include: -Wetland encroachment around Lake George for farming and settlements, Deforestation for charcoal burning and firewood, Soil erosion on cultivated slopes and Overfishing & illegal nets reducing fish stocks in Lake George.

- Kitagwenda faces institutional and human resource capacity gaps at both district and LLG levels with over 34% of approved posts vacant. Recruitment is delayed, and many technical officers serve in acting capacities, stretching delivery.

- Supervision of programmes is limited by transport shortages, poor ICT connectivity, and underfunding. Implementation of national programmes like the Parish Development Model (PDM) is slowed by weak data systems, limited community mobilization, and poor alignment with local realities.

- Kitagwenda’s private sector is largely informal, dominated by petty trade, small-scale retail, fishing, and boda-boda transport. Businesses face challenges such as: -Lack of affordable credit and collateral, Low financial literacy, weak market infrastructure and linkages. This limits enterprise growth, job creation, and agro-processing potential.

- Low access to grid electricity.

- Growing urbanization that is largely unplanned and this comes with challenges such as Informal settlements thus leading to lack of piped water, poor drainage and poor waste management.

- Many schools are overcrowded and under-staffed. ECD coverage is low, and vocational training options are limited.

- Low staffing in the health sector Health centers are under-staffed, with long distances to facilities in rural areas. Drug stockouts and limited maternal care equipment persist. Family planning uptake is low

# CHAPTER 3: LOCAL GOVERNMENT DEVELOPMENT PLAN IV STRATEGIC DIRECTION

# 3.1	LOCAL GOVERNMENT DEVELOPMENT PLAN IV DIRECTION

This chapter presents the Strategic Direction of the plan, the macroeconomic and financing strategies. The strategic direction is the proposed key priority activities that have the greatest multiplier effects in order to achieve the Uganda Vision 2040.

# DISTRICT VISION AND MISSION

Kitagwenda District’s vision is: “A Transformed middle-income earning population with improved quality life in Kitagwenda by 2040”

The District’s mission is: “To provide effective and efficient equitable services to foster and stimulate socio-economic development to the people of Kitagwenda in conformity with national and local priorities”

Core Values:

Transparency, Accountability, Professionalism, Integrity, Partnership, and Impartiality

# 3.2	STRATEGIC DIRECTION

The theme of DDP IV is “Sustainable industrialization for inclusive growth, employment, and wealth creation in Kitagwenda district”

Goal: “Achieve higher household income, full monetization and employment for sustainable socio-economic transformation in Kitagwenda district”.

Strategic Objectives:

- To sustainably increase production, productivity and value addition in agriculture, industry, minerals, oil & gas, tourism, ICT and financial services;

- To enhance human capital development along the entire life cycle;

- To support the private sector to drive growth and create jobs;

- To build and maintain strategic sustainable infrastructure in transport, housing, energy, water, industry and ICT; and

- To strengthen good governance, security, and the role of the State in development.

# 3.3. ALIGNMENT OF LGDP DIRECTION WITH THE NDPIV PROGRAMMES

Government is putting much emphasis on Infrastructural development as an engine to growth and social economic transformation. Government will focus on implementing key development priorities over the next five years within the existing financial resource constraint, shifting from mere service delivery provision to wealth creation that will accelerate socio-economic transformation, continue to narrow infrastructure gap while promoting economic productivity and diversification for better service delivery in the districts following existing policy framework. The District will harmonize physical planning with socio-economic planning. This will be intended to attain the national vision of 2040 that aims at attaining “a transformed Ugandan society from a peasant to a modern and prosperous country within 30 years”

##### Table 3.1 Alignment of Kitagwenda District Development Plan Objectives and Strategies with the NDPIV programmes

| Strategic Objectives (a) | Strategies (b) | NDPIV Programme (s) |
| --- | --- | --- |
| 1. Sustainably increase production, productivity and value addition in agriculture, industry, tourism, minerals, oil & gas, ICT and financial services. | - Increase Production and Productivity in agriculture, tourism and financial services. - Increase Value Addition in agriculture and tourism | - Agro-Industrialization - Tourism Development - Land, Natural Resources, Climate Change and ENR Management |
| 2. Enhance human capital development along the entire life cycle | - Improve access, equity, and quality of education at all levels, - Improve Access, Equity and Quality of Healthcare at all Levels - Rehabilitate, Equip and Construct Health Infrastructure at all levels - Enhance access to water, sanitation, and hygiene. - Promote Community Mobilization and Mindset change - Expand Social Protection Safety nets - Institutionalize Manpower Planning and Promote Industry-driven Skilling and Training - Promote empowerment and livelihood for programmes youth, women, children, elder persons, and People with Disabilities (PWDs).; - Promote decent employment opportunities - Leverage the culture and creative economy for employment and domestic resource mobilization; - Promote Games and Sports; - Promote better nutrition for all | - Human Capital Development - Regional Development |
| 3. Strengthen private sector capacity to drive growth and create jobs | - Reduce the Cost of doing Business - Strengthen Public-Private Partnerships - Inculcate the entrepreneurship mindset and educate the population to invest in productive sectors like agriculture | - Private Sector Development |
| 4. Build and maintain strategic Sustainable infrastructure in transport, housing, energy, water, industry and ICT | - Prioritize Infrastructure Maintenance - Increase Access to Clean, Reliable and Affordable Energy - Leverage Urbanization for Socio-economic Transformation | - Integrated Transport Infrastructure and Services - Sustainable Urbanisation and Housing |
| 5. Strengthen good governance, security, and the role of the state in development. | - Strengthen the Rule of law - Increase local government investment and Participation in Strategic Areas - Improve Capacity and Accountability for Implementation of Public Programmes - Leverage Capacity of the Non-State Actors to Implement the District - Increase civic participation in the development process, decision making, democratic governance, and socioeconomic development | - Governance and Security - Legislature, Oversight and Representation - Public Sector Transformation - Development Plan Implementation |

# 3.4. LOCAL GOVERNMENT DEVELOPMENT PLAN IV DEVELOPMENT RESULTS AND TARGETS

To focus implementation on delivery of common results, strengthen the alignment of the DDP IV to the NDP IV, reduce the silo approach and enhance synergies across sectors, key development results have been identified to provide a coordinated framework for implementation and monitoring the development plan as shown in the following tables.

##### Table 3.2 Kitagwenda District Development Plan Development Results and Targets

| Level | Key Results (Impacts for Goal and Outcomes for the Objectives) | Indicators | Baseline | LGDP Targets |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2023/24 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |
| Goal: Achieve higher household income, full monetization and employment for sustainable socio-economic transformation | Impact 1: Higher household incomes in the district | Average monthly nominal household income (UGX) | 200,000 | 276,000 | 351,000 | 427,000 | 503,000 | 578,000 |
|  | Impact 2: Lower the percentage of households in the subsistence economy in the district | % of households in the subsistence economy | 40% | 38% | 36% | 34% | 32% | 30% |
| Strategic Objective 1: Sustainably increase production, productivity and value addition in agriculture, industry, tourism, minerals, oil & gas, ICT and financial services | Outcome 1.1: Increased volume and yield of priority agricultural commodities in the district | Percentage change in volume and yield of priority agricultural commodities | 25 | 30 | 35 | 40 | 45 | 50 |
|  |  | Proportion of the household that is food insecure | 28.4 | 23.4 | 18.4 | 13.4 | 8.4 | 3.4 |
|  | Outcome 1.2: Increased value addition (harvesting, post-harvest handling and storage) in agriculture | Percentage reduction in harvesting, post-harvest handling and storage losses | 40 | 35 | 30 | 25 | 20 | 15 |
|  | Outcome 1.3: Increased tourism, services in the district | Percentage improvement in tourism infrastructure | 5 | 10 | 15 | 20 | 25 | 30 |
| Strategic Objective 2: Enhance human capital development along the entire life cycle | Outcome 2.1: Improved learning outcomes and acquired skills relevant to the job market | Literacy rates | 56 | 58 | 60 | 62 | 64 | 66 |
|  |  | Numeracy | 60 | 62 | 65 | 68 | 70 | 72 |
|  |  | Performance index | 80 | 82 | 84 | 85 | 86 | 88 |
|  |  | Completion rate | 65 | 68 | 70 | 72 | 75 | 77 |
|  |  | Survival rate primary | 80 | 81 | 82 | 83 | 84 | 85 |
|  |  | Survival rate secondary | 72 | 75 | 77 | 80 | 82 | 84 |
|  | Outcome 2.2 Improved quality of life: | Maternal mortality ratio/1000 | 189 | 179 | 168 | 165 | 152 | 145 |
|  |  | Infant mortality rate /1000 | 41 | 38 | 35 | 30 | 25 | 20 |
|  |  | U5 mortality ration /1000 | 147 | 138 | 135 | 129 | 125 | 120 |
|  |  | Neo-natal mortality rate/1000 | 27 | 26 | 25 | 18 | 16 | 15 |
|  |  | Proportion of deliveries conducted in government health facilities | 73% | 75% | 78% | 80% | 82% | 85% |
|  | Outcome 2.3 Improved access to services for social care, protection, safety and equity | Access to rural safe water | 61% | 65% | 67% | 69% | 72% | 75% |
|  |  | Sanitation coverage | 74.5% | 76.5% | 78.5% | 80.5% | 82.5% | 84.5% |
|  |  | Hygiene (hand washing) | 30.4% | 35.4% | 40.4% | 45.4% | 50.4% | 55.5% |
|  |  | Proportion of the population accessing social insurance | 33% | 37% | 40% | 50% | 60% | 70% |
|  |  | Percentage of the population receiving direct income support | 30% | 33% | 37% | 52% | 60% | 70% |
|  |  | Gender inequality | 60% | 63% | 70% | 70% | 80% | 90% |
|  |  | Proportion of the population with access to social care services | 57% | 60% | 70% | 70% | 80% | 90% |
| Strategic Objective 3: Strengthen private sector capacity to drive growth and create jobs | Outcome 3.1 Conducive environment for private sector investment is created, firms are competitive and meet national, regional and international standards | Percentage of the informal sector |  | 5% | 5% | 5% | 5% | 5% |
|  |  | Growth in private sector credit |  | 40 | 40 | 30 | 30 | 20 |
|  |  | Transition rate of MSMEs |  | 2 | 2 | 2 | 2 | 2 |
|  | Outcome 3.2: Youth, women and other categories of the labour force is empowered, innovate, develop enterprises and create decent jobs | Youth employed | 3415 | 10 | 10 | 10 | 10 | 10 |
|  |  | Number of annual jobs created | 3415 | 15 | 15 | 15 | 15 | 15 |
| Strategic Objective 4: Build and maintain strategic Sustainable infrastructure in transport, housing, energy, water, industry and ICT | Outcome 4.1: Improved transport services, connectivity and cost effectiveness usability | Percentage of district roads in fair to good condition | 60% | 62% | 64% | 66% | 68% | 70% |
|  | Outcome 4.2: Increased land under irrigation | Cumulative WFP area under irrigation (acres) | 80 | 104 | 135 | 175 | 228 | 297 |
| Strategic Objective 5: Strengthen good governance, security, and the role of the state in development. | Outcome 5.1: Increased Peace, Stability, accountability and civic participation | Corruption perception index (100 being the best) | 26 | 36 | 46 | 56 | 66 | 76 |
|  | Outcome 5.2: Increased government effectiveness, access to public goods & services, and good image | Level of public satisfaction with service delivery |  | 60% | 70% | 80% | 85% | 90% |

## 3.4	LOCAL GOVERNMENT DEVELOPMENT PLAN IV PROGRAMMES

Strategic Objective 1: Sustainably increase production, productivity and value addition in agriculture, industry, tourism, minerals, oil & gas, ICT and financial services.

3.5.1. Programme 1: Agro-Industrialization

The Agro-industrialization programme aims to address key development challenges related to low value addition to agricultural products, among others. The key focus areas are: establishment of value addition infrastructure; harvest and post-harvest handling; enhancing production and competitiveness of agricultural products for domestic, regional and international markets; strengthening specialized extension services; strengthening the adoption and integration of STI in agriculture; strengthening farmers field schools and cooperatives; de-risking agro-industry; eliminating counterfeits & low quality agro-inputs; and strengthening coordination, legal, and institutional framework for agro-industry.

##### Table 3.3 Programme Results and Targets for Agro-Industrialization

| Programme (a): | Outcome (b) | Indicator (c) | FY2023/24 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Sustainably increase production and productivity in agriculture. | Outcome 1.1: Increased yield of priority agricultural commodities | Outcome Indicator 1.1.1: Percentage change in yield of priority agricultural commodities | 25 | 30 | 35 | 40 | 45 | 50 | Production Statistical Abstract |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Increased production volumes of priority agricultural commodities | Intermediate Outcome Indicator 1: Percentage in in production volumes (MT) of priority agriculture commodities (Coffee, Dairy, Fish, Hass avocado, Honey and Oil seed crops) | 5 | 10 | 20 | 30 | 40 | 50 | Production statistical abstract |
|  | Intermediate Outcome 1.2: Increased adoption of improved agricultural technologies | Intermediate Outcome Indicator 1: Percentage of farmers adopting improved agricultural technologies | 10 | 15 | 20 | 25 | 30 | 40 | Production statistical abstract |
|  |  | Intermediate Outcome Indicator 2: Percentage of farmers accessing and using labor saving technologies by type (tractors, draught animal power, chaff cutters, etc) | 15 | 20 | 25 | 30 | 35 | 40 | Production statistical abstract |
|  | Intermediate Outcome 1.3: Reduced occurrence of crop pests, livestock vectors and diseases for crops, livestock and fisheries | Intermediate Outcome Indicator 1: Prevalence of crop pest and diseases | 40 | 35 | 30 | 25 | 20 | 15 | Production statistical abstract |
|  |  | Intermediate Outcome Indicator 2: Prevalence of livestock vectors and diseases | 30 | 25 | 20 | 15 | 10 | 5 | Production statistical abstract |
|  |  | Intermediate Outcome Indicator 3: Number of pests, vectors and diseases surveillance and outbreak investigations undertaken | 6 | 6 | 6 | 6 | 6 | 6 | Production statistical abstract |
|  | Intermediate Outcome 1.4: Increase smallholder farmers’ resilience to shocks of climate change effects | Intermediate Outcome Indicator 1: Percentage of farmers adopting sustainable land management and climate smart agricultural practices | 5 | 10 | 15 | 20 | 25 | 30 | Production statistical abstract |
|  | Intermediate Outcome 1.5: Increase access to agricultural extension services | Intermediate Outcome Indicator 1: Percentage of farming households accessing agricultural extension services | 4 | 7 | 9 | 12 | 15 | 17 | Production statistical abstract |
| Intervention (d) | Key Output (e) | Indicator (f) | Time Frame and Output Target |  |  | Data Source |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |  |
| Intervention 1.1: Increase uptake of quality seed and other inputs | Output 1.1.1: Quality seed and other agricultural inputs accessed by, and/or provided to, farmers | Output Indicator 1: Number of farmer groups provided with quality seed and other inputs for demonstration purpose | 40 | 40 | 40 | 40 | 40 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 2: Number of compliance inspections undertaken at the crop related agro-input dealers and premises | 4 | 4 | 4 | 4 | 4 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 3: Number of compliance inspections undertaken at the livestock related agro-input dealers and premises | 4 | 4 | 4 | 4 | 4 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 4: Number of Coffee mother gardens established in Kitagwenda | 1 | 1 | 1 | 1 | 1 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 5: Number of smallholder farming households supported with good planting materials for Coffee, Hass avocado, Soybean, Pasture, etc | 40 | 40 | 40 | 40 | 40 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 6: Number of smallholder farming households supported with improved breeds of Pigs, Poultry, Dairy heifers, Beef bulls, etc | 23 | 40 | 40 | 40 | 40 | QPRs | KDLG, MAAIF, Private Sector |
| Intervention 1.2: Investment in the aquaculture development | Output 1.2.1: Aquaculture production promoted | Output Indicator 1: Number of aquaculture surveys conducted | 2 | 2 | 2 | 2 | 2 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 2: Number of fish ponds established under the guidance of Fisheries Officers | 14 | 21 | 28 | 35 | 42 | QPRs | KDLG, MAAIF, Private Sector |
|  |  | Output Indicator 3: Number of fish farmers supported with fingerlings and associated feeds | 10 | 10 | 10 | 10 | 10 | QPRs | KDLG, MAAIF, Private Sector |
| Intervention 1.3: Increase access to and use of water for agricultural production | Output 1.3.1: On-farm water for production infrastructure established | Output Indicator 1: Number of solar powered small scale irrigation systems for demonstration and crop production established | 69 | 69 | 69 | 69 | 69 | QPRs | Farmers, Local Government, MAAIF, MWE, Private Service Providers. |
| Intervention 1.4: Pest, vector and disease diagnosis and control | Output 1.4.1: Pest, vector and disease diagnosis and control infrastructure established and capacity enhanced | Output Indicator 1: Number of mini-diagnostic laboratories for pest, vector and disease control and post-mortem constructed and equipped | 1 | 0 | 0 | 0 | 0 | QPRs | Local Government, MAAIF, Private Sector Service Providers. |
|  |  | Output Indicator 2: Number of communal cattle dip tanks re-constructed and/or rehabilitated | 0 | 0 | 0 | 2 | 0 | QPRs | Local Government, MAAIF, Private Sector Service Providers. |
|  |  | Output Indicator 3: Number of existing communal cattle crushes equipped with foot bucket spray pumps and acaricide | 0 | 0 | 6 | 0 | 0 | QPRs | Local Government, MAAIF, Private Sector Service Providers. |
|  |  | Output Indicator 4: Number of treated tsetse fly traps acquired and deployed in high risk areas | 0 | 0 | 500 | 500 | 500 | QPRs | Local Government, MAAIF, Private Sector Service Providers. |
|  |  | Output Indicator 5: Number of extension staff trained in integrated pest, vector and disease control | 42 | 42 | 42 | 42 | 42 | QPRs | Local Government, MAAIF, NARO |
|  |  | Output Indicator 6: Number and type (FMD, Rabies, PPR, etc) of vaccine doses acquired and administered | 20,000 | 20,000 | 20,000 | 20,000 | 20,000 | QPRs | Local Government, MAAIF |
| Intervention 1.5: Strengthen agricultural extension system | Output 1.5.1: Agricultural extension staff recruited | Output Indicator 1: Number of agricultural extension staff recruited | 26 | 26 | 26 | 26 | 26 | QPRs | Local Government, MAAIF, MOLG, MOPS |
|  | Output 1.5.2: Agricultural extension staff equipped and facilitated | Output Indicator 2: Number of agricultural extension staff equipped and facilitated | 66 | 92 | 118 | 144 | 170 | QPRs | Local Government, MAAIF |
|  | Output 1.5.3: Agricultural extension staff trained | Output Indicator 3: Number of agricultural extension staff trained | 66 | 92 | 118 | 144 | 170 | QPRs | Local Government, MAAIF, MAAIF Agencies, Private sector |
|  | Output 1.5.4: On-farm result-based demonstrations established and maintained | Output Indicator 4: Number of on-farm result-based demonstrations established and maintained for farmers practical training | 40 | 40 | 40 | 40 | 40 | QPRs | KDLG, MAAIF, Private Sector. |
|  | Output 1.5.5: Farmers from farmers’ groups mobilized, sensitized and trained | Output 1.5.5: Number of farmers from farmers’ groups mobilized, sensitized and trained | 33,000 | 46,000 | 59,000 | 72,000 | 85,000 | QPRs | KDLG, MAAIF, Private Sector. |
| Intervention 1.6: Promote climate adaptation and mitigation practices | Output 1.6.1: Cover crop and shade tree seeds acquired and distributed | Output Indicator 1: Kilograms of cover crop and shade tree seeds acquired and distributed | c7 | 14 | 21 | 28 | 35 | QPRs | KDLG, MAAIF, Private Sector. |
|  | Output 1.6.2: Farmers linked to green financing services institutions | Output Indicator 2: Number of farmers linked to green financing services institutions | 7 | 14 | 21 | 28 | 35 | QPRs | KDLG, MAAIF, Private Sector. |
|  | Output 1.6.3: Youths from groups engaged in commercial fodder production and conservation | Output Indicator 3: Number of youths from groups engaged in commercial fodder production and conservation | 7 | 14 | 21 | 28 | 35 | QPRs | KDLG, MAAIF, Private Sector. |
| Project 1: Establishment and maintenance of crop enterprises and livestock enterprises | Project Output: Units of crop enterprises and livestock enterprises (piggery, breeding bulls and dairy animals) established and/or maintained | Output Indicator: Number of units of crop enterprises (cassava, banana, coffee and fruit trees) and livestock enterprises (piggery, breeding bulls and dairy animals) established and maintained | 7 | 7 | 7 | 7 | 7 | Centre Manager DATIC Senior Veterinary Officer |  |
| Project 2: Supporting sub-county agricultural extension workers in setting up on-farm result demonstration sites for farmers’ practical training in all 40 LLGs | Project Output: Sub-county agricultural extension workers supported in setting up on-farm result demonstration sites | Output Indicator: Number of on-farm results demonstration sites set up by sub-county agricultural extension workers. | 40 | 40 | 40 | 40 | 40 | Sub-county Agricultural Extension Workers |  |
| Project 3: Acquisition and installation of units of micro-scale irrigation in farms of farmers that co-fund for equipment | Project Output: Units of micro-scale irrigation in farms of farmers that co-fund for equipment acquired and installed | Output Indicator: Number of units of micro-scale irrigation in farms of farmers that co-fund for equipment acquired and installed | 69 | 69 | 69 | 69 | 69 | Senior Agricultural Engineer (Water for Agricultural Production) |  |
| Project 4: Equipping a mini-diagnostic laboratory for animal diseases and post-mortem examination at District veterinary ground | Project Output: A mini-diagnostic laboratory for animal diseases and post-mortem examination equipped | Output Indicator: Number of mini-diagnostic laboratory for animal diseases and post-mortem examination equipped | 1 | 0 | 0 | 0 | 0 | Senior Veterinary Officer |  |
| Project 5: Re-construction and/or rehabilitation of communal cattle dip tanks for tick control | Project Output: Communal cattle dip tanks re-constructed and/or rehabilitated | Output Indicator: Number of communal cattle dip tanks re-constructed and/or rehabilitated | 0 | 0 | 0 | 2 | 0 | Senior Veterinary Officer |  |
| Project 6: Equipping communal cattle crushes with foot bucket spray pumps | Project Output: Ccommunal cattle crushes equipped with foot bucket spray pumps and acaricide. | Output Indicator: Number of communal cattle crushes equipped with foot bucket spray pumps and acaricide. | 0 | 0 | 6 | 0 | 0 | Senior Veterinary Officer |  |
| Project 7: Acquisition of motorcycles of 125 CC for sub-county agricultural extension workers | Project Output: Mmotorcycles for sub-county agricultural extension workers acquired | Output Indicator: Number of mmotorcycles for sub-county agricultural extension workers acquired | 2 | 2 | 0 | 2 | 2 | District Production Officer |  |
| Project 8: Acquisition of ICT equipment for agricultural extension workers at the district level | Project Output: ICT equipment for agricultural extension workers acquired | Output Indicator: Number and type of ICT equipment for agricultural extension workers acquired | 0 | 0 | 5 | 0 | 0 | District Production Officer |  |
| Programme (a): | Outcome (b) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 2: Improved harvesting, post-harvest handling and storage | Outcome 2.1: Reduced post-harvest handling losses for priority agricultural commodities | Outcome Indicator 2.1.1: Percentage change in post-harvest handling losses for priority agricultural commodities | 40 | 35 | 30 | 25 | 20 | 15 | Production statistical abstract |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 2.1.1: Increase adoption of recommended post-harvest handling practices | Intermediate Outcome Indicator 1: Percentage of farmers adopting recommended post-harvest handling practices | 5 | 10 | 15 | 20 | 25 | 30 | Production statistical abstract |
| Intervention (d) | Key Output (e) | Indicator (f) | Time Frame and Output Target |  |  | Data Source |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |  |
| Intervention 2.1: Provide appropriate harvest, post-harvest handling and storage technologies | Output 2.1.1: Farmers and other actors supported with appropriate post-harvest handling technologies | Output Indicator 1: Number of farmers and other actors supported with appropriate post-harvest handling technologies | 8 | 8 | 8 | 8 | 8 | QPRs | KDLG, MAAIF, Private Sector |
|  | Output 2.1.2: Harvest, post-harvest handling and storage infrastructure established | Output Indicator 2: Number of harvest, post-harvest handling and storage infrastructure established | 1 | 1 | 1 | 1 | 1 | QPRs | KDLG, MAAIF, Private Sector |
|  | Output 2.1.3: Value chain actors such as women supported with post-harvest handling equipment | Output Indicator 3: Number of value chain actors such as supported with post-harvest handling equipment | 6 | 6 | 6 | 6 | 6 | QPRs | KDLG, MAAIF, Private Sector |
| Intervention 2.2: Invest in appropriate agro-processing and value addition technologies | Output 2.2.1: Appropriate agro-processing and value addition technologies promoted | Output Indicator 1: Number of women farmers’ groups and other actors supported with appropriate agro-processing and value addition technologies | 6 | 6 | 6 | 6 | 6 | QPRs | KDLG, MAAIF, Private Sector |
| Programme (a): | Outcome (b) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| Programme Objective 4: Increase market access and competitiveness of agricultural products in domestic and international markets | Outcome 4.1: Increase income from agricultural enterprises | Outcome Indicator 4.1.1: Percentage increase in income from agricultural enterprises | 5 | 10 | 15 | 20 | 25 | 30 | Production statistical abstract |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 4.1.1: Reduce subsistence farming | Intermediate Outcome Indicator 1: Percentage of households dependent on subsistence agriculture as the main source of livelihood | 5 | 10 | 15 | 20 | 25 | 30 | UBOS household survey, Local Government Statistical Abstract |
| Intervention (d) | Key Output (e) | Indicator (f) | Time Frame and Output Target |  |  | Actors |  |  |  |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |  |
| Intervention 4.1: Establish and maintain appropriate marketing infrastructure | Output 4.1.1: Marketing infrastructure (animal slaughter facilities) established and maintained | Output Indicator 1: Number of animal slaughter house/shed constructed | 0 | 1 | 0 | 0 | 0 | Local Government, MAAIF, Private Sector Service Providers |  |
|  |  | Output Indicator 2: Number of slaughter slabs constructed and/or rehabilitated | 0 | 0 | 4 | 0 | 4 | Local Government, MAAIF, Private Sector Service Providers |  |
| Project 10: Construction of a slaughter house/shed at different Rural growth centres. | Project Output: A slaughter house/shed constructed | Output Indicator: Number of slaughter houses/sheds constructed | 0 | 1 | 0 | 1 | 2 | Senior Veterinary Officer |  |

3.5.1. Programme 2: Tourism Development

Tourism Development Programme: aims to increase the district’s attractiveness as a preferred tourist destination. Tourism in Kitagwenda remains largely underdeveloped despite its considerable potential, given the district’s strategic location in the Albertine Rift Valley. Kitagwenda borders Queen Elizabeth National Park and hosts part of the Lake George Ramsar Site, which is internationally recognized for its aquatic biodiversity and birdlife. Current challenges include negative mindset by the community in regards to development of tourism sites, Lack of funding to support development of identified tourism sites and nearly all the identified tourism sites are under private land owners who are not allowing Government to develop these areas.

##### Table 3.4: Programme Results and Targets for Tourism Development

| Programme (a): | Outcome (a) |  | Indicator (c) | FY2023/24 | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Develop, Conserve and Diversify tourism products | 1.1. Increased tourism earnings |  | Tourist’s length of stay (Nights) | 0 | 0 |  | 2 |  | 3 |  | 4 |  | 5 | Field Visits |
|  |  |  | Tourism direct contribution to total taxes (%) | 0 | 0.1 |  | 0.3 |  | 0.7 |  | 0.8 |  | 1 | DLG |
|  |  |  | Domestic tourism expenditure (UGX)(million) | 10 | 15 |  | 20 |  | 25 |  | 30 |  | 40 | DLG |
|  | Intermediate Outcome: |  | Indicator (c) | FY2023/24 | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Increased domestic and inbound tourism |  | No. of local and foreign tourist registered. | 0 | 30 |  | 40 |  | 60 |  | 80 |  | 100 | Tourist Site Register |
| Intervention |  | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  |  | Actors |
|  |  |  |  | FY2023/24 |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 | FY2029/30 |  |
| - Develop new tourist sites |  | 1.1.1. Domestic and inbound tourism promoted | No. of accommodation and restaurant facilities registered, inspected. | 20 |  | 30 |  | 50 |  | 70 |  | 80 | 100 | Private Sector |
|  |  |  | Develop the Equator area as a district tourist site |  |  |  |  |  |  |  |  | 1 |  | DLG |
| Development and promotion of tourism in the district |  | Tourism officer recruited; Hospitality facilities upgraded; Tourist sites profiled | Tourism officer recruited. |  |  |  |  |  |  | 1 |  |  |  | Tourism officer Private sector |
|  |  |  | No. training conducted for private sector | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 1 | DLG |
|  |  |  | Profiling of tourism sites conducted. |  |  |  |  |  |  | 1 |  |  |  | DLG |

3.5.1. Programme 3: Environment, Natural Resources, Climate Change and Land Management

Environment, Natural Resources, Climate Change and Land Management: aims to stop and reverse the degradation of Water Resources, Environment, Natural Resources as well as the effects of Climate Change on economic growth and livelihood security. Major cause of the degradation of the quality and quantity of natural resource base is associated with human activity. This includes deforestation mostly on privately owned lands. Others are wetland degradation as a result of cultivation of crops and soil erosion contributed by poor farming methods.

##### Table 3.5: Programme Results and Targets for Environment, Natural Resources, Climate Change and Land Management

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24 | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: To ensure availability of adequate and reliable water for different use | Outcome 1.1: Improved water quality and availability | Outcome Indicator 1 % of water bodies with good ambient water quality | 78 | 79 | 82 |  | 83 |  | 84 |  | 85 | Annual Programme Performance Report, QPRs |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24 | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Enhanced water quality management | Intermediate Outcome Indicator 1 % age compliance to portable water standards – Point | 55 | 61 | 65 |  | 72 |  | 76 |  | 84 | Annual Programme Performance Report, QPRs |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |
| Intervention 1.1 Implement ecosystem and catchment management practices. | Output 1.1.1: District and Transboundary Catchment Management Plans prepared | Output Indicator 1 Number of Catchment Management Plans prepared | 1 | 2 |  | 1 |  | 1 |  | 2 |  | LLGs, MWE |
|  |  | Output Indicator 2 Area (hectares) of degraded water catchments protected and restored | 10 | 10 |  | 30 |  | 10 |  | 10 |  | LLG, HLG, MWE |

Programme Objective 2: Protect, restore and add value to forests and wetlands

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 2: Protect, restore and add value to forests and wetlands | Outcome 2.1: Increased forest and wetland cover for socio-economic and ecological benefits . | Outcome Indicator 1 Percentage of land area covered by forests | 17 | 17.2 |  | 17.4 |  | 17.6 |  | 17.7 | 17.9 | Annual Programme Performance Report, QPRs |
|  |  | Outcome Indicator 2 Percentage of land area covered by wetlands | 3.2 | 3.2 |  | 3.5 |  | 3.5 |  | 3.6 | 4.2 | Annual Programme Performance Report, QPRs |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 2.1: Reduced area of degraded forests and landscapes | Intermediate Outcome Indicator 1 Area (ha) of degraded forest and degraded landscapes restored | 500 | 30 |  | 25 |  | 35 |  | 40 | 32 | Annual Programme Performance Report, QPRs |
|  | Intermediate Outcome 2.2: Reduced area of degraded wetlands | Intermediate Outcome Indicator 2 Percentage reduction in area of degraded wetland | 0.24 | 0.3 |  | 0.4 |  | 0.6 |  | 0.8 | 1.2 | Annual Programme Performance Report, QPRs |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |
| Intervention 2.1 Increased forest and wetland cover for socio-economic and ecological benefits | Output 2.1.1: Forest reserves restored and protected | Output Indicator 1 Area (ha) of degraded forests restored | 12 |  | 13.5 |  | 14 |  | 16 |  | 16.8 | LLG, HLG, MWE |
|  | Output 2.1.2: Degraded landscapes restored | Output Indicator 1 Area (ha) of degraded landscapes restored | 13.5 |  | 14 |  | 16 |  | 16.8 |  | 17 | LLG, HLG, MWE |
| Intervention 2.2: Protect and increase the wetland cover | Output 2.2.1: Gender responsive wetlands management plans and district/city wetland action plans developed and implemented | Output Indicator 1 Area (ha) of wetlands under management plans | 100 |  | 100 |  | 130 |  | 150 |  | 160 | LLG, HLG, MWE |
|  | Output 1.2.2: Wetland boundaries surveyed and demarcated | Output Indicator 1 Length (Km) of wetlands boundaries demarcated. | 10 |  | 11 |  | 12.3 |  | 13 |  | 16 | LLG, HLG, MWE |
|  | Output 12.3: Degraded wetlands restored | Area (Ha) of wetlands restored | 58 |  | 100 |  | 80 |  | 85 |  | 100 | LLG, HLG, MWE |

Programme Objective 3: To ensure a clean, healthy and productive environment

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  | Data Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 3: To ensure a clean, healthy and productive environment | Outcome 3.1: Improved well-being, a sustainable and productive environment | Outcome Indicator : Average outdoor Air quality index for district (PM 2.5 | 111 | 110 | 108 |  | 105 |  | 103 |  | 100 |  | Annual Programme Performance Report, QPRs |  |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  | Data Source |  |
|  | Intermediate Outcome 3.1: Increased environmentally sustainable technologies and practices for social economic transformation | Intermediate Outcome Indicator 1 Percentage of ESIA certificate holders complying with ESIA conditions | 60 | 65 | 70 |  | 75 |  | 80 |  | 85 |  | Annual Programme Performance Report, QPRs |  |
|  |  | Intermediate Outcome Indicator 2 Proportion of Town councils solid waste collected and managed in sustainable manner | 20 | 20 | 25 |  | 25 |  | 35 |  | 35 |  | Annual Programme Performance Report, QPRs |  |
|  |  | Intermediate Outcome Indicator 3 Area (ha) of degraded river banks and lakeshores restored | 10 | 20 | 20 |  | 23 |  | 25 |  | 25 |  | Annual Programme Performance Report, QPRs |  |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |  |
|  |  |  | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |  |
| Intervention 3.1 Promote circular economy | Output 3.1.1: Improved waste management in Town councils | Output Indicator 1 Number of gazetted and waste management areas | 1 | 1 |  | 1 |  | 1 |  | 1 |  | LLG, HLG, NEMA Private sector |  |
| Intervention 3.2 Strengthen regulation and enforcement against environmental pollution and degradation | Output 3.2.1: Regulation and enforcement against environmental degradation strengthened | Output Indicator 1 Number environmental compliance monitoring and inspections carried out | 30 | 35 |  | 38 |  | 40 |  | 40 |  | LLG, HLG, NEMA Private sector |  |
|  |  | Output Indicator 2 Number of environmental and social impact assessments supported | 37 | 39 |  | 41 |  | 45 |  | 45 |  | LLG, HLG, NEMA Private sector |  |
|  |  | Output Indicator 3 Number of LLGs mainstreaming environment management in policies, programs, budgets and workplans. | 10 | 12 |  | 15 |  | 20 |  | 35 |  | LLG, HLG, NEMA Private sector |  |
|  |  | Output Indicator 4 Number of environment compliance audits supported | 42 | 42 |  | 47 |  | 50 |  | 53 |  | LLG, HLG, NEMA Private sector |  |

Programme Objective 4: To strengthen policy, legal, regulatory and coordination frameworks

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 4: To strengthen policy, legal, regulatory and coordination frameworks | Outcome 4.1: Increased attainment of sustainable results of the programme | Outcome Indicator 1 % number of programme outcomes achieved | 15 | 30 | 50 |  | 60 |  | 74 |  | 80 | Annual Programme Performance Report, QPRs |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 4.1: Improved planning and implementation capacity | Intermediate Outcome Indicator 2 % programme outputs achieved within the designated time frame | 20 | 35 | 50 |  | 56 |  | 68 |  | 70 | Annual Programme Performance Report, QPRs |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |
| Intervention 4.1 Strengthen planning, supervision, monitoring, evaluation and human resource capacity of the Programme | Output 4.1.1: Planning, budgeting, supervision, monitoring and evaluations undertaken | Output Indicator 1 Number of planning and budgeting documents produced | 3 | 3 |  | 3 |  | 3 |  | 4 |  | LLG, HLG, NEMA Private sector |
| Intervention 4.1 Strengthen programme, administration, coordination and management for efficient service delivery. | Output 4.1.1: Effective Program performance and coordination frameworks in place | Output Indicator 1 Number of Programme performance reviews held. | 1 | 1 |  | 1 |  | 1 |  | 1 |  | LLG, HLG, NEMA Private sector |
|  | Output 4.1.2: Programme Administration and management supported | Output Indicator 1 Number of recurrent cost paid | Yes/No | Yes/No |  | Yes/No |  | Yes/No |  | Yes/No |  | Natural resources management department |
| Intervention 4.2 Integrate crosscutting issues in the programme | Output 4.2.1: Crosscutting issues mainstreamed in the programme | Output Indicator 1 Number of Gender mainstreaming interventions implemented | 15 | 15 |  | 18 |  | 18 |  | 20 |  | Natural resources management department |
|  |  | Output Indicator 2 Number of HIV/AIDS mainstreaming interventions undertaken | 3 | 3 |  | 3 |  | 2 |  | 2 |  | Natural resources management department |
|  |  | Output Indicator 3 Number of projects supported with Social and Environmental safeguards. | 30 | 35 |  | 40 |  | 45 |  | 45 |  | Natural resources management department |

Strategic Objective 2: Enhance human capital development along the entire life cycle.

3.5.1. Programme 4: Human Capital Development

Human Capital Development aims to increase productivity of the population for increased competitiveness and better quality of life for all. Key development challenges related low proportion of labour force transiting to gainful employment; high pupil teacher, classroom, pit latrine, desk ratios; poor child and maternal outcomes; access to safe and clean water not everywhere in the district and sanitation; and low access by population to social protection and Gender responsiveness.

##### Table 3.6: Programme Results and Targets for Human capital development

| Programme (a): Human Capital Development | Outcome (a). | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Improve the foundation for human capital development. | Outcome 1.1: Increased access to quality and inclusive education | Number of ECCE centres licensed and Registered | 105 | 109 | 120 | 150 | 170 | 185 | EMIS |
|  |  | Gross Enrolment Rates at Primary | 240,000 | 242,000 | 245,000 | 245,500 | 250,000 | 260,000 | UBOS |
|  |  | Net Enrolment Rates at Primary | 217,000 | 217,200 | 217,300 | 217,400 | 217,600 | 218,000 | EMIS |
|  |  | Gross Enrolment Rates at Secondary | 20,000 | 21,000 | 22,000 | 23,000 | 24,000 | 25,000 | EMIS |
|  |  | Net Enrolment Rates at Secondary. | 18,000 | 18,500 | 19,000 | 19,500 | 20,000 | 21,500 | EMIS |
|  |  | Percentage of children completing P.7. | 65 | 65 | 68 | 70 | 80 | 82 | UNEB |
|  |  | Percentage of children transitioning from primary to lower secondary education | 50 | 55 56 | 58 | 60 | 65 | 70 | EMIS |
|  |  | Percentage of learners transitioning from Secondary to tertiary. | 50 | 55 | 60 | 65 | 70 | 75 | EMIS |
|  | Outcome 1.2: Improved Pupil/Student Learning Outcomes. | Proportion of students achieving proficiency in literacy | 55 | 60 | 65 | 70 | 75 | 80 | NAPE |
|  |  | Proportion of students achieving proficiency in Numeracy | 55 | 60 | 65 | 70 | 75 | 80 | NAPE |
|  |  | Completion Rate for Primary Education [SDG Indicator 4.1.2] | 70 | 71 | 73 | 75 | 77 | 80 | UNEB |
|  |  | Percentage of TVET institutions meeting the BRMS. | 75 | 80 | 85 | 90 | 95 | 100 | EMIS |
| Programme Objective 2: To produce appropriate knowledgeable, skilled and ethical labour force (with strong emphasis on science and technology; STEI/STEM in education and TVET) | Outcome 2.1: Increased access to quality higher educational and training with strong emphasis on STEM/STEI and TVET Programs. | Gross Enrolment Ratio (Tertiary Education), | 6.8 | 7 | 7.5 | 7.8 | 8 | 8.5 | EMIS |
|  | Outcome 2.2: Increased access to quality higher educational and training with strong emphasis on STEM/STEI and TVET Programs. | Enrolment growth rates in STEM/STEI | 2.5 | 2.7 | 2.9 | 3 | 4.2 | 3.5 | EMIS |
|  |  | Gross Enrolment Rates in TVET | 32 | 35 | 36 | 38 | 40 | 42 | EMIS |
|  |  | Transition rates from secondary to TVET | 12 | 16 | 18 | 20 | 21 | 22 | EMIS |
| Programme Objective 3: To promote sports, recreation and physical education | Outcome 3.1: Increased participation in sports, recreation, and physical education. | Number of Schools participating in Sports | 163 | 164 | 164 | 164 | 164 | 164 | SPORTS OFFICE |
|  |  | Number of athletes representing the district in national sports events | 30 | 40 | 50 | 60 | 70 | 80 | UPSSA |
|  |  | Percentage increase in athletes participating in competitions | 3 | 5 | 7 | 8 | 9 | 10 | UPSSA |
|  |  | Number of the medals won from national events | 0 | 1 | 3 | 4 | 5 | 6 | UPPSA |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1: Improved learning, instruction and learning environments at basic education | Improved Pupil Teacher Ratio | 108:1 | 98:1 | 90:1 | 80:1 | 75:1 | 70:1 | EMIS |
|  |  | Improved Student-to-Classroom ratio | 125:1 | 120:1 | 110:1 | 100:1 | 95:1 | 90:1 | EMIS |
|  |  | Percentage of classrooms equipped with adequate furniture | 75 | 80 | 85 | 88 | 90 | 95 | EMIS |
|  | Intermediate Outcome 2: Strengthened workforce planning, management and development | Percentage of TVET institutions meeting the BRMS. | 75 | 80 | 85 | 90 | 95 | 100 | EMIS |
|  |  | Enrolment growth rates in STEM/STEI | 2.5 | 2.7 | 2.9 | 3 | 4.2 | 3.5 | EMIS |
|  | Intermediate Outcome 3: Increased Enrolment in STEM/STEI and TVET Programs | Gross Enrolment Rates in TVET | 32 | 35 | 36 | 38 | 40 | 42 | EMIS |
|  |  | Gross Enrolment Ratio (Tertiary Education), | 6.8 | 7 | 7.5 | 7.8 | 8 | 8.5 | EMIS |
|  |  | Transition rates from secondary to TVET | 12 | 16 | 18 | 20 | 21 | 22 | EMIS |
|  | Intermediate Outcome 4: Enhanced Talent Development and Professionalization in Sports Intermediate | Number of athletes participating in competitions | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | UPSSA |
| Intervention | Key Output | Indicator (f) |  | Time Frame and Output Target |  |  |  |  | Actors |
|  |  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| 1. Improve access and equity of primary and secondary education. | Improve access to equitable primary and secondary education | Percentage of children completing P.7. |  | 65 | 65 | 68 | 70 | 80 | DEO |
|  |  | Percentage of children transitioning from primary to lower secondary education |  | 50 | 56 | 58 | 60 | 65 | MoES DEO |
| 2. Enforce the regulatory and quality assurance system for provision of ECCE. | Improved access to equitable ECCE | Number of ECCE centres licensed and Registered |  | 105 | 109 | 120 | 150 | 170 | I.Ss |
| 3.Equip all lagging schools to meet BRMS | Lagging Public primary schools constructed, renovated, equipped with required infrastructure and staffed | Number of schools constructed in in each parish of gazetted parishes. |  | 1 | 3 | 3 | 3 | 3 | MFPED MoES CAO, DEO |
|  |  | Number of schools constructed in in each parish of gazetted parishes. |  | 1 | 1 | 1 | 1 | 1 | MFPED MoES CAO, DEO |
|  |  | Number of exclusive public special needs schools adequately rehabilitated, expanded, equip and staffed |  | 1 | 1 | 1 | 1 | 1 | MFPED MoES CAO, DEO |
|  |  | Number of permanent classrooms in public primary schools constructed or Rehabilitated |  | 4 | 4 | 4 | 4 | 4 | MFPED MoES CAO, DEO |
|  |  | Number of existing public primary schools rehabilitated. |  | 2 | 2 | 2 | 2 | 2 | MFPED MoES CAO, DEO’ |
|  |  | Number of gender and disability sensitive emptiable VIP latrines constructed |  | 15 | 15 | 15 | 15 | 15 | MFPED MoES CAO, DEO |
|  |  | Number of classroom furniture (desks/tables/chairs/stools) provided in primary schools |  | 335 | 335 | 335 | 335 | 335 | MFPED, MoESCAO,DEO |
| 3.Enhance proficiency in literacy and numeracy through Early Grade Reading (EGR), Early Grade Mathematics (EGM) and remedial learning | Early Grade Reading (EGR), Early Grade Mathematics (EGM) and remedial learning programmes implemented | Number of primary schools implementing EGR |  | 20 | 50 | 70 | 80 | 90 | MoES DEO |
|  |  | No. of primary school teachers trained in EGMA |  | 0 | 50 | 100 | 150 | 200 | DEO DIS |
|  |  | No. of local languages in which EGR is rolled out in schools |  | 1 | 2 | 2 | 2 | 2 | DEO DIS |
|  |  | Number of primary schools implementing specialised EGR |  | 10 | 15 | 20 | 25 | 30 | DEO DIS |
|  |  | Number of teachers trained in remedial education program |  | 15 | 30 | 60 | 90 | 120 | DIS |
| 4. Improve the inclusivity in teaching and learning environments | Improved learning environment for SNE Learners | Number of LG level SNE officers trained in special needs education |  | 1 | 1 | 1 | 1 | 1 | DEO DIS |
|  |  | Number of SNE teachers trained in basic SNE skills |  | 164 | 164 | 164 | 164 | 164 | EOSNE |
|  |  | Number of workshops in SNE conducted. |  | 1 | 1 | 1 | 1 | 1 | DEO,DIS |
| 5. Strengthen support services (guidance and counselling, child protection, school health, nutrition services) to enable retention and completion at all | Schools provided with existing support services (guidance and counselling, child protection, school health, nutrition services) to ensure holistic development of learners at all levels | Number of schools provided with these support services |  | 164 | 164 | 164 | 164 | 164 | DEO |
|  |  | Number of schools with adequate water, sanitation, and hygiene (WASH) facilities |  | 164 | 164 | 164 | 164 | 164 | Water Officer |
|  |  | Number of schools whose parents are sensitized |  | 164 | 164 | 164 | 164 | 164 | DEO |
| 6. Implement ICT integrated teaching, learning and decision making through implementation | Increased Adoption of ICT in Teaching, Learning and decision making through the Digital Agenda Strategy | EMIS Statistical Abstract produced |  | 1 | 1 | 1 | 1 | 1 | DEO |
|  |  | Number of schools that have fully operationalized TELA |  | 182 | 183 | 184 | 185 | 186 | DEO DIS |
|  |  | Number of in-service teachers trained in ICT pedagogy |  | 30 | 50 | 80 | 100 | 120 | DEO |
| 7. Enforce the regulatory and quality assurance system of primary and secondary schools | Improved regulatory and quality assurance system for primary and secondary | Number of School Management Committees trained in leadership and management |  | 164 | 164 | 164 | 164 | 164 | DEO,DIS |
|  |  | Number of schools that are monitored for all three terms in a year for primary school inspection |  | 187 | 187 | 187 | 187 | 187 | DEO |
|  |  | Number of trainings conducted for heads of institutions on developing and implementing School Improvement Plans (SIPs) |  | 1 | 1 | 1 | 1 | 1 | DIS |
|  |  | Number of Inspector of Schools and Associate Assessors trained in the e-inspection system twice a year |  | 5 | 6 | 6 | 6 | 6 | DIS |
|  |  | Number of schools (primary) with updated/developed annual school improvement plans |  | 164 | 164 | 164 | 164 | 164 | DIS |
|  |  | Number of public primary schools inspected at least once per term |  | 164 | 164 | 164 | 164 | 164 | DIS IoSs |
| 8. Accelerate the acquisition of urgently needed skills in key growth areas | Strengthened Skills acquisition and development framework | Number of Tertiary Institutions funded |  | 4 | 4 | 4 | 4 | 4 | CAO DEO |
|  |  | Number of Students admitted in tertiary Institutions |  | 300 | 500 | 600 | 700 | 800 | DEO |
| 9. Develop and implement a framework for institutionalizing talent identification, development, and professionalization. | Framework for institutionalizing talent identification, development, and professionalization developed and implemented | Number of schools with creative arts and physical education (CAPE) implementation plans |  | 164 | 164 | 164 | 164 | 164 | S.O |
|  |  | Number of government aided Primary schools established and equipped as centres of sports excellence |  | 4 | 4 | 4 | 4 | 4 | DEO |
|  |  | Number of teachers trained in talent identification |  | 164 | 164 | 164 | 164 | 164 | SO |
|  |  | Number of schools participating in co-curricular activities |  | 164 | 164 | 164 | 164 | 164 | SO |
|  |  | Number of trainings conducted. |  | 3 | 3 | 3 | 3 | 3 | SO |
|  |  | Number of teachers trained in talent identification |  | 164 | 164 | 164 | 164 | 164 | SO |
|  |  | Number of schools monitored |  | 164 | 164 | 164 | 164 | 164 | DEO |
|  |  | Number of schools participating in regional and national sports competitions. |  | 30 | 30 | 30 | 30 | 30 | SO |
| Project: Improve School Infrastructure and Sanitation Facilities | Construction of Classrooms, 5 Stance VIP Latrines and Supply of Furniture | Number of 2 Classroom blocks constructed. |  | 2 | 2 | 2 | 2 | 2 | CAO, DEO |
|  |  | Number of 5-stance VIP latrines constructed. |  | 2 | 2 | 2 | 2 | 2 | CAO DEO |
|  |  | Number of three-seater desks supplied. |  | 335 | 335 | 335 | 335 | 335 | CAO,DEO |

Health

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme: Human Capital Development. Objective 1: Improve the foundation for human capital development | Outcome 1.1: Increase access to basic healthcare services | Outcome Indicator 1. Percentage of population with access to healthcare services | 65%. | 70%. | 75%. | 80%. | 85%. | 95%. | HMIS |
|  |  | Outcome Indicator 2. Immunization coverage rate | 85% | 90% | 93% | 95% | 97% | 98% | HMIS |
|  | Outcome 1.2: Improve maternal and child health | Outcome Indicator 1. Maternal mortality rate per 100,000 live births | 40 | 30 | 20 | 15 | 10 | 5 | HMIS |
|  |  | Outcome Indicator 2. Under-5 mortality rate per 1,000 live births. | 50 | 45 | 30 | 20 | 20 | 10 | HMIS |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Improved utilization of health services | Intermediate Outcome Indicator 1 Per Capita OPD attendance | 1.1 | 1.2 | 1.4 | 1.5 | 1.6 | 1.8 |  |
|  |  | Intermediate Outcome Indicator 2 Hospital (public & private) admission rate (per 1,000 population) | 70 | 75 | 73 | 75 | 72 | 69 | HMIS |
|  |  | Intermediate Outcome Indicator 3 Bed Occupancy Rate (%) | 62% | 65% | 71% | 75% | 72% | 62% | HMIS |
|  |  | Intermediate Outcome Indicator 4 HIV Viral Load Suppression rate among PLHA | 98% | 97% | 99% | 99% | 99% | 99% | HMIS |
|  |  | Intermediate Outcome Indicator 5 TB case notification rate/100,0000 | 198 | 189 | 178 | 174 | 168 | 164 | HMIS |
|  |  | Intermediate Outcome Indicator 6 DPTHibHep 3rd dose coverage (%) | 98% | 101% | 101% | 108% | 108% | 110% | HMIS |
|  |  | Intermediate Outcome Indicator 7 ANC 4th Visit Coverage (%) | 52% | 60% | 65% | 68% | 70% | 75% | HMIS |
|  |  | Intermediate Outcome Indicator 8 Institutional deliveries. | 68% | 75% | 78% | 78% | 79% | 80% | HMIS |
|  |  | Intermediate Outcome Indicator 9 Service availability and readiness index (%) | 45% | 52% | 55% | 65% | 70% | 75% | LQAS |
|  | Intermediate Outcome 1.2: Improved Health and wellbeing of the population | Intermediate Outcome Indicator 1. Percentage of the Population with Access to Healthcare Services: | 70% | 75% | 80% | 85% | 90% | 95% | LQAS |
|  |  | Intermediate Outcome Indicator 2. Percentage reduction in mortality rates | 4.0 | 3.5 | 3.0 | 2.5 | 2.0 | 1.5 | HMIS |
|  |  | Intermediate Outcome Indicator 3. %ge improvement in Strengthened Health Systems and Governance. | 65% | 70% | 75% | 80% | 95% | 99% | M&E Reports |

| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Actors |
| Intervention 1.1 (d) Promote optimal Maternal, Infant, Young child, Adolescent and Elderly Nutrition Practices | Output 1.1.1: Enabling environment for scaling up nutrition at all levels strengthened | Output Indicator 1 % of Health facilities designated as mother-baby friendly (Hospitals, HC IVs and IIIs) | 80% | 90% | 100% | 100% | 100% | MOH |
|  | Output 1.1.2: Prevent and control micro-nutrient deficiencies | Output Indicator 1 Vitamin A second dose coverage for U5s (%) | 47% | 50% | 60% | 75% | 80% | HMIS |
|  |  | Output Indicator 2 % of Pregnant women receiving Iron and Folic Acid supplementation on 1st ANC visit | 85% | 95% | 99% | 100% | 100% | HMIS |
|  |  | Output Indicator 3 Number of Health workers oriented on micronutrient supplementation for the elderly | 26 | 38 | 85 | 120 | 300 | Training reports |
| Intervention 1.2 (d) | Output 1.2.1: Promote dietary diversification | Output Indicator 1 Number of Health workers trained in dietary diversification (Number) | 0 | 50 | 140 | 220 | 430 | Training Reports |
|  |  | Output Indicator 2 Number of Awareness campaigns on dietary diversification and breast feeding conducted | 1 | 1 | 1 | 1 | 1 | Reports |
|  | Output 1.2.2: Promote Food Safety along the food systems | Output Indicator 1 % of Eating places inspected | 85% | 88% | 90% | 95% | 98% | Activity reports |
|  |  | Output Indicator 2 % of Food handlers screened for Typhoid, TB | 75% | 80% | 85% | 90% | 100% | HMIS |
| Increase access to immunization against childhood diseases | OutPut: Increase access to immunization against childhood diseases | Output Indicator 1 % of under 5 children dewormed in last 6 months | 70% | 75% | 80% | 85% | 90% | HMIS |
|  |  | Output Indicator 2 Measles-Rubella 2nd dose Coverage | 75% | 85% | 90% | 95% | 99% | HMIS |
|  |  | Output Indicator 3 % of Children under one year fully immunized | 78% | 80% | 85% | 90% | 95% | HMIS |
|  |  | Output Indicator 4 % of children under 24 months immunized against malaria (malaria 4th dose coverage) | 0% | 50% | 65% | 70% | 95% | HMIS |
|  |  | Output Indicator 5 % of subcounties with at least one health facility having a functional refrigerator for EPI | 100% | 100% | 100% | 100% | 100% | Equipment inventory report |
|  |  | Output Indicator 6 % of static EPI facilities conducting outreaches | 100% | 100% | 100% | 100% | 100% | HMIS |
|  |  | Number of health workers trained in immunization practice . | 321 | 325 | 330 | 421 | 485 | Training reports |
| Improve Adolescent and Youth health | Promote adolescent and youth friendly health services | % presence of DICAH (%) | 100% | 100% | 100% | 100% | 100% | Meeting minutes |
|  |  | % of Health facilities providing adolescent friendly services | 35% | 45% | 70% | 80% | 100% | Reports |
|  |  | Number of Adolescent and youth health campaigns conducted | 1 | 2 | 3 | 3 | 4 | Reports |
| Objective 3: To improve population health, safety and management; Access to safe water sanitation and hygiene services. | Improved Health and wellbeing of the population | % of Prevalence of stunting among children under 5 | 2% | 1.5% | 0.9% | 0.8% | 0.2% | HMIS |
|  |  | Under Five Mortality Rate (per 1,000 live births) | 50 | 45 | 40 | 35 | 30 | HMIS |
|  |  | Maternal Mortality Ratio (per 100,000 live births) | 20 | 18 | 16 | 14 | 10 | HMIS |
|  |  | Unmet Need for Family Planning Services among currently married women (%) | 35% | 32% | 28% | 25% | 15% | HMIS |
|  |  | Contraceptive Prevalence Rate | 45 | 38 | 37 | 34 | 28 | HMIS |
|  |  | % of mortality rate attributed to cardiovascular disease, cancer, diabetes or chronic respiratory disease between 30 - 70 years | 4.2 | 3.8 | 3.2 | 3.1 | 2.8 | HMIS |
|  |  | Mortality attributed to communicable diseases (Malaria, TB & HIV/AIDS) (%) | 3% | 2.3% | 1.8% | 1.5% | 0.5% | HMIS |
|  |  | Teenage pregnancy rate (%) | 18% | 16% | 14% | 12% | 8% | HMIS |
|  |  | Knowledge of HIV among the youth (%) | 78% | 88% | 100% | 100% | 100% | Survey reports |
|  |  | Number of new HIV infections per 1,000 susceptible population | 98 | 74 | 41 | 28 | 18 | HMIS |
|  |  | % of Population with access to basic sanitation (improved toilet) (Urban) | 52 | 75 | 77 | 85 | 95 | EH -reports |
|  |  | % of population with access to safe water | 65 | 70 | 85 | 88 | 90 | EH -reports |
|  |  | % of population with access to improved sanitation | 48 | 68 | 85 | 89 | 95 | EH -reports |
|  |  | % of the population with access to basic hygiene services | 52 | 65 | 74 | 88 | 95 | EH -reports |
| Increase community ownership, access and utilization of health promotion, environmental health and community health services | Integrated community health services package rolled out in all villages | % of sick children who were managed by VHTs who recovered | 65% | 68% | 70% | 72% | 75% | HMIS |
|  |  | % of Parishes with at least 2 functional Community Health Extension Workers | 10% | 25% | 50% | 70% | 80% | Reports |
|  |  | % of Villages with at least 2 VHTs offering integrated community health service package | 100% | 100% | 100% | 100% | 100% | HMIS |
|  |  | % of Parishes with functional Parish Social Services Committees | 0% | 15% | 20% | 25% | 50% | Reports |
|  | Strengthen enforcement of health/WASH-related legislation | Mortality rate from un safe WASH (Diarrhoea, Typhoid, Dysentery & Cholera), per 100,000 population | 280 | 240 | 140 | 110 | 78 | HMIS |
|  |  | % of Households using a hand washing facility with soap and water | 36% | 54% | 60% | 70% | 85% | EH Reports |
|  |  | % of Households with access to an improved water source | 65% | 70% | 80% | 85% | 95% | EH Reports |
|  |  | % Households with improved sanitation facilities | 52% | 55% | 60% | 65% | 75% | EH Reports |
|  |  | Number of Health/WASH related By-laws passed | 0 | 0 | 1 | 1 | 1 |  |
|  |  | Number SCs/Divisions/TCs with Health/ WASH related Regulations disseminated | 0 | 42 | 42 | 42 | 42 |  |
|  |  | % of Subcounties / Wards / Divisions conducting monthly community sanitation days | 0 | 18 | 32 | 40 | 42 | EH Reports |
|  |  | % of Vermin and vector control interventions carried out in high endemic areas every | 0 | 55 | 60 | 65 | 85 | Reports |
|  |  | Subcounties oriented on the revised healthcare waste management guidelines | 0 | 42 | 42 | 42 | 42 | Reports |
| Reduce the burden of communicable diseases with focus on high burden diseases (Malaria, HIV/AIDS, TB, Neglected Tropical diseases, Hepatitis), epidemic prone diseases across all age groups emphasizing Primary Health Care Approach | Access to malaria prevention and treatment services improved | % of sick children seen by VHT and treated within 24 hours for fever | 70% | 74% | 74% | 79% | 84% | HMIS |
|  |  | Intermittent Presumptive Treatment for Malaria in Pregnancy 3rd dose coverage (%) | 55% | 58% | 65% | 66% | 70% | HMIS |
|  |  | % of Subcounties implementing Indoor Residual Spraying | 100% | 100% | 100% | 100% | 100% | IRS performance Reports |
|  | Access to HIV/AIDs prevention, control and treatment services improved | % of Population who know 3 methods of HIV prevention | 96% | 98% | 99% | 99% | 100% | LQAS |
|  |  | ART Retention rate at 12 months (%) | 85% | 92% | 95% | 99% | 99% | HMIS |
|  |  | % of HIV positive Pregnant women initiated on ART | 95% | 100% | 100% | 100% | 100% | HMIS |
|  |  | % of HIV exposed infants with 2nd DNA/PCR within 9 months | 55% | 65% | 85% | 90% | 95% | HMIS |
|  | Access to prevention, treatment and control of TB and leprosy services improved. | TB treatment coverage rate (%) | 75% | 77% | 85% | 89% | 90% | HMIS |
|  |  | TB treatment success rate (%) | 98% | 99% | 99% | 99% | 99% | HMIS |
|  |  | % of Leprosy cases with grade 2 disability | 0% | 0% | 0% | 0% | 0% | HMIS |
|  |  | Number of CAST+ campaigns conducted | 2 | 2 | 2 | 2 | 2 | Cast Activity reports |
|  | Access to NTDs Services improved | Number of people requiring interventions against NTDs (leprosy, schistosomiasis, trachoma, sleeping sickness, Lymphatic Filariasis, soil transmitted helminths, taenia solium, onchocerciasis, Visceral Leishmaniasis, Buruli Ulcer, podoconiosis, rabies, tungaisis (jiggers), scabbies) | 509,445 | 509,445 | 509,445 | 509,445 | 509,445 | HMIS |
|  |  | % of Planned mass drug administration for NTDs conducted | 52% | 55% | 65% | 70% | 75% | Reports |
|  |  | Number of Health workers oriented on NTD management | 0 | 250 | 270 | 300 | 320 | Training reports |
|  | Hepatitis Prevention and control strategy implemented | Viral Hepatitis B birth dose coverage | 34% | 65% | 75% | 80% | 90% | HMIS |
|  |  | % of Health Facilities (HC IV and above) with diagnostics for Hepatitis | 100% | 100% | 100% | 100% | 100% | HMIS |
|  |  | % of Health facilities with staff trained in viral hepatitis management | 60% | 62% | 65% | 65% | 65% | Training reports |
|  | Public health emergencies prevented and/or detected, managed and controlled in time | % of Public health emergencies detected within 72 hours | 42% | 55% | 75% | 78% | 85% | Reports |
|  |  | % of major PHE controlled/contained in timely manner as per guideline | 52% | 85% | 90% | 98% | 100% | Reports |
| Prevent and control Non-Communicable diseases with specific focus on cancer, cardiovascular, genetic, renal, endocrine, mental, trauma and malnutrition across all age groups. | Establish Centres of excellence in provision of oncology, cardiovascular and trauma services at both National and Regional Levels and foster regional integration | Population aged 15 - 49 years diagnosed with diabetes who are on treatment (%) | 2 | 1.2 | 0.9 | 0.7 | 0.5 | HMIS |
|  |  | Population aged 15 - 49 years diagnosed with heart/chronic disease who are on treatment (%) | 80% | 100% | 100% | 100% | 100% | HMIS |
|  |  | % of Women 25 - 49 years screened for cervical cancer | 65% | 70% | 75% | 80% | 85% | HMIS |
|  |  | % of Men 40+ years screened for prostate cancer | 33% | 42% | 50% | 70% | 85% | HMIS |
|  |  | HPV 2nd dose coverage for girls at 10 years | 35% | 36% | 55% | 60% | 80% | HMIS |
| Improve maternal, neonatal, child and adolescent health services at all levels of care | Investments in maternal and child health services at all levels of care increased | % of under 5 illnessess attributed to diarrhoeal diseases | 15% | 12% | 11% | 9% | 8% | HMIS |
|  |  | % of deliveries in health facilities | 68% | 72% | 75% | 82% | 85% | HMIS |
|  |  | Institutional/Facility Maternal Mortality Risk/ 100,000 deliveries | 200 | 180 | 160 | 140 | 120 | HMIS |
|  |  | % of HC IVs that are fully functional (Offering blood Transfusion and Cesearian Section) | 50 | 75 | 100 | 100 | 100 | HMIS |
|  | Invest in appropriate neonatal careservices at all levels | Institutional perinatal mortality rate per 1,000 births | 50 | 48 | 41 | 35 | 30 |  |
|  |  | % of perinatal deaths reviewed | 85 | 99 | 100 | 100 | 100 | HMIS |
|  |  | % of Health facilities with functional Level II new born care units | 25% | 30% | 50% | 80% | 100% |  |
|  |  | Number of health workers trained in specialised neonatal care | 2 | 10 | 20 | 30 | 50 | Training reports |
| High impact adolescent health interventions to reduce teenage pregnancies, with a special focus on hot spot districts developed and implemented | Adolescent Birth Rate (per 1,000 women aged 15 - 19 years) | Adolescent Health Services implementation plan 2025 - 2030 disseminated to all HCs | 0 | 0 | 80% | 90% | 100% | Minutes |
|  |  | Number of Adolescent & Youth peer educators oriented on age appropriate reproductive health | 5 | 10 | 15 | 20 | 50 | Activity Reports |
| Improve curative, palliative, rehabilitative and geriatric care services | Quality curative, palliative, rehabilitative and geriatric care services provided | Per Capita OPD attendance | 1.1 | 1.2 | 1.4 | 1.5 | 1.6 | HMIS |
|  |  | Hospital admission rate (per 1,000 population) | 70 | 75 | 75 | 75 | 72 | HMIS |
|  |  | Bed Occupancy Rate (%) | 62 | 65 | 71 | 75 | 72 | HMIS |
|  |  | Malaria Case Fatality Rate (per 10,000) | 2% | 1.5% | 1% | 0.2% | 0.1% | HMIS |
|  |  | % of health facilities (public & private) in conformity with the IPC standards (WHO) | 55 | 85 | 90 | 95 | 100 | Reports |
|  |  | Number of DHMT meetings held | 4 | 4 | 4 | 4 | 4 | Minutes |
| Improve the functionality of the health system to deliver quality and affordable preventive, promotive, curative and palliative healthcare services. | Adequate and well trained human resources for health at all levels in place | % of approved posts filled in public health facilities | 39 | 40 | 50 | 60 | 80 | iHRIS |
|  |  | Number of health workers trained (in-service training) for all programs / services | 110 | 120 | 125 | 130 | 135 | Training reports |
|  | Health Infrastructure improved | Number of health facilities rehabilitated / expanded to increase scope of services | 2 | 2 | 5 | 5 | 5 | Certificates of completion |
|  |  | Number of staff houses constructed/rehabilitated | 2 | 1 | 2 | 1 | 1 | Certificates of completion |
|  |  | Number of X-ray machines procured and installed | 0 | 0 | 0 | 0 | 1 | Payment vourchers |
|  |  | % of Health facilities with adequate (solar) source | 5 | 10 | 50 | 85 | 90 |  |
|  | Emergency Medical Services and the referral system improved | Road traffic mortality rate (per 100,000 population) | 50 | 25 | 25 | 15 | 10 | HMIS |
|  |  | Number of Ambulances procured | 1 | 0 | 0 | 1 | 1 | Ambulance cards |
|  |  | Number of EMS cadres trained (in-service) | 2 | 4 | 10 | 30 | 36 |  |
|  | Expand geographical access | Number of Health facilities upgraded to District Hospital | 0 | 0 | 1 | 0 | 0 | Certificates |
|  |  | Number of HC IVs/ Community Hospitals established | 0 | 0 | 1 | 1 | 1 | Certificates of completion |
|  |  | Number of HCIIs upgraded to IIIs established | 0 | 1 | 1 | 1 | 1 | Certificates of completion. |
| Increase availability of affordable medicines and health supplies including promoting local production of medicines.(including complementary medicine) |  | % of health facilities with 95% availability of the 50 basket of EMHS | 75 | 88 | 90 | 92 | 95 | Stock cards |
|  |  | % of health facilities with a SPARS (Supervision, Performance, Assessment, Recognition, Strategy) score of 75% and above (%) | 95% | 99% | 95% | 99% | 90% | Support Supervision Reports |
|  |  | Availability of the tracer public health emergency commodities - examination gloves, coveralls, surgical masks, 70% alochol, vacutainer tubes, IV Ringer's lactate, sodium hypochlorite & aprons) (%) | 75% | 85% | 90% | 95% | 99% | Stock Cards |
|  |  | % of health facilities (Hospitals, HC IVs & IIIs) with functional Logistics Management Information System | 45 | 55 | 75 | 95 | 100 |  |
|  | Increase availability of safe blood and blood products | % availability of safe blood and blood products at health facilities | 35% | 45% | 50% | 65% | 70% | Laboratory refrigerator, Blood bank |
|  |  | Number of staff oriented and mentored in quality system and appropriate use of blood | 12 | 15 | 20 | 25 | 45 | Mentorship and training reports |
|  | Develop and monitor implementation of the health service and service delivery standards | Client satisfaction level (%) | 85% | 86% | 88% | 90% | 99% |  |
|  |  | % of health workers expressing satisfaction with their jobs | 45 | 55 | 95 | 100 | 100 |  |
|  |  | Number of Harmonized Health Facility Assessments conducted | 1 | 4 | 4 | 4 | 4 | Facility Assessment reports |
|  |  | Number of Quarterly supervisory visits conducted | 4 | 4 | 4 | 4 | 4 | Supervision reports |
|  | Promote digitalization of the health information system | Health Information and Digital Health Strategy in place |  |  |  |  |  |  |
|  |  | % of hospitals and HC IVs with functional Electronic Medical Record System | 100% | 100% | 100% | 100% | 100% | Assets Register |
|  |  | % of SCc with functional Electronic Community Health Information System | 0 | 0 | 60 | 100 | 100 | Assets registers |
|  |  | Number of health workers trained in EMRs use | 60 | 80 | 110 | 120 | 150 | Training reports |
|  |  | Number of health workers trained in telemedicine application | 0 | 0 | 30 | 50 | 80 |  |
|  | Adherance to client charter and ethical code of conduct by health workers | % of health institutions with Client Charters | 99 | 100 | 100 | 100 | 100 |  |
|  |  | Number of health workers trained in Human rights based approach, client charter and ethical conduct. | 5 | 10 | 20 | 40 | 80 | Training reports |
| Improving Occupational Safety and Health (OSH) management | Mechanisms for reducing workplace injuries, accidents and occupational diseases implemented | Number of workplaces with OSH systems in place | 70% | 100% | 100% | 100% | 100% | OSH reports |
|  |  | Number of workplaces reporting OSH injuries and diseases | 32 | 65 | 65 | 65 | 65 | Facility reports |
| Undertake monitoring, evaluation, and reporting of progress for HCD programme during plan implementation | Monitoring and Evaluation | Number of performance reports produced | 4 | 4 | 4 | 4 | 4 |  |
|  |  | Monitoring Reports prepared and disseminated | 4 | 4 | 4 | 4 | 4 | Monitoring Reports |
|  |  | Quarterly budget performance progress report prepared and submitted to MoFPED | 4 | 4 | 4 | 4 | 4 | Quarterly budget performance progress report |
|  |  | Quarterly performance review meetings conducted | 4 | 4 | 4 | 4 | 4 | Reports |
|  | Planning and budgeting under the health sub-programme strengthened. | Budget Framework Paper developed | 1 | 1 | 1 | 1 | 1 |  |
|  |  | Number of quarterly budget performance progress report prepared and submitted to CAOs office | 4 | 4 | 4 | 4 | 4 | Performance progress report prepared |
|  |  | Number of Top management programme meetings held | 4 | 4 | 4 | 4 | 4 | Minutes |
| Strengthen population planning and development along the life cycle approach including civil registration, vital statistics and national | Birth and death registration scale up | % of health facility births notified in DHIS2 and registered by NIRA | 45% | 85% | 100% | 100% | 100% | DHIS2 |
|  |  | % of health facility deaths notified in DHIS2 and registered by NIRA | 78% | 100% | 100% | 100% | 100% | DHIS2 |
|  |  | % of community deaths notified in the population data bank | 10% | 45% | 70% | 85% | 95% | population data bank |
|  |  | % of community births notified in the population data bank | 5% | 45% | 75% | 81% | 99% | population data bank |
| Project 1: (Title) Completion of OPD block at Ntara HC IV | Output OPD block at Ntara HC IV completed | One OPD block at Ntara HCIV at Kitagwenda subcounty completed | 0 | 1 | 0 | 0 | 1 |  |
|  |  | Improved OPD utilisation | 1.2 | 1.5 | 1.8 | 2.0 | 2.0 | HMIS |
| Construction of semi detached staff house at Ntara HC IV | Semi detached staff house at Ntara HC IV constructed | One semidetached staff house at Ntara HC IV completed | 1 | 1 |  |  |  |  |
|  |  | %ge reduction in late coming and absenteeism rates | 15% | 12% | 11% | 9% | 7% | iHRIS |
| Completion of the walk way to the mortuary |  | Output Indicator 1 Walk way to the mortuary completed | 1 | 1 |  |  |  | Certificate of completion |
| Completion of upgrading of Buhanda HC II to Buhanda HC III | Upgrading of Buhanda HC II to Buhanda HC III completed. | Buhanda HC II upgraded to Buhanda HC III | 1 | 1 |  |  |  | Certificate of completion |
|  |  | %age reduction in maternal and perinatal mortality | 20/100,0000 | 10/100,0000 | 5/100,0000 | 5/100,0000 | 2/100,000 | HMIS |
|  |  | Increased patient capacity and services |  |  |  |  |  | HMIS |
| Completion of maternity block at Kicheche HC III |  | One maternity block at Maternity HC III completed | 0 | 0 | 1 |  |  | Certificate of completion |
|  |  | %age reduction in maternal and perinatal mortality | 20/100,0000 | 10/100,0000 | 5/100,0000 | 5/100,0000 | 2/100,000 | HMIS |
|  |  | Improved maternal care provided | 65% | 75% | 80% | 85% | 99% | HMIS |
| Completion of maternity block at Nyabbani HC III |  | One maternity block completed at Nyabbani HC III | 0 | 1 | 0 | 0 | 0 | Certificate of completion |
|  |  | Institutional deliveries improved | 65% | 75% | 85% | 90% | 95% | HMIS |
|  |  | Increased access to maternal health |  |  |  |  |  |  |
| Upgrading of Kakasi HC II to HC III | Kakasi HC II upgraded to HC III | Kakasi HC II at Kakasi Subcounty upgraded to HC III status | 0 | 0 | 1 | 0 | 0 | Certificate of completion |
|  |  | Enhanced medical services provided |  |  |  |  |  |  |
|  |  | Expansion of patient care services |  |  |  |  |  |  |
| Upgrading of Bukurungu HC II to HC III | Bukurungu HC II upgraded to HC III | Bukurungu HC II at Bukurungu Subcounty upgraded to HC III status | 0 | 0 | 0 | 0 | 1 | Certificate of completion |
|  |  | Enhanced medical services provided |  |  |  |  |  |  |
|  |  | Expansion of patient care services |  |  |  |  |  |  |
| Upgrading of Kanara HC III to HC IV | Kanara HC III at Kanara Subcounty upgraded to HC IVstatus | Kanara HC III at Kanara Subcounty upgraded to HC IV status | 0 | 0 | 1 | 0 | 0 | Certificate of completion |
|  |  | Enhanced medical services provided |  |  |  |  |  |  |
|  |  | Expansion of patient care services |  |  |  |  |  |  |
| Upgrading of Mahyolo HC III to HC IV | Mahyolo HC III at Mahyolo Subcounty upgraded to HC IVstatus | Mahyolo HC III at Mahyolo Subcounty upgraded to HC IV status | 0 | 0 | 0 | 1 | 0 | Certificate of completion |
|  |  | Enhanced medical services provided |  |  |  |  |  |  |
|  |  | Expansion of patient care services |  |  |  |  |  |  |
| Construction of 5 stance pitlatrines at Kanara HCIII and Mahyolo HCIII | Five stance pit latrines constructed each at Kanara HC III, Mahyolo HC III, Kicheche HC III and Nyabbani HC III | Five stance pit latrines constructed each at Kanara HC III, Mahyolo HC III, Nyabbani HC III and Kicheche HC III | 0 | 1 | 1 | 2 | 1 | Certificate of completion |
|  |  | Sanitation standards improved |  |  |  |  |  |  |
|  |  | Community health enhanced through improved hygiene |  |  |  |  |  |  |
| Construction of semidetached staff house each at Ntara HC IV, Nyabbani HC III, Kicheche HC III, Mahyolo HC III and Kanara HCI II |  | Semidetached staff house each at Ntara HC IV, Nyabbani HC III, Kicheche HC III, Mahyolo HC III and Kanara HC III constructed | 0 | 0 | 2 Nyabbani and Kicheche HC III | 2 Mahyolo and Kanara HCIII | 1 Ntara HCIV | Certificate of completion |
| Upgrading of Rwenzaja HC II to HC III |  | Rwenzaja HC upgraded to HC III from HC II | 0 | 0 | 0 | 0 | 1 | Certificate of completion |
|  |  | Expanded healthcare services |  |  |  |  |  |  |
| OPD blocks renovated at Ntara HC IV, Kicheche HC III and Nyabbani HC III |  | One OPD block each at renovated at Ntara HC IV, Kicheche HC III and Nyabbani HC III | 0 | 0 | 1 | 1 | 1 | Certificate of completion |
|  |  | Increased OPD utilization | 1.2 | 1.5 | 1.8 | 1.9 | 2.0 | HMIS |

| Programme (a): Human Capital Development. |  | Outcome (b). |  | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 | FY2028/29 | FY2029/30 |  | Data Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: To improve population health, safety and management; Access to safe water sanitation and hygiene services |  | Outcome 1.1: Improved Health and wellbeing of the population |  | % of population with access to safe water | 61 | 65 | 67 |  | 69 | 72 | 75 |  | MWE MIS |  |
|  |  |  |  | % of population with access to safely managed sanitation | 74.5 | 76.5 | 78.5 |  | 80.5 | 82.5 | 84.5 |  | MWE MIS |  |
|  |  |  |  | % of the population with access to handwashing facilities in rural areas (handwashing with soap) | 30.4 | 35.4 | 40.4 |  | 45.4 | 50.4 | 55.5 |  | MWE MIS |  |
|  |  |  |  | % of rural water supply facilities that are functional at the time of spot check | 92 | 93 | 94 |  | 95 | 96 | 97 |  | MWE MIS |  |
| Intervention |  | Key Output |  | Indicator (f) |  |  | Time Frame and Output Target |  |  |  |  |  | Actors |  |
|  |  |  |  |  |  | FY2024/25 | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 |  | FY2029/30 |  |
| 1. Intervention Increase investment in water supply and sanitation infrastructure to increase service in underserved communities in urban, rural and refugee settlements |  | Output 1.1 Climate resilient water supply facilities constructed |  | No. of climate resilient piped water supply systems constructed in rural areas |  |  | 1 |  | 1 | 1 | 1 |  | 1 | MWE,DWO,CAO |
|  |  |  |  | No. of climate resilient point water facilities constructed in rural areas |  |  | 10 |  | 10 | 10 | 10 |  | 0 | MWE,DWO,CAO |
| 2.Intervention Increase rehabilitation and expansion of existing WASH infrastructure. |  | Output 2.1 Existing water supply facilities rehabilitated |  | No. of point water facilities in rural areas rehabilitated. |  |  | 20 |  | 20 | 20 | 20 |  | 20 | MWE,DWO,CAO |
|  |  | Output 2.2 Existing water supply upgraded and expanded |  | Length of water pipe network extended (Kms) in small towns |  |  | 3 |  | 3 | 3 | 3 |  | 3 | MWE,DWO,CAO |
| 3. Intervention Increase investment in water supply and sanitation infrastructure to increase service in underserved communities in rural, urban, and refugee settlements. |  | Output 3.1 Public sanitation facilities constructed |  | No. of new public sanitation facilities constructed in rural areas |  |  | 3 |  | 3 | 3 | 3 |  | 3 | MWE,DWO,CAO |
|  |  |  |  | No. of new public sanitation facilities constructed in urban areas |  |  | 2 |  | 2 | 2 | 2 |  | 2 | MWE,DWO,CAO |
| 4.Intervention Invest in effective management and regulation of the entire WASH value chain segments such as water production to point of use, catchment management, containment, emptying, |  | Develop and operationalise digitised regulatory information systems |  | No. of digitized regulatory information systems developed and operationalized |  |  | 1 |  | 1 | 1 | 1 |  | 1 | MWE,DWO,CAO |
| Project 1: (Title) Development of water supply and sanitation facilities |  | Water and sanitation facilities developed |  | No. of bore holes constructed |  |  | 10 |  | 10 | 10 | 10 |  |  | MWE,DWO,CAO |
|  |  |  |  | No. of mini-solar powered schemes constructed |  |  | 5 |  | 1 | 1 | 1 |  | 1 | MWE,DWO,CAO |
|  |  |  |  | No. of public sanitation facilities constructed |  |  | 5 |  | 5 | 5 | 5 |  | 5 | MWE,DWO,CAO |
| Programme (a): | Outcome (a) | Indicator (c) |  |  |  | FY2023/24(BL) | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 |  | FY2029/30 | Data Source |
|  |  |  |  |  |  | % | %%% |  | % | % | % |  | % |  |
| Programme Objective 1: Improve the foundation for human capital development | Outcome 1.1: Improved child wellbeing and development | Outcome Indicator 1 Percentage of children who are developmentally on track in at least three of the four domains of development (Numeracy, physical, socio-emotional, and learning) disaggregated by nationality, refugee status and disability. |  |  |  | 25 | 20 |  | 17 | 15 |  |  | 9 | MGLSD, MoES, MoH, UBoS |
|  |  | Outcome Indicator 2 Percentage of children who are attending early childhood development programs, disaggregated by nationality, refugee status and disability. |  |  |  | 17 | 17 |  | 9 | 6 | 4 |  | 3 | MGLSD, MoES, MoH, UBoS |
|  |  | Outcome Indicator 1 Percentage of children age 15-17 who have ever experienced sexual violence aggregated by nationality and refugee status |  |  |  | 29 | 32 |  | 40 | 50 | 61 |  | 72 | MGLSD, MoES, MoH, UBoS |
|  |  | Outcome Indicator 2 Proportion of duty bearers (families, parents and caregivers) complying to the parenting standards |  |  |  | 30 | 35 |  | 47 | 53 | 62 |  | 80 | MGLSD, MoES, MoH, UBoS |
|  |  | Outcome Indicator 3 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome (b) | Indicator (c) |  |  |  | FY2023/24(BL) | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Enhanced compliance of duty bearers (families, parents and caregivers) to parenting standards | Intermediate Outcome Indicator 1 |  |  |  | % | % |  | % | % | % |  | % |  |
|  |  | Intermediate Outcome Indicator 2 Proportion of duty bearers (families, parents and caregivers) complying to the parenting standards |  |  |  | 30 | 35 |  | 47 | 53 | 62 |  | 72 | MGLSD, MoES, MoH, UBoS |
| Intervention | Key Output |  | Indicator (f) |  |  | Time Frame and Output Target |  |  |  |  |  |  |  | Actors |
|  |  |  |  |  |  | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 |  | FY2029/30 |  |  |
| Intervention 1.1 (d) Strategic Intervention 1.4: Improve Physical and Cognitive development of children below 8 years | Output 1.1.1: Prog. Output 1.4.1: Capacity of duty bearers (D/CDOs, and parents/caregivers) built on effective parenting of children |  | Output Indicator 1 Number of D/CDOs trained on effective parenting of children |  |  | 20 |  | 40 | 60 | 60 |  | 60 |  | Kitagwenda DLG |
|  |  |  | Output Indicator 2 Number of caregivers/parents trained on effective parenting of children |  |  | 714 |  | 714 | 714 | 714 |  | 714 |  | Kitagwenda DLG |
|  |  |  | Output Indicator 3 Percentage of people who believe that a child needs to be physically punished aggregated by nationality, refugee status and disability. |  |  | 53% |  | 40% | 20% | 15% |  | 9% |  | MGLSD Annual report, Kitagwenda GBV, OVC MIS |
|  | Output 1.1.2: Strategies for preventing and responding to abuse, exploitation and violence against children, 0-8 years and their caregivers reviewed and rolled out |  | Output Indicator 1 Number of Sub counties and town councils implementing the strategies for preventing and responding to abuse, exploitation and violence against children, 0-8 years and their caregivers. |  |  | 10 |  | 10 | 22 | 42 |  | 42 |  | Kitagwenda DLG Planning Unit |
|  | Output 1.1.2: Establish a functional multisectoral coordination mechanism at national and sub-national levels to prevent and respond to violence against children and adolescents |  | Number of functional multi-sectoral coordination mechanisms established at national and sub-national levels including in refugee settlements |  |  | 43 |  | 43 | 43 | 43 |  | 43 |  | Kitagwenda DLG Planning Unit |

Objective 2 Programme Objective 2: To promote decent work and productive employment

| Programme (a): | Outcome (a) |  | Indicator (c) |  | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | % | % | % | % | % | % |  |  |
| Programme Objective 2: To promote decent work and productive employment | Prog. Outcome 2.1: Improved productive employment and decent work for all |  | Outcome Indicator 1 Average monthly earnings of employees (UGX |  | 120 | 150 | 200 | 240 | 280 | 300 |  | UBOS, MoPS, MGLSD |
|  | Intermediate Outcome (b) |  | Indicator (c) |  | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  | Data Source |
|  | Intermediate Outcome 1: Employment opportunities, safety and Compliance to labour standards increased measuring compliance? Define family) |  | Intermediate Outcome Indicator |  | % | % | % | % | % | % |  |  |
|  |  |  | Intermediate Outcome Indicator 1 Percentage of jobs created in formal and informal sector |  | 40 | 50 | 60 | 60 | 70 | 80 |  | MGLSD, NPA, UBOS |
|  |  |  | Percentage of workplaces reporting Occupational injuries and diseases |  | 50 | 60 | 60 | 80 | 90 | 100 |  | MGLSD, NPA, UBOS |
|  |  |  | Number of inspected work places compliant with labour standards |  | 45 | 47 | 50 | 70 | 80 | 100 |  | MGLSD, NPA, UBOS |
|  |  |  | Proportion of children aged 5-17 years engaged in child Labour excluding household chores aggregated by nationality, refugee status and disability. |  | 40 | 33 | 25 | 20 | 16 | 10 |  | MGLSD, NPA, UBOS |
|  |  |  | Number of jobs created by enterprises as a result of improved access to BDS |  | 100 | 170 | 300 | 500 | 900 | 1000 |  | MGLSD, NPA, UBOS |
| Intervention |  | Key Output |  | Indicator (f) |  |  | Time Frame and Output Target |  |  |  |  | Actors |
|  |  |  |  |  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 2.1 Strengthen compliance with labour standards and rights |  | Output 1.1.1: Prog. Output 2.1.1: Compliance with labour laws, Policies ,Guidelines and standards |  | Output Indicator 1 Number of labour, employment and OSH policies, Laws, regulations, guidelines and standards revised /developed |  |  | 20 | 40 | 60 | 60 | 60 | Kitagwenda DLG |
|  |  |  |  | Output Indicator 2 Number of workers, employers, training institutions and recruitment agencies sensitized on labour Policies, laws, regulations and guidelines |  |  | 714 | 714 | 714 | 714 | 714 | Kitagwenda DLG |
|  |  |  |  | Output Indicator 3 Number of workers, employers, training institutions and recruitment agencies sensitised on labour Policies, laws, regulations and guidelines aggregated by nationality and refugee status |  |  | 53% | 40% | 20% | 15% | 9% | MGLSD Annual report, Kitagwenda GBV, OVC MIS |
| Strategic Intervention 4.4 Improving Occupational Safety and Health (OSH) management |  | Output 1.1.2: Mechanisms for reducing workplace injuries, accidents and occupational diseases implemented |  | Number of workplaces with OSH systems in place |  |  | 43 | 43 | 43 | 43 | 43 | Kitagwenda DLG Planning Unit |
|  |  |  |  | Number of workplaces reproting OSH injuries and diseases to MGLSD |  |  |  |  |  |  |  |  |

Programme Objective 3: Reduce vulnerability, gender inequality and inequity along the lifecycle

Table 2: Programme Results and Targets

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/ 26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | % | % | % | % | % | % |  |
| Programme Objective 3: Reduce vulnerability, gender inequality and inequity along the lifecycle | Outcome 1.1: Reduced vulnerabilities, inequity and gender inequality | Outcome Indicator 1 Proportion of children married below 18 years | 17 N 32.8 | 15 | 13 | 11 | 9 | 6 | MGLSD, UBoS |
|  |  | Outcome Indicator 2 Average number of hours a week spent on un-paid care work by sex | 20 Hrs | 18 | 16 | 14 | 12 | 9 | MGLSD, UBoS |
|  |  | Outcome Indicator 3 Percentage distribution of working children aged 5-11; 12-13; 14-17 by sex and selected background characteristics urban/rural/age group/disability/orphan hood, nationality and refugee status) | 67 | 60 | 50 | 40 | 30 | 20 | MGLSD, UBoS |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Increased number of positions held by special interest groups (women, Older Persons, Persons with Disabilities (PWDs), Children& Youth, Ethnic minorities) in parliament, local governments and managerial positions in the formal sector | Intermediate Outcome Indicator 1 | % | % | % | % | % | % |  |
|  |  | Intermediate Outcome Indicator 2 Percentage of seats/positions held by special interest groups (women, Older Persons, Persons with Disabilities (PWDs), Children& Youth, Ethnic minorities) in the District Council and managerial positions in the formal sector | 27 women | 28 | 29 | 30 | 31 | 31 | MGLSD, NPA, UBOS |
|  |  |  | 3 older persons | 4 | 4 | 4 |  | 4 |  |
|  |  |  | 3 PWDs | 4 | 4 | 4 | 4 | 4 |  |
|  |  |  | 4 youth | 4 | 4 | 4 | 4 | 4 |  |
|  | Intermediate Outcome 1.2: Improved social protection systems by sex, distinguishing children, older persons, PWDs, work injury victims, the poor and vulnerable | Intermediate Outcome Indicator 1 Proportion of the population covered by social protection systems by sex, distinguishing children, youth, older persons, PWDs, work injury victims, the poor, vulnerable and refugees | 4 (Women) | 5 | 6 | 7 | 9 | 10 | MGLSD, UBoS, UNICEF |
|  |  |  | 5 Older persons | 5 | 7 | 8 | 9 | 10 | MGLSD, UBoS, UNICEF |
|  |  |  | 5 PWDs | 5 | 7 | 8 | 9 | 10 | MGLSD, UBoS, UNICEF |
|  |  |  | 5 Youth | 5 | 7 | 8 | 9 | 10 | MGLSD, UBoS, UNICEF |

| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  | Actors |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 3.1 Expand scope and coverage of livelihood enhancement and economic empowerment programmes for Youth, Women, Older Persons, PWDs and ethnic minorities | Output 3.1.1: Youth, Women, Older Persons, PWDs, indigenous ethnic minorities and refugees livelihood and empowerment programmes implemented | Output Indicator 1 Number of youth in livelihood and empowerment program aggregated by nationality and disability. | 2023 | 2163 | 2263 | 2326 | 2500 | Kitagwenda DLG |
|  |  | Number of women in livelihood and empowerment programmes aggregated by nationality and disability. | 1459 | 1672 | 1820 | 1960 | 2300 | MGLSD Annual reports, CBSD Annual reports |
|  |  | Number of Older Persons Supported in livelihood and empowerment programmes aggregated by nationality, refugee status and disability. | 120 | 156 | 192 | 244 | 256 | MGLSD Annual reports, CBSD Annual reports |
| Intervention 3.2 Promote Women’s economic empowerment, leadership and participation in decision making through investment in entrepreneurship programmes, business centres | Output 32.1: Programmes to promote women, Youth, PWDs, older persons and ethnic minorities in leadership and decision making in public and private designed and implemented. | Output Indicator 1 Number of programs in place for women | 2 | 2 | 2 | 2 | 2 | MGLSD Annual reports |
|  |  | Number of programs in place for youth | 2 | 2 | 2 | 2 | 2 | MGLSD Annual reports |
|  |  | Number of programs in place for PWDs | 1 | 1 | 1 | 1 | 1 | MGLSD Annual reports |
|  |  | Number of programs in place for older persons | 0 | 1 | 1 | 1 | 1 | MGLSD Annual reports |
|  |  | Percentage of Women, youth, PWDs engaged and with signed contracts in public procurement. | 6 | 10 | 50 | 65 | 80 | MGLSD, MLG, EOC, PPDA, LGs. |
|  | Output 32.2 Blueprint on disability prevention, management and inclusion implemented | Output Indicator Number of PWDs completing trained in skilling programmes aggregated by age, gender nationality, refugee status and disability | 100 | 300 | 300 | 300 | 300 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of PWDs provided with assistive and rehabilitative devices aggregated by age, gender, nationality and refugee status | 50 | 200 | 200 | 200 | 200 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of staff trained and recruited as Special Needs Education Teachers aggregated by age, gender, nationality, refugee status and disability | 10 | 10 | 10 | 10 | 10 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of eligible children accessing disability benefit/grant (‘000s) disaggregated by age, gender, nationality and refugee status | 50 | 100 | 100 | 100 | 100 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of PWDs benefitting from the disability grant aggregated by gender, age, nationality and refugee status | 150 | 500 | 500 | 500 | 500 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of PWDs recruited across government in Kitagwenda District ( LGs) | 5 | 10 | 10 | 10 | 10 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of creative and innovative projects initiated by young entrepreneurs with disabilities. | 2 | 5 | 5 | 5 | 5 | MGLSD Annual reports and Kitagwenda District Annual report |
| Strategic Intervention 3.3: Promote gender equality and equity responsive planning, budgeting and implementation | Prog. Output 3.3.1: Gender and equity compliance assessments conducted | Percentage of Divisions, Town council and Sub counties and counties complying with gender and equity responsive planning and budgeting. | 80 | 90 | 100 | 100 | 100 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of Divisions, Town council and Sub counties implementing gender and equity commitments | 80 | 90 | 100 | 100 | 100 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Percentage of private entities implementing gender and equity guidelines | 60 | 70 | 80 | 90 | 90 | MGLSD Annual reports and Kitagwenda District Annual report |
|  | Prog. Output 3.3.2: Gender statistics produced, accessed and used | Number of functional statistical GBVMIS with data | 1 | 1 | 1 | 1 | 1 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of District Abstracts with Gender data | 1 | 1 | 1 | 1 | 1 | MGLSD Annual reports and Kitagwenda District Annual report |
|  | Prog. Output 3.3.3: Scale up Gender Based Violence (GBV) and VAC prevention and response interventions at all levels | Number of GBV cases reported | 2056 | 1500 | 1000 | 1000 | 1000 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Percentage of children aged 13-17 who experienced sexual abuse aggregated by age, type of violence, gender, nationality, refugee status and disability | 17 | 15 | 12 | 10 | 6 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Proportion of ever partnered population aged 15 and above subjected to physical, sexual or psychological violence | 31 | 25 | 20 | 15 | 9 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of vulnerable persons incuding victims of VAC and GBV provided pyscosocial support services (aggregated by age and sex) | 1000 | 2000 | 3000 | 3000 | 4000 | MGLSD Annual reports and Kitagwenda District Annual report |
|  |  | Number of GBV shelters constructed | 0 | 0 | 1 | 0 | 0 | Kitagwenda District Annual report |
|  |  | Number of children living under residential care deinstitutionalized | 30 | 10 | 0 | 0 | 0 | Kitagwenda District Annual report |
|  | Prog. Output 3.3.4:Enhance protection, respect and redress mechanisms for Human rights | Number of pre-tribunal sessions conducted | 40 | 40 | 80 | 80 | 160 | CBS dept |
|  |  | Number of Social justice cases handled to completion. | 60 | 60 | 140 | 140 | 200 | CBS dept |
| Strategic Intervention 3.4: Expand the scope and coverage of Social Security along the life cycle. | Prog. Output 3.4.1: Direct Income Support Programmes designed and implemented | Number of Direct Income Support Interventions developed and implemented | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  | Prog. Output 3.4.2: Contributory Social Security to workers in the formal and Informal Sector implemented | Number of contributory Social Security packages implemented | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  | Prog. Output 3.4.3: Shock responsiveness in the delivery of Social Protection | Number of social protection programmes that are shock responsive implemented | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  | Prog. Output 3.4.4: Social protection systems strengthened. | Functional social protection systems in place and implemented | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  | Prog. Output 3.4.5: Develop and implement Health Insurance Schemes | Number of Community Health Insurance Scheme Supported | 1 | 1 | 1 | 1 | 1 | CBS dept |
| Strategic Intervention 3.5 : Provide holistic social care and support (assistance) services to vulnerable groups | Prog. Output 3.5.2: Holistic Social Care and Support for the Poor and Vulnerable persons provided across the Lifecycle | Number of eligible poor accessing social care and support aggregated by nationality, refugee status and disability in Kitagwenda District | 50 | 100 | 100 | 100 | 100 | CBS dept |
|  |  | No. of eligible children provided alternative care services aggregated by nationality, refugee status and disability in Kitagwenda District | 250 | 500 | 500 | 500 | 500 | CBS dept |
|  |  | No of PWDs provided rehabilitative and assistive devices in Kitagwenda District | 50 | 100 | 100 | 100 | 100 | CBS dept |
|  |  | Number of children rescued from the streets, discharged from remand homes and victims of trafficking supported under social reintegration mechanisms in Kitagwenda District | 50 | 50 | 30 | 30 | 20 | CBS dept |
|  |  | Institutional and Regulatory arrangements to strengthen the Social Service Workforce (Para social workers, VHTs, LC1 secretary for children affairs, Head teachers) in Kitagwenda District | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  |  | Institutional and Regulatory arrangements to strengthen the Social Service Workforce (Para social workers, VHTs, LC1 secretary for children affairs, teachers, Social medical workers)in Kitagwenda District | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  | Prog. Output 3.5.2: Improve the capacity of the social service workforce to deliver comprehensive care and support | Number of the social service workforce capacity Improved to deliver comprehensive care and support | 1 | 1 | 1 | 1 | 1 | CBS dept |
|  | Prog. Output 5.5.2: Family and Community capacities to care and support vulnerable individuals strengthened | Number of family and community member’ capacity strengthened to care and support vulnerable individuals. | 4000 | 4000 | 4000 | 4000 | 4000 | CBS dept |

Objective 4 Programme Objective 4: To mobilize communities for increased participation in national development.

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) |  | FY2025/26 |  | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | % |  | % |  | % | % |  | % | % |  |
| Programme Objective 4: To mobilize communities for increased participation in national development. | Prog. Outcome 4.1: Empowered and engaged Ugandan communities that actively address their social issues, promote equitable practices, and embrace positive behavioural changes for improved well-being and resilience | Outcome Indicator 1 Percentage of households who have adopted new behaviours (e.g. gender roles, healthcare-seeking behaviour, participation in community events). | 120 |  | 150 |  | 200 | 240 |  | 280 | 300 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |
|  |  | Percentage of households actively involved in national development initiatives and decision-making processes. | 30 |  | 40 |  | 60 | 80 |  | 90 | 90 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |
|  |  | Proportion of special interest groups (e.g. youth, women, PWDs, older persons, ethnic minorities) benefiting in national development initiatives i.e. PDM, YLP/UWEP, EMYOOGA, etc (%) | 30 |  | 40 |  | 40 | 50 |  | 60 | 70 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |
|  |  | Perception that harmful practices (e.g. child marriage, domestic violence, GBV, etc) are socially acceptable within the community (%) | 60 |  | 70 |  | 80 | 90 |  | 90 | 95 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) |  | FY2025/26 |  | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1: Increased participation of the population in development initiatives in development initiatives | Intermediate Outcome Indicator | % |  | % |  | % | % |  | % | % |  |
|  |  | Intermediate Outcome Indicator 1 Percentage of households benefiting in development initiatives | 40 |  | 50 |  | 60 | 60 |  | 70 | 80 | MGLSD, NPA, UBOS |
|  |  | Proportion of households informed about national initiatives | 50 |  | 60 |  | 60 | 80 |  | 90 | 100 | MGLSD, NPA, UBOS |
|  |  | Percentage of households participating in village saving initiatives | 45 |  | 47 |  | 50 | 70 |  | 80 | 100 | MGLSD, NPA, UBOS |
| Intervention | Key Output | Indicator (f) |  | Time Frame and Output Target |  |  |  |  |  |  |  | Actors |
|  |  |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 | FY2028/29 |  | FY2029/30 |  |
| Intervention 4.1 Promote community mobilization, sensitization and awareness creation for demand and uptake of development initiatives | Output41.1.1: Prog. Increased awareness and capacity of community members to participate in and influence national development processes | Output Indicator 1 Number of community duty bearers (Civil servants, community leaders, religious leaders, parish chiefs) trained on CMMC |  | 20 |  | 40 |  | 60 | 60 |  | 60 | MGLSD, Kitagwenda District |
|  |  | Output Indicator 2 Percentage of villages sensitized on the negative social and cultural practices (Teenage pregnancies, child labour, child marriage, children on the move, FGM, VAC, SGBV, etc) |  | 714 |  | 714 |  | 714 | 714 |  | 714 | MGLSD, Kitagwenda District |
|  |  | Output Indicator 3 Number of barazas conducted |  | 53% |  | 40% |  | 20% | 15% |  | 9% | MGLSD, Kitagwenda District |
|  |  | Number of blind, deaf, and elderly persons sensitized on business, chattels, civil, intellectual property, insolvency registration services |  | 25 |  | 30 |  | 40 | 50 |  | 70 | MGLSD, Kitagwenda District |
|  |  | Number of youths, women, PWDs and older persons sensitized on business formalization |  | 30 |  | 40 |  | 50 | 70 |  | 90 | MGLSD, Kitagwenda District |
|  | Prog. Output 7.1.4: Enhanced reach of media houses in informing and engaging communities about national initiatives | Number of media programs broadcast on national and District development initiatives. |  | 5 |  | 6 |  | 6 | 7 |  | 8 | MGLSD, Kitagwenda District |
|  |  | Number of DDP IV programmes content translated in various indigenous languages |  |  |  |  |  |  |  |  |  | MGLSD, Kitagwenda District |
| Strategic Intervention 4.2: Build capacities and equip community institutions at central, local government and non-state actors | Prog. Output 4.1.2: Institutional capacity for central, local government, political leaders and non-state actors in the implementation of CMMC strengthened | Number of stakeholders at national and local government level capacity developed |  | 43 |  | 43 |  | 43 | 43 |  | 43 | Kitagwenda DLG Planning Unit |
| Strategic Intervention 7.3: Develop and Implement a national civic education and adult literacy programmes with emphasis on roles and responsibilities of families, communities and citizens | Prog. Output 7.3.1: Robust non formal Adult Learning and community Education System implemented | Number of S/C and TC implementing ICOLEW |  | 43 |  | 43 |  | 43 | 43 |  | 43 | MGLSD, Kitagwenda District |
|  |  | Number of persons participating in adult learning and community education programmes |  | 430 |  | 430 |  | 430 | 430 |  | 430 | Kitagwenda DLG Planning Unit |
|  |  | No of persons completing adult learning and community education programmes |  | 300 |  | 300 |  | 300 | 300 |  | 300 | MGLSD, Kitagwenda District |
|  | Prog. Output 4. 3.2: A national civic education program aimed at improving the level of awareness of rights, duties and responsibilities of individuals, families, communities and citizens developed and implemented | A national civic education program in place |  | 1 |  | 1 |  | 1 | 1 |  | 1 | Kitagwenda DLG Planning Unit |
|  |  | Number of people participating in the civic education program |  | 43000 |  | 43000 |  | 43000 | 43000 |  | 43000 |  |

Objective 5 Programme Objective 5: To promote culture and creative industries

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | % | % |  | % |  | % |  | % | % |  |  |
| Programme Objective 5: To promote culture and creative industries | Prog. Outcome 5.1: Improved ecosystem for culture and creative industries | Outcome Indicator 1 Proportion of jobs created by the culture and creative industries | 120 | 150 |  | 200 |  | 240 |  | 280 | 300 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |  |
|  |  | Percentage of the population employed in the arts, entertainment and recreation | 2 | 2 |  | 2 |  | 2 |  | 2 | 2 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |  |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 | FY2029/30 | Data Source |  |
|  | Intermediate Outcome 1: Improved access to cultural goods and services. | Intermediate Outcome Indicator | % | % |  | % |  | % |  | % | % |  |  |
|  |  | Intermediate Outcome Indicator 1 Number of Arts and culture facilities established | 40 | 50 |  | 60 |  | 60 |  | 70 | 80 | MGLSD, UBOS |  |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |  |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |  |  |
| Intervention 5.1 Empower culture and creative practitioners with resources, entrepreneurship skills and opportunities using appropriate technologies and innovations for value addition. | Output41.1.1: Prog. Practioners and enterprenuers capacity under CCIs enhanced ( Music, films, visual art, fashion and design etc.) | Output Indicator 1 Number of CCIs practitioners enrolled and trained in skills development and entrepreneurship | 20 | 40 | 60 |  | 60 |  | 60 |  |  |  | MGLSD, Kitagwenda District |
|  |  | Output Indicator 2 Number of networking events organized for the CCIs | 1 | 1 | 1 |  | 1 |  | 1 |  |  |  | MGLSD, Kitagwenda District |
|  | Prog. Output 5.1.2: Cultural heritage preserved and promoted | Number of traditional institutions supported to promote indegineous knowledge and skills | 2 | 2 | 2 |  | 2 |  | 2 |  |  |  | MGLSD, Kitagwenda District |
|  |  | Number of traditional institutional document and recordings databases on cultural traditions, norms and practices | 2 | 2 | 2 |  | 2 |  | 2 |  |  |  | MGLSD, Kitagwenda District |
| Strategic Intervention 4.2: Build capacities and equip community institutions at central, local government and non-state actors | Prog. Output 5.1.3: An enabling environment for Small and medium CCI enterprises created | Number of CCIs SMEs created. | 2 | 2 | 2 |  | 2 |  | 2 |  |  |  | Kitagwenda DLG Planning Unit |
|  |  | Number of MOUs with financing institutions for supporting CCIs investment developed. | 2 | 2 | 2 |  | 2 |  | 2 |  |  |  | Kitagwenda DLG Planning Unit |
|  |  | Number of Cultural and Creative Industry domain SACCOs licensed | 2 | 2 | 2 |  | 2 |  | 2 |  |  |  | Kitagwenda DLG Planning Unit |
|  |  | Number of CCIs projects financed. | 2 | 2 | 2 |  | 2 |  | 2 |  |  |  | Kitagwenda DLG Planning Unit |
|  |  | Number of registered companies under the Culture and Creative Industry | 1 | 1 | 1 |  | 1 |  | 1 |  |  |  | Kitagwenda DLG Planning Unit |

Objective 6: Programme Objective 6: To promote culture and creative industries

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | % | %%% | % |  | % |  | % |  | % |  |
| Programme Objective 6: Strengthen policy, legal, institutional coordination and regulatory frameworks for Human Capital Development | Prog. Outcome 5.1: Improved institutional coordination and regulatory frameworks for Human Capital Development | Outcome Indicator 1 Number of ordinances and position policy papers developed | 120 | 150 | 200 |  | 240 |  | 280 |  | 300 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |
|  |  | Number of coordination initiatives strengthened and functional | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | MGLSD, MoICT/NG, NGOs, CSOs, Development Partners |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 1: HCD Secretariat administration services provided | Intermediate Outcome Indicator |  |  |  |  |  |  |  |  |  |  |
|  |  | Intermediate Outcome Indicator 1 Number of HCD programme meetings held | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | HCD SECRETARIAT |
|  | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |
| Intervention 5.1 Strategic Intervention 6. : Capacitate institutions to deliver Human Capital Development Programme | Output41.1.1: HCD TDLG administration services provided | Output Indicator 1 Number of contracts Committee meetings conducted | 3 | 3 |  | 3 |  | 3 |  | 3 |  | MGLSD, Kitagwenda District |
|  |  | Output Indicator 2 Policy briefs and position papers on topical sectoral public policy issues developed. | 1 | 1 |  | 1 |  | 1 |  | 1 |  | MGLSD, Kitagwenda District |
|  |  | Number of Contracts Committee meetings conducted | 5 | 5 |  | 5 |  | 5 |  | 5 |  |  |
|  | Prog. Output 5.1.2: Cultural heritage preserved and promoted | Number of traditional institutions supported to promote indegineous knowledge and skills | 2 | 2 |  | 2 |  | 2 |  | 2 |  | MGLSD, Kitagwenda District |
|  |  | Number of traditional institutional document and recordings databases on cultural traditions, norms and practices | 2 | 2 |  | 2 |  | 2 |  | 2 |  | MGLSD, Kitagwenda District |
| Strategic Intervention 4.2: Build capacities and equip community institutions at central, local government and non-state actors | Prog. Output 5.1.3: An enabling environment for Small and medium CCI enterprises created | Number of CCIs SMEs created. | 2 | 2 |  | 2 |  | 2 |  | 2 |  | Kitagwenda DLG Planning Unit |
|  |  | Number of MOUs with financing institutions for supporting CCIs investment developed. | 2 | 2 |  | 2 |  | 2 |  | 2 |  | Kitagwenda DLG Planning Unit |
|  |  | Number of Cultural and Creative Industry domain SACCOs licensed | 2 | 2 |  | 2 |  | 2 |  | 2 |  | Kitagwenda DLG Planning Unit |
|  |  | Number of CCIs projects financed. | 2 | 2 |  | 2 |  | 2 |  | 2 |  | Kitagwenda DLG Planning Unit |
|  |  | Number of registered companies under the Culture and Creative Industry | 1 | 1 |  | 1 |  | 1 |  | 1 |  | Kitagwenda DLG Planning Unit |

# Strategic Objective 3: Strengthen private sector capacity to drive growth and create jobs

Programme 5: Private Sector Development

Private Sector Development Programme:  Private sector-led industrial development will play a significant role in bringing about the much-needed structural changes that can set the economies on a path of sustained economic growth. Economic development is driven by access to finance; to produce and especially add value, you need capital to invest and the most critical source of funding are commercial banks which are in the hands of the private sector, mainly foreign owners. Commercial bank interest rates have for long been above 20 per cent and reached a staggering 30 per cent which has greatly hindered access to credit for both farmers and entrepreneurs.

Programme Objective 1: Sustainably lower the cost of financing

##### Table 3.7: Programme Results and Targets for Private Sector Development

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sustainably lower the cost of financing | Access to affordable finance | Growth in private sector credit |  | 30 | 30 | 20 |  | 10 |  | 10 | Performance reports |
|  | Intermediate Outcome: | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Increasing short term financing for key growth Sectors | Total value (UGX billions) of short-term loans to PDM beneficiaries |  | 10 | 10 | 10 |  | 10 |  | 10 | Credit Disbursements from PDM, Emyooga & SBRF) |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |
| Increase access and affordability of financial services | Increase in number of households accessing credit | Growth in the number of beneficiaries accessing under Parish Development model and Emyooga funds |  |  |  |  |  |  |  |  | Credit Disbursments from PDM, Emyooga & SBRF) |

Programme Objective 2: Strengthen the organisation and institutional Capacity of the private sector

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 2: Strengthen the organisation and institutional Capacity of the private sector | Enhanced survival & Growth of MSMEs | Outcome Indicator: Growth in private sector credit |  | 30 | 30 |  | 20 |  | 10 |  | 10 | Performance reports |
|  | Intermediate Outcome: | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Enhanced survival of MSMEs | Intermediate Outcome Indicator 1: Average Life of businesses |  | 2 | 2 |  | 2 |  | 2 |  | 2 | Performance reports |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |
| Roll out business development services (BDS) to support MSMEs | Compliance to Good corporate Governance best practices improved | Number of Business Development Services (BDS) trainings conducted | 4 | 4 |  | 4 |  | 4 |  | 4 |  | Performance reports |

# Strategic Objective 4: Build and maintain strategic Sustainable infrastructure in transport, housing, energy, water, industry and ICT

# Programme 6: Integrated Transport Infrastructure and Services

Programme: Integrated Transport Infrastructure and Services: aims to have a seamless, safe, inclusive and sustainable multi-modal transport system. Key challenges includes roads being impassable due to the heavy rains the district faced during the financial years, Water drainages are always blocked by the community and in a number of areas the community gardens are up to the road reserve.

Table 3.8: Programme Results and Targets for Integrated Transport Infrastructure and Services

Programme Objective 1: To strengthen transport asset management

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 | FY2028/29 |  | FY2029/30 | Data Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: To strengthen transport asset management | Outcome 1.1: Longer service life of transport infrastructure | Outcome Indicator 1 Average Service life of transport infrastructure (first class marram roads yrs) | 5 yrs | 5 yrs |  | 5 yrs |  | 5 yrs | 5 yrs |  | 5 yrs | Annual district roads condition survey |  |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 | FY2028/29 |  | FY2029/30 | Data Source |  |
|  | Intermediate Outcome 1.1: Improved condition of transport infrastructure | Intermediate Outcome Indicator 1 % of DUCAR in fair to good condition | 60% | 62% |  | 64% |  | 66% | 68% |  | 70% | Annual district roads condition survey |  |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  |  |  |  | Actors |  |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 |  | FY2028/29 | FY2029/30 |  |  |  |  |
| Intervention 1.1 (d) Rehabilitate and maintain transport infrastructure; | Output 1.1.1: Road Transport infrastructure Maintained | Output Indicator 1 Km of Bridges Maintained on District Roads | 2 | 2 | 2 |  | 2 | 2 |  | LG |  |  |
|  |  | Output Indicator 2 Number of Culverts maintained on District Roads | 3 | 3 | 3 |  | 3 | 3 |  | LG |  |  |
|  |  | Output Indicator 3 Number of Culverts maintained on CARs | 5 | 5 | 5 |  | 5 | 5 |  | LG |  |  |
|  | Output 1.1.2: Road Transport infrastructure Rehabilitated | Output Indicator 1 Km of District gravel roads rehabilitated (MoWT) | 10 | 10 | 10 |  | 10 | 10 |  | (MoWT) |  |  |
|  |  | Output Indicator 2 Km of District gravel roads rehabilitated (LGs)) | 15 | 15 | 15 |  | 15 | 15 |  | LG |  |  |
|  |  | Output Indicator 3 Km of Low Volume Sealed roads rehabilitated | 2 | 2 | 5 |  | 5 | 5 |  | LG |  |  |
|  |  | Output Indicator 4 km of Community Access Roads Rehabilitated (MoWT) | 15 | 15 | 15 |  | 15 | 15 |  | (MoWT) |  |  |
| Intervention 1.2 (d) Strengthen mechanical engineering services | Output 1.2.1: Mechanical engineering services strengthened | Output Indicator 1 Number of salvageable tools, machines and equipment repaired and/or upgraded | 11 | 11 | 11 |  | 11 | 11 |  | LG |  |  |
|  |  | Output Indicator 2 Number of field supervision and monitoring vehicles purchased | 01 | 0 | 0 |  | 0 | 0 |  | LG |  |  |
|  |  | Output Indicator 3 % of road construction equipment rehabilitated | 2 | 2 | 2 |  | 2 | 2 |  | LG/(MoWT) |  |  |

# Programme 7: Sustainable Urbanisation and Housing

Sustainable Urbanisation and Housing Programme: aims to attain inclusive, productive and live able urban areas for socioeconomic transformation. Lack of physical development plans is contributing to uncoordinated development, land use conflicts, inefficient land use and invasion of environment. Several housing units in Town councils and Growth centres haven’t gone through any approval process creating potential for growth of slums if nothing is done then ecologically sensitive ecosystems in towns will be depleted deteriorating urban environment and slum development will continue to grow.

##### Table 3.9: Programme Results and Targets for Sustainable Urbanisation and Housing

Programme Objective 1: Strengthen land use management

| Programme (a): | Outcome (a) |  | Indicator (c) | FY2023/24(BL) |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Strengthen land use management | Outcome1.1: Improved district land tenure security. |  | Outcome Indicator 1 Proportion of district land with secure tenure rights to land, with legally recognized documentation | 40 |  | 45 | 50 | 60 | 65 | 70 | Annual performance report |
|  | Intermediate Outcome (b) |  | Indicator (c) | FY2023/24(BL) |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Increased registration of land |  | Intermediate Outcome Indicator 1 (%) of district Land Registered | 40 |  | 45 | 50 | 60 | 65 | 70 | PIR |
|  | Intermediate Outcome 1.2: Increased compliance to Land Use in the district areas |  | Intermediate Outcome Indicator 2 Level of Compliance to the land use regulatory framework in urban areas | 2 |  | 3 | 4.5 | 5 | 8 | 10 | APR |
| Intervention |  | Key Output | Indicator (f) |  | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  |  |  | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 1.1 Undertake Land Tenure Security Enhancement Programmes |  | Output 1.1.1: District land bank established | Output Indicator 1 Number of land inventory established |  | 1 |  | 1 | 1 | 1 | 1 | DLB, LMO |
|  |  | Output 1.1.2: District Land Surveyed and titled | Output Indicator 2 Proportion of district land titled |  | 45 |  | 50 | 60 | 65 | 70 | DLB, LMO, MZO |
| Intervention 1.2 Develop lower level PDPs to operationalise the District Physical Development Plan |  | Output 1.2.1: Lower level Physical and detailed plans developed and implemented | Output Indicator 1 Number of Town Council PDPs developed |  | 1 |  | 1 | 1 | 1 | 1 | LMO, SAS, TCs |
|  |  |  | Output Indicator 2 Number of Detailed Plans developed |  | 1 |  | 1 | 1 | 1 | 1 | LMO, SAS, TCs |

Strategic Objective 5: Strengthen good governance, security, and the role of the state in development.

Programme 8: Development Plan Implementation

Development Plan Implementation Programme:  aims to increase the efficiency and effectiveness in the implementation of the Plan. Over the plan period, the following results are expected: increased GDP growth rate, increased revenue, and improvements in alignment of plans and budgets key challenges the district facing include poor revenue collection, low local revenue base, inadequate data for evidence based planning

##### Table 3.10: Programme Results and Targets for Development Plan Implementation

Programme Objective 1: Strengthen Capacity for Evidence Based Development Planning across Government

| Programme (a): | Outcome (a) |  | Indicator (c) |  | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  | Data Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Strengthen Capacity for Evidence Based Development Planning across Government | Outcome 1.1: Enhanced Capacity for evidence based planning |  | Outcome Indicator 1: Statistical performance indicator (SPI) |  | 100 | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | Departmental reports |  |
|  | Intermediate Outcome (b) |  | Indicator (c) |  | FY2023/24(BL) | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  | Data Source |  |
|  | Intermediate Outcome 1.1: Improved alignment of Plans to DDP |  | Intermediate Outcome Indicator 1 : Level of alignment of Development Plans to DDP |  |  | 100% |  |  |  |  |  |  |  |  |  | Certification from NPA |  |
|  | Intermediate Outcome 1.2: Increased use of research and statistics for development policy and planning across government and key private sector players |  | Intermediate Outcome Indicator 1: Percentage of DDP IV results informed by official statistics at goal and objective level |  | 100% | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Departmental reports |  |
|  |  |  | Intermediate Outcome Indicator 2: Proportion of National Standard indicators (NSI) with up-to-date data |  | 100% | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | Reports from Ministry of Finance |  |
| Intervention |  | Key Output |  | Indicator (f) |  |  | Time Frame and Output Target |  |  |  |  |  |  |  |  |  | Actors |
|  |  |  |  |  |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |
| Intervention 1.1: Build capacity in development planning and project formulation at all levels of government. |  | Output 1.1.1: Gender and equity responsive plans |  | Output Indicator : Proportion of LGs with gender and equity responsive plans |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | HLG LLGs |
| Intervention 1.2: Generate and use statistical data to inform Development plans at all levels |  | Output 1.2.1: Updated Administrative data and Statistics |  | Output Indicator : Proportion of LGs with updated DDP Administrative data |  |  | 60% |  | 70% |  | 80% |  | 90% |  | 100% |  | HLG LLGs |
|  |  |  |  | Output Indicator : Proportion of programmes with updated DDP Administrative data |  |  | 60% |  | 70% |  | 80% |  | 90% |  | 100% |  | HLG LLGs |
|  |  | Output 1.2.2: Plan for National Statistical Development (PNSDIV) |  | Output Indicator : Proportion of functional statistical units in LGs |  |  | 80% |  | 80% |  | 80% |  | 80% |  | 80% |  | HLG LLGs |
|  |  |  |  | Output Indicator : Proportion of LGs implementing the PNSD |  |  | 70% |  | 70% |  | 70% |  | 70% |  | 70% |  | HLG |

Programme Objective 2: Strengthen Oversight, Coordination and M&E across Government

| Sub-programme (a): |  |  | Intermediate Outcome (b) |  | Indicator (c) |  | FY2023/24(BL) |  | FY2025/26 |  |  | FY2026/27 |  |  | FY2027/28 |  |  |  |  | FY2028/29 |  |  |  | FY2029/30 |  |  |  | Data Source |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 2: Strengthen Oversight, Coordination and M&E across Government |  |  | Outcome 2.1: Improved delivery of the Plan |  | Outcome Indicator 1: Percentage of DDP IV results on target |  | 50% |  | 90% |  |  | 90% |  |  | 90% |  |  |  |  | 90% |  |  |  | 90% |  |  |  | Midterm review report Departmental reports |  |  |  |
|  |  |  | Intermediate Outcome 1.1: Enhanced coordination for the implementation of DDPIV |  | Intermediate Outcome Indicator 1 : Functionality of the DDPIV coordination architecture |  | 90% |  | 90% |  |  | 90% |  |  | 90% |  |  |  |  | 90% |  |  |  | 90% |  |  |  | DTPC minutes |  |  |  |
|  |  |  | Intermediate Outcome 1.2: Strengthened oversight function for the delivery of the plan |  | Intermediate Outcome Indicator 1: Level of Oversight across Government |  | 90% |  | 90% |  |  | 90% |  |  | 90% |  |  |  |  | 90% |  |  |  | 90% |  |  |  | Monitoring reports |  |  |  |
| Intervention |  | Key Output |  |  | Indicator (f) |  |  |  |  | Time Frame and Output Target |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actors |  |
|  |  |  |  |  |  |  |  |  |  | FY2025/26 |  |  | FY2026/27 |  |  |  | FY2027/28 |  |  |  |  | FY2028/29 |  |  |  | FY2029/30 |  |  |  |  |  |
| Intervention 1.1: Strengthen the oversight function across departments |  | Output 1.1.1: Consolidated District Risk Management Register |  |  | Output Indicator : Percentage of departments with standard risk registers |  |  |  |  | 100% |  |  | 100% |  |  |  | 100% |  |  |  |  | 100% |  |  |  | 100% |  |  |  | HoDs |  |
|  | Intermediate Outcome (b) |  |  | Indicator (c) |  |  |  | FY2023/24(BL) |  |  | FY2025/26 |  |  | FY2026/27 |  |  |  | FY2027/28 |  |  | FY2028/29 |  |  |  |  |  | FY2029/30 |  |  | Data Source |  |
|  | Intermediate Outcome 1.1: Improved M&E Performance across government |  |  | Intermediate Outcome Indicator 1 : Percentage of DDP IV results on target |  |  |  | 60% |  |  | 70% |  |  | 80% |  |  |  | 90% |  |  | 100% |  |  |  |  |  | 100% |  |  | MTR, Quarterly progress reports |  |
| Intervention | Key Output |  |  | Indicator (f) |  |  |  | Time Frame and Output Target |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actors |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | FY2025/26 |  |  | FY2026/27 |  |  |  | FY2027/28 |  | FY2028/29 |  |  |  | FY2029/30 |  |  |  |
| Intervention 1.1: Strengthen the M&E function across government.. |  |  | Output 1.1.1: Mid Term Review of DDPIV, Vision 2040 and End term evaluations conducted |  |  | Output Indicator 1: No. Mid Term Review reports of DDPIV in Place |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  | HoDs |  |
|  |  |  |  |  |  | Output Indicator 2: No. End Term Review reports of DDPIII in Place |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | HoDs |  |

Programme Objective 1: Enhance Resource Mobilization to finance the National Development Plan

| Programme (a): | Outcome (a) |  | Indicator (c) |  | FY2023/24(BL) |  |  |  |  |  |  |  | FY2025/26 |  | FY2026/27 |  |  | FY2027/28 |  |  |  | FY2028/29 |  |  | FY2029/30 | Data Source |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: Enhance Resource Mobilization to finance the National Development Plan | Outcome 1.1 Increased OSR performance and budget self sufficiency |  | Outcome Indicator1 OSR to Total Revenue % |  | 1.91 |  |  |  |  |  |  |  | 2.41 |  | 2.91 |  |  | 3.41 |  |  |  | 3.91 |  |  | 4.41 | Kitagwenda district budget estimates |  |  |  |
|  | Outcome 1.2: Fiscal sustainability enhanced |  | Outcome Indicator 1 OSR to Total Revenue % |  | 1.91 |  |  |  |  |  |  |  | 2.41 |  | 2.91 |  |  | 3.41 |  |  |  | 3.91 |  |  | 4.41 | Kitagwenda district budget estimates |  |  |  |
|  | Intermediate Outcome (b) Increase domestic revenue performance and budget self sufficiency |  | Indicator (c) OSR to Total Revenue % |  | FY2023/24(BL) |  |  |  |  |  |  |  | FY2025/26 |  | FY2026/27 |  |  | FY2027/28 |  |  |  | FY2028/29 |  |  | FY2029/30 | Data Source |  |  |  |
|  | Intermediate Outcome 1.1: Increased domestic revenue performance and budget self sufficiency |  | Intermediate Outcome Indicator 1 OSR to Total Revenue |  | 1.91 |  |  |  |  |  |  |  | 2.41 |  | 2.91 |  |  | 3.41 |  |  |  | 3.91 |  |  | 4.41 | Kitagwenda district budget estimates |  |  |  |
| Intervention Implement the Tax compliance improvement initiatives | Key Output Local Government own source revenue growth |  | Indicator (f) Percentage increase in own source revenue |  | Time Frame and Output Target |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actors |  |  |  |  |
|  |  |  |  |  | FY2025/26 |  |  |  |  |  |  |  | FY2026/27 | FY2027/28 |  |  |  |  | FY2028/29 |  |  |  |  | FY2029/30 |  |  |  |  |  |
| Intervention 1.1 (d) Enhanced OSR mobilization through improved tax administration | Output 1.1.1: increased OSR |  | Output Indicator 1 Amount of OSR collected |  | 2.1bn |  |  |  |  |  |  |  | 2.7bn | 3.3bn |  |  |  |  | 4.0bn |  |  |  |  | 4.7bn |  |  |  |  | Finance dept |
|  |  |  | Output Indicator 2 OSR to Total Revenue % |  | 2.41 |  |  |  |  |  |  |  | 2.91 | 3.41 |  |  |  |  | 3.91 |  |  |  |  | 4.41 |  |  |  |  | Finance dept |
| Programme (a): | Outcome (a) | Indicator (c) |  | FY2023/24(BL) |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  |  |  | FY2029/30 |  |  |  | Data Source |  |  |  |  |  |  |
| Programme Objective 2: Strengthen Budgeting and Accountability systems | Outcome 1.1Budget Credibility and Fiscal Discipline | Outcome Indicator1 % of budget realised against originally approved budget |  | 113.99 |  |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 100 |  |  |  | Kitagwenda district financial statements |  |  |  |  |  |  |
|  |  | % of funds absorbed against funds realised |  | 94.86 |  |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 100 |  |  |  | Kitagwenda district financial statements |  |  |  |  |  |  |
| Sub-programme (a): | Intermediate Outcome (b) Increased alignment of budget to the National Development Plan | Indicator (c) Level of Compliance of the District Budget to NDPIV |  | FY2023/24(BL) |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  |  |  | FY2029/30 |  |  |  | Data Source |  |  |  |  |  |  |
|  | Intermediate Outcome 1.1: Credible Budget | Intermediate Outcome Indicator 1 % of budget realised against originally approved budget |  | 113.99 |  |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 100 |  |  |  | Kitagwenda district financial statements |  |  |  |  |  |  |
|  |  | Intermediate Outcome Indicator 2 % of funds absorbed against funds realised |  | 94.86 |  |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 100 |  |  |  | Kitagwenda district financial statements |  |  |  |  |  |  |
|  | Intermediate Outcome 1.2: Accurate financial reporting | Intermediate Outcome Indicator 1 Annual Financial statement Opinion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OAG reports |  |  |  |  |  |  |
| Intervention | Key Output | Indicator (f) |  |  |  | Time Frame and Output Target |  |  |  |  |  |  |  |  |  | A |  |  |  |
|  |  |  |  |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  |  |  | FY2029/30 |  |  |  |  |  |  |  |  |  |  |
| Intervention Strengthen alignment of LGs budgets to NDP priorities during budget preparation and execution | Output 1.1.1: Aligned LGs and Programme budgets to the NDP priorities | Output Indicator 1 Level of Compliance of the LGs budget to NDPIV |  |  |  | 85% |  | 85% |  | 85% |  | 85% |  |  |  | 85% |  |  |  | Finance dept |  |  |  |  |  |  |

Programme 9: Governance and Security

Governance security, and peace promote transparency, accountability, and efficient resource management creating a safe and conducive environment for investment and economic activity. The Local Government Act, Cap 138 (Section 35 (1)) designates Districts Councils as the planning authorities for the districts. The Act mandates the district technical planning committees to coordinate and integrate all the sectoral plans of lower level Local Governments for presentation to the district council (Section 36 (2)). The district is currently challenged with inadequate office space in several lower local governments

##### Table 3.11: Programme Results and Targets for Governance and Security

Programme Objective 1: Strengthen governance structures and enhance community security

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Governance and Security Objective 1: Strengthen Government Institutions for effective and efficient service delivery | Outcome 1.1: Improved efficiency and transparency | Outcome Indicator 1 Percentage increase in citizen satisfaction with local government services | 10 | 15 | 20 | 30 | 35 | 40 | Community surveys |
|  |  | Outcome Indicator 2 No of barazas conducted in a year | 1 | 1 | 2 | 2 | 3 | 4 | Meeting records |
|  | Outcome 1.2: Enhance staff safety and Security | Outcome Indicator 1 Percentage increase of staff attendance to duty | 80 | 85 | 90 | 95 | 96 | 97 | Monthly staff attendance analysis reports |
|  |  | Outcome Indicator 2 Percentage increase in walk ins to Subcounty in regards to local government services | 15 | 20 | 25 | 30 | 35 | 40 | Service usage statistics |
|  |  | Outcome Indicator 3 Percentage increase of staff reporting to work on time and leaving at the right time | 70 | 75 | 80 | 85 | 90 | 95 | Attendance log ins and log outs |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24 (BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 1.1: Enhanced inter agency collaboration | Intermediate Outcome Indicator 1 No of coordination meetings held | 2 | 2 | 2 | 3 | 3 | 4 | Minutes |
|  |  | Intermediate Outcome Indicator 2 No of collaborative projects initiated | 1 | 2 | 2 | 3 | 3 | 4 | Project records |
|  | Intermediate Outcome 1.2: Improved stakeholder engagement | Intermediate Outcome Indicator 1 Percentage increase of stakeholder engagement in governance issues | 20 | 25 | 30 | 35 | 40 | 45 | Participation surveys |
|  |  | Intermediate Outcome Indicator 2 No of feedback mechanisms established for stakeholder input | 2 | 4 | 6 | 8 | 10 | 12 | Feedback logs |
|  |  | Intermediate Outcome Indicator 3 Percentage of stakeholders reporting satisfaction with coordination efforts | 60 | 65 | 70 | 75 | 80 | 85 | Stakeholder surveys |
| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2025/26 |  | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 1.1 (d) Construction Administration blocks | Output 1.1.1: Completed construction of administration blocks | Output Indicator 1 No of blocks constructed | 3 |  | 3 | 3 | 3 | 2 | Administration dept |
|  |  | Output Indicator 2 Percentage of budget utilized effectively | 80 |  | 85 | 90 | 95 | 95 | Administration dept |
|  |  | Output Indicator 3 No of staff utilising the administration blocks | 100 |  | 100 | 100 | 100 | 100 |  |

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Governance and security Programme Objective 1: To Strengthen public policy management, legal and institutional frameworks for socio-economic transformation | Outcome 1.1: Effective, efficient and equitable utilization of public resources | Outcome indicator 1: Percentage increase in unqualified audit opinion |  |  |  |  |  |  | Audited financial statements/ accounts |
|  | Outcome 1.2: Effective and efficient utilization of public resources | Outcome Indicator 1: Percentage improvement in value for money audit ratings | 4 IA Reports produced, disseminated and submitted | 4 IA Reports produced, disseminated and submitted | 4 IA Reports produced, disseminated and submitted | 4 IA Reports produced, disseminated and submitted | 4 IA Reports produced, disseminated and submitted | 4 IA Reports produced, disseminated and submitted | 4 IA Reports produced, disseminated and submitted |

| Intervention | Key Output | Indicator (f) | Time Frame and Output Target |  |  |  |  | Actors |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention 1.1 (d) Enhance Compliance to anti-corruption and accountability rules and regulations | Output 1.1.1: Enhanced coverage, quality and follow up of audits | Output Indicator 1 Percentage of Audited entities with an unqualified (clean) audit opinion | 100% | 100% | 100% | 100% | 100% | Internal Audit unit |

Programme 10: Legislature, Oversight and Representation

Legislature, Oversight and Representation, Effective legislation, oversight, and representation promotes and protects good governance through establishing the necessary checks and balances, ensuring alignment with the development aspirations. Effective legislation provides the legal framework which provides a conducive environment for economic, social, and political activities. Oversight ensures that laws and policies are effectively implemented and public resources are used efficiently and transparently.

##### Table 3.11: Programme Results and Targets for Legislature, Oversight and Representation

| Programme (a): | Outcome (a) | Indicator (c) | FY2023/24(BL) |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  | Data Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective 1: To increase effectiveness and efficiency in legislative processes | Outcome 1.1: Improved legal framework for supporting National development | Percentage of laws enacted against bills presented | 100 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | Council minutes |  |
|  | Intermediate Outcome (b) | Indicator (c) | FY2023/24(BL) |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  | Data Source |  |
|  | Intermediate Outcome 1.1: Enhanced scrutiny and quality of legislation | Proportion of bills withdrawn against bills presented | 00 |  | 00 |  | 00 |  | 00 |  | 00 |  | 00 |  | Minutes |  |
|  |  | 2 Proportion of legislation challenged in court within six months | 00 |  | 00 |  | 00 |  | 00 |  | 00 |  | 00 |  | Minutes |  |
| Intervention | Key Output | Indicator (f) |  | Time Frame and Output Target |  |  |  |  |  |  |  |  |  |
|  |  |  |  | FY2025/26 |  | FY2026/27 |  | FY2027/28 |  | FY2028/29 |  | FY2029/30 |  |  |  |
| Strategic Intervention 4: Conduct legislative reviews and updates | : Legislative reviews and updates conducted | Number of legislations updated |  | 50 |  | 20 |  | 20 |  | 20 |  | 20 |  |  | Council |
|  |  | Proportion of laws aligned to international treaties |  | 50 |  | 20 |  | 20 |  | 20 |  | 20 |  |  | council |
|  |  | Number of post legislative study reports produced |  | 50 |  | 20 |  | 20 |  | 20 |  | 20 |  |  | Council |
|  |  | Proportion of legal advisories adopted by council. |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  |  | CAO |

Programme 11: Digital Transformation

| Programme Objectives | Outcomes (a) | Outcome Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 2: Improve efficiency in Business processes and public service delivery | Outcome 2.1: Improved efficiency in delivery of government services. | Turnaround time (Working days) | 5 | 4 | 3 | 2 | 1 | 1 | LG |
|  | Intermediate Outcome (b) | Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 2.2.2: Increased uptake of e-services | Percentage of LGs and LLGs adopting e-services | 5% | 10% | 15% | 20% | 25% | 30% | IT Office |
|  |  | Proportional of the population accessing e-services through the citizen portal | 0% | 10% | 15% | 20% | 25% | 30% | System reports |
|  | Intermediate Outcome 3.3.3: Improved digital literacy | Proportion of population that is digitally skilled | 10% | 15% | 20% | 25% | 30% | 35% | IT Office |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Intervention: Implement specialized ICT and basic digital skills training programmes | Prioritized Output: Increased ICT proffesional skillsets | Number of Specialised group participants trained in digital literacy | 0 | 5 | 10 | 15 | 20 | 25 | IT Office |
|  |  | Number of Teachers Retooled in ICT- research enabled education. | 0 | 20 | 40 | 60 | 80 | 100 | IT Office |
|  | Prioritized Output: Increased citizenry with basic digital skills | Number of Specialised group participants trained in digital literacy | 500 | 700 | 1000 | 1200 | 1400 | 1500 | UCC Administrative reports |

Programme 12: Public Sector Transformation

| Programme Objectives | Outcomes (a) | Outcome Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Strengthen accountability for results across government | Outcome 1.1: Increased transparency and public trust in provision of public services | Percentage of population knowledgeable about public services | 50.00% | 60% | 70% | 80% | 90% | 100% | ADMIN |
|  | Intermediate Outcome (b) | Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome: Improved performance and results in Government Institutions | Percentage of Government Institutions meeting their established performance targets | 20.00% | 30% | 40% | 50% | 60% | 85% | OPM LGPA REPORT |
|  | Intermediate Outcome 2: Improved performance and accountability at institutional and individual level | Percentage of institutions achieving their performance targets | 60% | 70% | 70% | 80% | 80% | 90% | LGPA Report |
|  |  | % of individuals achieving at least 80% of their performance targets | 85% | 90% | 90% | 90% | 90% | 90% | Staff appraisal reports |
|  |  | Absenteeism rate in the Public Service | 39% | 5% | 25% | 15% | 10% | 5% | Attendance book |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 1.2: Strengthen efficiency of D/CSCs | Strategic Output 1.2.1: D/CSCs fully constituted and functional | Number of D/CSCs fully constituted | 1 | 1 | 1 | 1 | 1 | 1 | PSC Performance Reports, MoLG Performance Reports |
|  | Strategic Output 1.2.2: Transparency and accountability mechanisms for DSC operations established | Number of D/CSCs on which Performance Audits conducted | 1 | 1 | 1 | 1 | 1 | 1 | PSC Performance Reports |
|  | Strategic Output 1.2.3: Disciplinary cases timely concluded with complete submissions | Number of disciplinary cases concluded | 0 | 2 | 4 | 6 | 15 | 30 | REWARDS AND SANCTIONS REPORTS |
| Strategic Intervention 1.3: Strengthen public sector performance management initiatives | Strategic Output 1.3.1: LGs, LLGs and Institutions supported to develop and implement the Balanced Score Card | No. of LGs, LLGs and Institutions supported to develop and Implement the BSC | 1 | 20 | 30 | 40 | 50 | 60 | Appraisal reports |
|  | Strategic Output 1.3.2: LLGs and Institutions supported to cascade and implement the Balanced Score Card | No. of LLGs and Institutions supported to develop and Implement the BSC | 1 | 5 | 10 | 15 | 20 | 30 | Appraisal reports |
|  | Strategic Output 1.3.3: Attendance to duty in LGs, LLGs and Institutions monitored | No. of LGs, LLGs and Institutions monitored on attendance to duty | 107 | 60 | 70 | 80 | 90 | 100 | Attendance book |
| Strategic Intervention 1.4: Strengthen implementation of service delivery standards and feedback mechanisms | Strategic Output 1.4.3: LGs, LLGs and Institutions supported to develop Client Charters aligned to NDP IV with clear feedback mechanism | No. of LGs, LLGs and Institutions monitored and supported to develop Client Charters aligned to NDP IV | 0 | 20 | 30 | 40 | 50 | 60 | Client Charter |
|  |  | No. of LGs, LLGs and Institutions with valid client charters | 0 | 20 | 30 | 40 | 50 | 60 | Client Charter |
| Objective 3: Strengthen human resource management for improved service delivery | Outcome 3: Improved performance of civil servants in performance of their duties | Perception of Public to on performance of Civil Servants | 47% | 50% | 55% | 60% | 65% | 70% | UBOS , LGPA |
|  | Intermediate Outcome (b) | Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 3.1:Improved staffing in LGs and LLGs | Staffing levels in MDAs and LGs | 55% | 60% | 65% | 70% | 75% | 80% | State of HR Report |
|  | Intermediate Outcome 4.2.1:Improved functionality and coordination of local economic development | % of LGs with Functional LEDICs | 0% | 20% | 40% | 60% | 80% | 100% | Quarterly Local Government Reports |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 3.1: Strengthen recruitment in MDAs and LGs | Strategic Output 3.1.1: Guidance on Recruitment and Selection Procedures provided | Number of DSCs in which appointed members inducted | 1 | 1 | 1 | 1 | 1 | 1 | PSC Performance Reports |
|  |  | Number of DSCs appointed members inducted | 2 | 0 | 2 | 0 | 2 | 0 | Induction reports |
|  |  | Number of DSCs Secretaries inducted | 1 | 1 | 1 | 1 | 1 | 1 | Induction reports |
|  |  | Number of DSCs Guided on Recruitment and Selection Procedures | 1 | 1 | 1 | 1 | 1 | 1 | PSC Performance Reports |
|  | Strategic Output 3.2.1: Capacity of public servants enhanced | No. of Public Officers Trained in core and tailor made courses | 2577 | 2500 | 2,700 | 3,000 | 3,500 | 3,700 | MoPS Performance Reports |
|  | Strategic Output 3.2.1: Capacity of public servants enhanced | No. of public officers trained under the National Service Scheme | 0 | 2030 | 2,030 | 2,030 | 2,030 | 2,030 | MoPS Performance Reports |
| Strategic Intervention 3.3: Strengthen human resource management in government | Strategic Output 3.3.3: Public Service Negotiating, Consultative and Disputes Settlement Machinery Operationalized | No. of LGs &LLGs supported on implementation of Consultative Committees | 68 | 50 | 50 | 50 | 50 | 50 | MoPS Performance Reports |
|  |  | Percentage of employee grievances disposed off by the Rewards and sunctions committee | 100% | 100% | 100% | 100% | 100% | 100% | Rewards And Sanctions Reports |
|  | Strategic Output 3.3.4: HR Policies implemented in MDAs and LGs | No. of LGs and LLGs supported to implement HR policies | 1 | 2 | 8 | 10 | 12 | 14 | MoPS Performance Reports |
|  | Strategic Output 3.4.3: Implementation of the Reports of the Auditor General on active and pension payroll undertaken | Percentage of recommendations of the Reports of the Auditor General on active and pension payroll implemented | 0 | 50% | 60% | 70% | 80% | 100% | MoPS Performance Reports |
| Strategic Intervention 3.5: Reform the pension schemes and systems | Strategic Output 3.5.2: Technical support on decentralised management of pension and gratuity undertaken | No of LGs and LLGs supported on decentralised management of pension and gratuity | 1 | 2 | 4 | 6 | 10 | 12 | Human resource reports |
|  | Strategic Output 4.1.4: Local revenue allocated to community development Community | % of Local revenue invested in community Services | 20% | 25% | 30% | 35% | 40% | 45% | LGFC Performance Reports |
| Strategic Intervention 4.3: Enhance local economic development | Strategic Output 4.2.1: Contribution of Local stakeholders to LED improved | No. of LGs trained to operationalize LEDICS | 5% | 10% | 15% | 20% | 25% | 30% | LGPR |
|  | Strategic Output 4.2.1: Contribution of Local stakeholders to LED improved | No. of LLGs trained to operationalize LEDICS | 5 | 7 | 9 | 11 | 15 | 17 | LGPR |
|  | Output 4.2.2: Parish Development Model strengthened | No. of Parish Development Committees and SACCO Executive Leaders trained on PDM | 525 | 525 | 525 | 525 | 525 | 525 | PDM Annual Report |
|  | Output 4.3.2: Capacity of private local firms built to participate in Districtpublic procurements | %ge increase in the number of local firms participating in the District public procurements | 0 | 5% | 10% | 15% | 20% | 25% | District Performance Reports |
|  | Output 4.3.2: Capacity of private local firms built to participate in city public procurements | Number of capacity buiding engagments for local firms held | 0 | 5 | 10 | 15 | 20 | 25 | District Performance Reports |
|  | Output 4.3.2: Capacity of private local firms built to participate in city public procurements | % value of of District Public procurements awarded to Local firms | 0% | 2% | 5% | 10% | 15% | 20% | District Performance Reports |
| Objective 5: Re- Engineer the Public Service Delivery Processes/ System | Outcome 5: Increased access to public services | Percentage of the population satisfied with the quality of public services by sector |  |  |  |  |  |  |  |
|  |  | Health | 73% | 80% | 85% | 90% | 95% | 95% | NSDS |
|  |  | Extension services | 78% | 80% | 85% | 90% | 95% | 95% | NSDS |
|  |  | Administrative and Legal Services | 77% | 80% | 85% | 90% | 95% | 95% | NSDS |
|  | Intermediate Outcome (b) | Indicator (c) | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | Data Source |
|  | Intermediate Outcome 5.1: Increased integration of service delivery | Proportion of LGss integrated with data sharing and integration platform | 20% | 25% | 30% | 35% | 64% | 73 % | MoICT&NG Quarterly reports |
| Interventions | Key Outputs ( e) | Output Indicator (f) | Time Frame and Output Target |  |  |  |  |  | Actors |
|  |  |  | FY2024/25(BL) | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 |  |
| Strategic Intervention 5.1: Enforce adoption and implementation of e-government services | Strategic Output 5.1.1: Uptake of ICT in provision and management of government services enhanced. | No. of entities implementing e-government systems | 0 | 1 | 4 | 6 | 10 | 14 | ICT-PR |
|  |  | No of new e-services introduced | 0 | 1 | 1 | 1 | 1 | 1 | ICT -PR |
|  |  | No. of citizens accessing government services online | 500 | 1000 | 2000 | 3000 | 4000 | 5000 | ICT-PR |
| Strategic Intervention 5.3: Strengthen Government Institutions in Records, Archives and Information Management | Strategic Output 5.3.1: Records Management Systems set up and streamlined in MDAs and LGs | Number of LGs and LLGs supported to set up and streamline Records management systems. | 0 | 0 | 1 | 4 | 6 | 10 | District Performance Reports |
|  | Strategic Output 5.3.2: Electronic Document and Records Management System (EDRMS) rolled out to LGs and LLGs | Number of MDAs and LGs with fully operational Electronic Document and Records Management System | 0 | 1 | 1 | 1 | 1 | 1 | District Performance Reports |
|  | Strategic Output 5.3.6: Valuable archival records acquired from MDAs/LGs and preserved at the NRCA | Number of MDAs and LGs Contributing Archival Records to the National Records Centre and Archives | 36 | 10 | 10 | 10 | 10 | 10 | District Performance Reports |
|  | Strategic Output 6.1.2: Staff salaries and related costs paid | Percentage of staff whose salaries have been processed by 28th of every month | 100% | 100% | 100% | 100% | 100% | 100% |  |
|  | Strategic Output 6.1.6: Cross cutting issues mainstreamed | % compliance with gender and equity for District | 60% | 65% | 67% | 69% | 71% | 73% | District Performance Reports |
|  |  | % compliance with gender and equity for LLG | 67% | 69% | 71% | 0% | 75% | 77% | District Performance Reports |
|  |  | % compliance with gender and equity for KCCA | 73% | 75% | 77% | 79% | 81% | 83% | District Performance Reports |
|  |  | % of HIV/AIDS interventions undertaken per vote |  | 100% | 100% | 100% | 100% | 100% | District Performance Reports |
|  | Strategic Output 6.1.8: Human Resources managed | Percentage of staff supported to undertake their roles and responsibilities by vote | 20% | 30% | 40% | 50% | 60% | 70% | District Performance Reports |
|  | Strategic Output 6.1.21: M&E undertaken | No. of Monitoring and evaluative reports prepared | 2 | 4 | 4 | 4 | 4 | 4 | District Performance Reports |
|  | Strategic Output 6.1.22: Statistics services coordinated | Annual Statistical Report in place by Vote | 1 | 1 | 1 | 1 | 1 | 1 | District Performance Reports |
|  | Strategic Output 6.1.22: Statistics services coordinated | Strategic Plan for Statistics in place by vote |  | 1 | 1 | 1 | 1 | 1 | District Performance Reports |
|  | Strategic Output 6.1.22: Statistics services coordinated | Midterm review report for strtaegic plan for statistics in place by vote | 0 | 0 | 0 | 1 | 0 | 0 | District Performance Reports |
|  | Strategic Output 6.1.25: Institutions retooled | %ge of required equipment installed by vote | 5% | 10% | 25% | 50% | 75% | 100% | District Performance Reports |
|  | Strategic Output 6.1.23: Government institutional infrastructure constructed and/or rehabilitated | Number of Government Institutional Infrastructure Projects with Documented Progress Reports | 0 | 2 | 3 | 4 | 4 | 4 | District Performance Reports |

CHAPTER FOUR

FINANCING FRAMEWORK AND RESOURCE MOBILISATION STRATEGY

This Chapter clearly articulates how the LG Development plan will be financed including an overview of development resources and projections, resources mobilisation strategy that specifies; strategies for raising required resources and ensuring efficiency in resource use and also roles, responsibilities and conditions of development partners in financing LGDP including a specification of whether the funding will be budget or off-budget.

4.1 Financing framework

Table 19: Financing Framework

| Sources of Financing |  | Total Contribution (Millions UGX) |  |  |  |  | GRAND Contribn | (%) Share by source | Off Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | FY | FY | FY 2027/28 | FY 2028/29 | FY 2029/30 |  |  |  |
|  |  | 2025/26 | 2026/27 |  |  |  |  |  |  |
| 1. Central Government Transfers (Total Contribution) |  | 30,586.18 | 32,115.49 | 33,721.26 | 35,407.33 | 37,177.69 | 169,007.95 | 96.7 | 0 |
| 2. Locally Raised Revenue |  | 835 | 876.75 | 920.59 | 966.62 | 1,014.95 | 4,613.91 | 2.7 | 0 |
| 3. Development Partners (Donors) |  | 197.51 | 207.39 | 217.75 | 228.64 | 240.07 | 1,091.36 | 0.6 | 0 |
| 4. Other sources of financing | Private | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | CSO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Academia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Total | 31,618.69 | 33,199.63 | 34,859.60 | 36,602.59 | 38,432.71 | 174,713.22 | 100 | 0 |

The district has projected that at least UGX 174.71322 billion shillings would be required to implement the 5-year plan from the various sources. Out of this, approximately 96.7% will be from Central Government Transfers, 2.7 % will be from Locally Raised Revenues and 0.6 % will be from donor funding and 0% from other sources of financing.

4.2	Costs of the Plan Period (2025/26-2029/30)

Table 20: Summary Costs of the Interventions

| Strategic Objectives and Interventions | Total Cost (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 1: Sustainably increase production, productivity and value addition in agriculture, Minerals, oil & gas, Tourism, ICT & financial services |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 1.1 Increase access to and use of water for agricultural production | 200 | 50 | 50 | 50 | 50 | 50 |
| 1.2 Strengthen systems for management of pests, vectors and diseases | 175 | 35 | 35 | 35 | 35 | 35 |
| 1.3 Strengthen agricultural research and technology development | 225 | 75 | 75 | 75 | 75 | 75 |
| 1.4 Strengthen the agricultural extension system | 125 | 25 | 25 | 25 | 25 | 25 |
| 1.5 Strengthen the agricultural inputs markets and distribution systems to adhere to quality standards and grades | 75 | 15 | 15 | 15 | 15 | 15 |
| 1.6 Promote sustainable land and environment management practices in line with the agroecological needs | 50 | 10 | 10 | 10 | 10 | 10 |
| 1.7 Introduce and upscale Agro-forestry for mitigation and climate resilience | 75 | 15 | 15 | 15 | 15 | 15 |
| 1.8 Increase the number of farmers with titled land to ensure land tenure security with special attention to the youth, women, PWDS and other vulnerable groups | 100 | 20 | 20 | 20 | 20 | 20 |
| 1.9 Establish post-harvest handling, storage and processing infrastructure including silos, dryers, warehouses, and cold rooms of various scale and capacities at subcounty, district and zonal levels | 500 | 100 | 100 | 100 | 100 | 100 |
| 1.10 Improve agricultural market infrastructure in rural and urban areas | 300 | 60 | 60 | 60 | 60 | 60 |
| 1.11 Develop new tourist sites | 50 | 10 | 10 | 10 | 10 | 10 |
| 1.12 Improve coordination, planning, regulation and monitoring of water resources at catchment level |  |  |  |  |  |  |
| 1.13 Develop and implement a Land Valuation Management Information System |  |  |  |  |  |  |
| Strategic Objective 2: Enhance human capital development along the entire life cycle |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 2.1 Reduce the burden of communicable diseases with focus on high burden diseases, epidemic prone diseases and malnutrition across all age groups emphasizing Primary Health Care Approach | 375 | 75 | 75 | 75 | 75 | 75 |
| 2.2 Improve the functionality of the health system to deliver quality and affordable preventive, promotive, curative and palliative health care services | 600 | 120 | 120 | 120 | 120 | 120 |
| 2.3 Increase access to inclusive safe water, sanitation and hygiene (WASH) with emphasis on increasing coverage of improved toilet facilities and handwashing practices | 250 | 50 | 50 | 50 | 50 | 50 |
| 2.4 Establish and operationalize mechanisms for effective collaboration and partnership for UHC at all levels | 75 | 15 | 15 | 15 | 15 | 15 |
| 2.5 Improve Occupational Safety and Health (OSH) management | 30 | 6 | 6 | 6 | 6 | 6 |
| 2.6 Strengthen population planning and development including civil registration, vital statistics registration and population data bank at National and Sub national levels |  |  |  |  |  |  |
| 2.7 Promote optimal Maternal, Infant, Young Child and Adolescent Nutrition practices | 300 | 60 | 60 | 60 | 60 | 60 |
| 2.8 Increase investment in child and maternal health services at all levels | 200 | 40 | 40 | 40 | 40 | 40 |
| 2.9 Improve adolescent and youth health |  |  |  |  |  |  |
| 2.10 Roll out Early Grade Reading (EGR) and Early Grade Maths (EGM) in all primary schools to enhance proficiency in literacy and numeracy |  |  |  |  |  |  |
| 2.11 Implement an integrated ICT school level inspection and supervision | 40 | 8 | 8 | 8 | 8 | 8 |
| 2.12 Implement the 15 Household model for social economic empowerment | 60 | 12 | 12 | 12 | 12 | 12 |
| 2.13 Review and implement a Comprehensive Community Mobilization Strategy | 15 | 3 | 3 | 3 | 3 | 3 |
| 2.14 Conduct awareness campaigns and enforce laws enacted against negative and/ or harmful religious, traditional/ cultural practices and beliefs | 20 | 4 | 4 | 4 | 4 | 4 |
| 2.15 Popularize the national vision, interest and common good for the citizenry | 30 | 6 | 6 | 6 | 6 | 6 |
| 2.16 6 Scale up Gender Based Violence (GBV) interventions at all levels | 25 | 5 | 5 | 5 | 5 | 5 |
| Strategic Objective 3: Support private sector to drive growth and create jobs |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 3.1 Improve management capacities of local enterprises through massive provision of business development services geared towards improving firm capabilities | 10 | 2 | 2 | 2 | 2 | 2 |
| Strategic Objective 4: Build and maintain strategic infrastructure in transport, housing, energy, water, industry and ICT |  |  |  |  |  |  |
| Interventions |  |  |  |  |  |  |
| 4.1 Rehabilitate and maintain transport infrastructure | 5,000 | 1000 | 1000 | 1000 | 1000 | 1000 |
| 4.2 Adopt cost-efficient technologies to reduce maintenance backlog | 1,600 | 400 | 400 | 400 | 400 | 400 |
| 4.3 Establish a construction equipment hiring pool | 500 | 100 | 100 | 100 | 100 | 100 |
| 4.4Monitor and evaluate transport infrastructure and services policy, legal and regulatory framework |  |  |  |  |  |  |
| 4.5 Build local technical capacity in renewable energy solutions | 30 | 6 | 6 | 6 | 6 | 6 |
| 4.6 Scale up the physical planning and urban management information system |  |  |  |  |  |  |
| 4.7 Enhance economic opportunities in cities and urban areas |  |  |  |  |  |  |
| 4.8 Improve the provision of quality social services to address the peculiar issues of urban settlements |  |  |  |  |  |  |
| 4.9 Implement the national networking system |  |  |  |  |  |  |
| Strategic objective 5: strengthening good governance, security and the role of the state in development. |  |  |  |  |  |  |
| 5.1 Strengthening public sector performance management | 150 | 30 | 30 | 30 | 30 | 30 |
| 5.2 Develop and enforce service and service delivery standards | 25 | 5 | 5 | 5 | 5 | 5 |
| 5.3 Design and implement a rewards and sanctions system | 15 | 3 | 3 | 3 | 3 | 3 |
| 5.4 Develop and enforce service and service delivery standards | 10 | 2 | 2 | 2 | 2 | 2 |
| 5.5 Deepening the reduction of informality and streamlining taxation at Local Government level |  |  |  |  |  |  |
| 5.6 Strengthen capacity for development planning, particularly at the MDAs and LGs | 50 | 10 | 10 | 10 | 10 | 10 |
| 5.7 Strengthening statistical performance | 60 | 12 | 12 | 12 | 12 | 12 |
| 5.8 Strengthen implementation, monitoring and reporting of Local Governments | 150 | 30 | 30 | 30 | 30 | 30 |
| 5.9 Monitoring of Government Programs for effective service delivery |  |  |  |  |  |  |
| Strengthen the prevention, detection and elimination of corruption | 50 | 10 | 10 | 10 | 10 | 10 |
| Improve legislative processes in LG Councils to ensure enhanced scrutiny and quality of legislation. | 400 | 80 | 80 | 80 | 80 | 80 |
| Building capacity of councillors, Boards and commissions | 80 | 30 | 50 |  |  |  |
| Total | 12025 | 2539 | 2559 | 2509 | 2509 | 2509 |

Table 21: Cost of Projects

| Total Cost for the Plan Period (UGX in Million) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Projects | Total (Millions) | FY2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 |
| 1. Promotion of agroforestry in the district | 150 | 30 | 30 | 30 | 30 | 30 |
| 2. | 300 | 100 | 100 | 100 |  |  |
| 3. Construction of laboratory at district headquarters | 200 | 100 | 100 |  |  |  |
| 4. Development and promotion of tourism in the district | 360 | 60 | 120 | 60 | 60 | 60 |
| 5. Procurement of RTK machine and accessories | 30 | 30 |  |  |  |  |
| 5. Health infrastructure and service delivery improvement project | 2,500 | 600 | 600 | 600 | 600 | 600 |
| 6. School infrastructures improvement Project | 925 | 185 | 185 | 185 | 185 | 185 |
| 7. Construction, rehabilitation and management of water supply and sanitation facilities | 3,875 | 755 | 765 | 775 | 785 | 795 |
| 9. Expansion of ICT service proliferation and uptake | 320 | 80 | 60 | 60 | 60 | 60 |
| 10. Procurement of council furniture and equipment | 50 | 10 | 10 | 10 | 10 | 10 |
| TOTAL | 8,860 | 2,050 | 2,020 | 1,820 | 1,730 | 1,730 |

4.3 Resource Mobilization Strategy

The 5-year District Development Plan (DDP IV) for Kitagwenda District will be financed through multiple revenue sources available to the district. This will be implemented via the preparation and execution of annual budget estimates and work plans. These annual revenue and expenditure projections will be prepared in a participatory manner involving consultations with stakeholders across the district. Revenues will be generated from realistic and verifiable sources to meet projected expenditures.

Objectives for Resource Mobilisation

- To mobilize sufficient revenues to finance planned interventions under the DDP IV.

- To identify, document, and efficiently collect budgeted revenues.

- To strengthen inspection, supervision, and monitoring of revenue mobilization activities.

- To promote awareness and tax education among taxpayers and the general public.

- To strengthen Kitagwenda District’s relationships with donors and promote Public-Private Partnerships (PPPs).

Strategies for Resource Mobilization

Kitagwenda District will mobilize resources from three main sources:

- Locally raised revenues

- Central Government transfers

- Development partner (donor) support

These sources will be strategically pursued to ensure effective and efficient mobilization and utilization.

Locally Raised Revenues

Locally generated revenue remains a crucial component of financing the district’s development priorities. In Kitagwenda, the following strategies will be used to enhance revenue collection:

- Formation and strengthening of revenue collection committees at sub-county and parish levels, including market and boda-boda associations in Kabujogera Town Council, Ntara Town Council, and Mahyoro Sub-County.

- Training Local Revenue Enhancement Committee members, parish chiefs, and town agents on revenue roles.

- Enumeration and assessment of eligible taxpayers including market vendors, motorcycle operators, small-scale traders, and fisheries operators along Lake George (Kanara, Mahyoro).

- Documentation of all potential sources including markets (e.g., Kabujogera Market), slaughter slabs, fish landing sites, trading licenses, and resource use fees (charcoal, timber, and sand).

- Identification and tapping of new revenue sources such as:

  - Hire of district tents, chairs, and public address systems for community functions.

  - User fees for registration of community-based organizations (CBOs).

  - Collection of advertisement and branding fees from businesses and mobile money kiosks.

  - Rental of public halls (e.g., Ntara Community Hall) for events and training.

Central Government Grants

To optimize access to central government funding, Kitagwenda District will:

- Adhere strictly to the Public Finance Management Act, 2015 (Revised 2016) through timely submission of quarterly, nine-month, and annual financial statements.

- Strengthen financial planning and management systems to maximize absorption capacity and avoid returning funds to the Consolidated Fund.

- Build capacity of planning and finance staff to ensure accurate forecasting, budgeting, and reporting as per MoFPED requirements.

Donor Funding

To enhance trust and sustain donor support, Kitagwenda District will:

- Comply with donor MOUs and reporting requirements.

- Ensure transparent and timely accounting for donor funds.

- Provide regular updates through monitoring and evaluation reports.

- Engage development partners such as UNICEF, World Vision, Baylor Uganda, and WWF to support health, education, water, sanitation, environmental conservation (wetlands and Lake George), and youth empowerment.

Other Strategic Actions

- Formulation of a Local Revenue Enhancement Plan: To guide the district in raising revenues from both traditional and non-traditional sources.

- Project proposal development: Targeting donor funding for initiatives such as:

  - Renewable energy (e.g., solar lighting in health centres like Kabujogera HCIV and schools in Nyabbani).

  - Value addition in agriculture (coffee hulling in Ntara, banana processing in Kicheche, and fisheries value chains along Lake George).

- Agriculture modernization: Supporting production and productivity in coffee, bananas, dairy, and fisheries to generate taxable economic activity and employment.

- Road infrastructure improvement: Prioritizing feeder road maintenance (e.g., Kabujogera–Ntara–Kamwenge road, Mahyoro–Kanara road) to ease market access.

- Revenue inspection and supervision: Regular and surprise inspections at collection points, empowering parish chiefs and market masters to enforce accountability.

- Strengthening revenue management systems:

  - Use of official receipts and mandatory notices.

  - Organization of quarterly community baraza forums for accountability.

- Community mobilization: Using radio talk shows via Voice of Tooro (VOT FM), Uganda Radio West, and other local channels to explain DDP IV priorities, BFPs, and annual work plans.

- Compliance with laws and regulations: Ensuring integrity and credibility to attract more donor funding.

- Community Ambulance Financing Scheme: Exploring expansion of a community-based ambulance scheme piloted at Kabujogera HCIV to improve emergency referrals in remote sub-counties like Mahyoro and Kanara.

- Partner coordination: Ensuring alignment of off-budget interventions (e.g., those by ACODE, Baylor, and CBOs) with the five-year district priorities to avoid duplication and maximize impact.

CHAPTER FIVE: INSTITUTIONAL ARRANGEMENTS FOR IMPLEMENTING THE PLAN

This chapter highlights the Implementation and Institutional Arrangements, Role of Key Stakeholders, Coordination and Partnerships Framework, Prerequisites for Successful Implementation, and Conditions for Successful Implementation of the Kitagwenda District Development Plan IV.

5.1 Implementation Arrangements

Overall, LGDP implementation strategy will mainly depend on financing the planned interventions, timely release of funds, local revenue performance and adequate staffing.

The LGDP IV has integrated all LLG plans and programme plans, emphasized annual and quarterly budget performance reviews, supervision, mentoring, monitoring and evaluation. The planned and implemented activities at Lower Local Government level shall contribute to the realization of the LGDP IV objectives and programme priorities.

The implementation of the DDP IV in Kitagwenda District will follow the existing decentralization framework guided by national planning and budgeting policies. The plan will be executed through collaborative arrangements involving the District Council, Technical Planning Committee, Lower Local Governments (LLGs), Civil Society, Private Sector, and Development Partners.

However, the district has been facing challenges in delivering services mainly related to financing and revenue mobilization, human resources capacity gaps; urban development and physical planning; and governance.

Policy decisions for implementation; in the execution of the Local Government Development Plan IV, the district leadership will ensure all government structures from the Local Council one to Local Council five play their administrative function as spelt out the Local Government Act CAP 138 that involves planning, budgeting, implementation, monitoring and enforcement of all government policies.

Implementation of works that involves delivery of goods and services will be carried out through the exiting mandated departments and units i.e. utilization of the Contracts Committee for procurement of service providers, the District Service commission for the recruitment of the human resources.

Each financial year through the budget preparation process the District Council will avail funding for the implementation of the Local Government Development Plan IV.

Community and public safety; in the implementation of the LGDP IV, safety of the community members and beneficiaries will be at the core during project implementation. Before execution of the planned activities, the implementation team will review the project feasibility studies and risk assessments to identify potential threats. Stakeholder engagement will be conducted with local authorities at the Lower Local Governments and the community to identify any environmental and social issues. All projects shall be screened for environment and social acceptability. Those having negative issues will have mitigation measures identified. Monitoring and site inspections shall be conducted on a regular basis to ensure safety measures are being followed and to identify new hazards.

5.2 Institutional arrangements

The principal actor in the implementation and coordination of the District Development Plan shall be the District Council operating through its line departments. Each Head of Department/Sector shall lead the implementation of programmes and projects under their jurisdiction. Coordination at community, LLG, district, and national levels is essential to achieving the planned outcomes.

The District Development Plan IV will be implemented through the existing decentralized governance structures, ensuring effective coordination across political, technical, and community institutions.

Table 5.1: Specific Roles for the Various Organs/Committees and Institutions

| S/No. | LG Organ / Committee / Other Institution | Roles and Responsibilities |
| --- | --- | --- |
| 1 | District Council | • Approves district budgets and annual workplans |
|  |  | • Receives funds from MDAs and Development Partners |
|  |  | • Mobilizes local and external resources |
|  |  | • Enacts ordinances |
|  |  | • Oversees Monitoring and Evaluation of district programmes |
| 2 | District Executive Committee (DEC) | • Oversees implementation of government and council policies |
|  |  | • Coordinates NGO activities |
|  |  | • Monitors government programmes and recommends action |
|  |  | • Evaluates council performance against plans |
|  |  | • Supervises departments and regulates policy execution |
|  |  | • Participates in policy formulation and coordination with LLGs |
| 3 | District Council Standing Committees | • Scrutinize and review budgets and ordinances |
|  |  | • Monitor sectoral performance (e.g., agriculture, fisheries, tourism) |
|  |  | • Provide sector-based policy recommendations to council |
| 4 | District Technical Planning Committee (DTPC) | • Formulates workplans and budgets |
|  |  | • Reviews and appraises project proposals |
|  |  | • Coordinates submissions to ministries |
|  |  | • Oversees implementation progress of DDP |
|  |  | • Compiles and reviews LGBFP and Local Development Plans |
| 5 | Budget Desk/ Finance Committee | • Manages budget call circulars for district and LLGs |
|  |  | • Reviews departmental submissions |
|  |  | • Compiles LGBFP and Draft Development Plans |
| 6 | District Departments/Sectors | • Draft and submit departmental budgets and workplans |
|  |  | • Conduct technical supervision of projects |
|  |  | • Monitor and evaluate sector interventions |
|  |  | • Build technical capacity of staff and stakeholders |
|  |  | • Generate sector-specific data and priorities |
| 7 | District CAO’s Office | • Submits LGBFP and Performance Contracts to MoFPED |
|  |  | • Presents budget to District Council |
|  |  | • Organizes budget conferences |
|  |  | • Coordinates planning and reporting processes |
| 8 | Lower Local Governments (LLGs) | • Approve local priorities and formulate sub-county/town council plans |
|  |  | • Submit approved LLG plans to the District |
|  |  | • Enact by-laws (e.g., regulating charcoal burning) |
|  |  | • Monitor service delivery and community projects |
| 9 | Boards and Commissions: DSC, PAC, DLB, Contracts Committee | • Recruit, promote and discipline district staff |
|  |  | • Manage procurement and contract award processes |
|  |  | • Handle and allocate public land |
|  |  | • Review audit reports and recommend action |

5.2.1 Role of Key Stakeholders

The local government development planning process is a participatory process requiring several stakeholders, institutions, development partners to play their play part in the Development Plan formulation that will respond to the aspirations and needs of the community and the district

The implementation of the DDP IV will depend on effective collaboration among central government entities, development partners, private sector actors, civil society, and communities.

  - Coordination and Partnership Frameworks

A multi-level coordination framework will be operationalized through structured platforms that bring together stakeholders at district, sub-county, and community levels.

Table 5.2: Coordination Arrangements for Integrated Planning and Budgeting with Stakeholders

| Institutions | Roles & Responsibilities in the Partnership Arrangement |
| --- | --- |
| Central Government MDAs (e.g., MoFPED, MoLG, MoH, MoES, NPA, MoGLSD, OPM, NEMA, MoWT, DWD) | • Approve district plans and budgets • Mobilize external funds and issue policy guidance • Provide financial transfers • Offer technical support and M&E • Set standards and coordinate national priorities |
| Development Partners (e.g., UNICEF, Baylor Uganda, World Vision, World Bank) | • Provide financial and technical support • Monitor and evaluate funded projects • Align support with district and national priorities • Build local capacity and support innovation |
| Kitagwenda District Local Government (Council, CAO, DEC, DTPC) | • Approves and implements DDP IV • Coordinates departments, LLGs, and partners • Monitors project implementation • Mobilizes and manages resources • Procures service providers and ensures accountability |
| Line Departments (e.g., DEO, DHO, DE, DCDO, D/Planner) | • Develop and implement sector workplans • Supervise projects • Build capacity for service delivery • Submit reports and technical inputs for planning |
| Sub-County and Town Council Local Governments | • Approve and submit local development plans • Enact by-laws and mobilize communities • Monitor project implementation and service delivery. |
|  | • Coordinate with parish and village leadership • Implement contracted works/supplies • Support community mobilization • Contribute to revenue and employment • Maintain partnerships through CSR activities |
| Private Sector Organizations |  |
| Local Council I & II | • Mobilize community contributions • Monitor project sites and contractor behavior • Ensure land access and project security • Facilitate local accountability |
| Facility Management Committees (HUMCs, SMCs, WSSCs, PMCs) | • Oversee operations and maintenance of community facilities • Represent community interests during planning and monitoring • Collect user fees where applicable (e.g., water user committees) |
| Civil Society Organizations | • Conduct community mobilization and advocacy • Build local capacity • Implement projects under MOUs with the district • Monitor services and champion community rights |
| User Communities | • Provide land, local materials, and labor • Operate and maintain community assets • Participate in planning and monitoring • Ensure sustainability and ownership of projects |

CHAPTER SIX: COMMUNICATION AND FEEDBACK STRATEGY

This chapter presents the Communication and Feedback Strategy for the District. It defines how communication and information exchange will support the implementation, monitoring, and evaluation of the District Development Plan IV (DDP IV) for FY2025/26–2029/30.

6.1 Communication Strategy

Communication will play a vital role in providing knowledge, changing people’s attitudes and norms for men and women, boys and girls. It will play an important role in initiating or accelerating the changes that are already underway as well as in reinforcing and supporting change that has occurred. Effective communication will also result in supportive policies, positive legislature and increased resource allocation.

From project identification to completion, stakeholders including local communities, development partners, political leaders, and civil society organizations will be engaged through clear, timely, and inclusive mechanisms. Progress will be shared regularly through council sittings, community engagements, and digital platforms; feedback will be solicited and integrated into planning and execution.

The District Council shall serve as the primary channel for communicating progress and plans. Regular reports will also be submitted to the Office of the Prime Minister (OPM), Ministry of Local Government (MoLG), Ministry of Finance, Planning and Economic Development (MoFPED), and other stakeholders, including donor agencies and NGOs operating in the district.

There will be a strong emphasis on dialogue, transparency, and community ownership, recognizing the crucial role of local voices in development.

Key Communication Strategies in Kitagwenda District

- Official Letters: The Chief Administrative Officer (CAO) communicates with Sub-County Chiefs and Town Clerks who, in turn, inform LC officials about Indicative Planning Figures (IPFs), project allocations, and progress.

- Local FM Radio (Rwenzori/Ankole corridor): Talk shows, jingles, and spot announcements on commonly accessed stations (e.g. Rukundo Radio, Voice of Kamwenge (VOK), Voice of Tooro (VOT FM), Uganda Radio West, and other area stations) to communicate government interventions and emerging issues.

- Community Engagement Forums: Barazas, community dialogues, and public accountability meetings conducted across the Lower Local Governments.

- District Newsletters: Bi-annual and annual newsletters summarizing progress and sharing success stories

- District Website and Social Media: Kitagwenda District website and social media pages updated quarterly with achievements, procurement notices, and announcements.

- Management Information Systems: Strengthening internal MIS to track project progress and support data-driven decision-making.

- Information, Education, and Communication (IEC) Materials: Posters, brochures, and infographics in local language and English, for use in health centers, schools, and sub-county offices.

- Press Briefings: Regular engagement with media outlets for transparency and promotion of key initiatives.

6.2. Target Institutions for effective communication and feedback

The development plan is responsible for guiding the implementation of the district development aspiration to realize a positive change in the community. Several players will be involved in the process. The different players have been heighted in table 6.1

Table 6.1: Levels, Target Institutions and Audience for Effective Communication and Feedback

| Institutions | Audiences |
| --- | --- |
| Central Government | Line Ministries (MoFPED, MoLG, OPM), Office of the Auditor General, Accountant General |
| Local Government | District departments (Education, Health, Works, Production, Natural Resources, Community Based Services, Planning, Internal Audit), Lower Local Governments, DTPC and STPCs |
| Council | LCV Chairperson’s Office, Standing Committees, Public Accounts Committee (PAC) |
| CSOs/NGOs | NGO Forum/Coordination platforms active in in the district, CBO networks |
| Mass Media | Local journalists, FM radio stations accessible in the district. |
| Cultural & Religious Institutions | Religious leaders (Imams, Priests, Reverends), clan elders, opinion leaders |
| Communities | General public, village leaders, School Management Committees, traders, youth & women groups |

Institutions’ interest and channel of communication.

Effective communication requires that messages are properly packed to suit the intended target, and the mode of transmission chosen should enable easy transfer of information from the send to the receiver. Table 6.2 shows the different target audience and channel of transmission that will be used.

Table 6.2: Analysis of Target Audience and Their Interests

| Audience | Common Interest | Key Message Concept | Channel |
| --- | --- | --- | --- |
| MoLG & NPA | Alignment with NDP IV and sector strategies | Kitagwenda DDP IV aligns with NDP IV and sector plans, promoting inclusive and sustainable development | Guidelines, circulars, dissemination workshops, supervision missions |
| MoFPED | Effective allocation, utilization, and accountability | Budget allocations support priority investments (education, health, feeder roads, water) and are transparently managed | Budget circulars, meetings, posters, letters, public barazas |
| Other Line Ministries | Adherence to sector norms and standards | Sector priorities (e.g., fisheries, agriculture, education, health) are implemented effectively in Kitagwenda | Sector guidelines, support supervision, MoUs, technical backstopping |
| Office of the LCV & Council | Improve quality of life via policies and oversight | State-of-District report reflects progress; enabling ordinances passed to implement DDP IV; leaders address public concerns | Public notices, radio, council meetings, community engagements |
| CAO’s Office and Departments | Coordinate official communication and progress updates | Departments disseminate implementation progress, handle emerging issues, and work with partners to engage communities | Barazas, IEC materials, press releases, radio talk shows |
| Mass Media | Timely and accurate district information | DDP IV implementation is on course; media is a development partner | Quarterly press briefings, newsletters, social media, district website |
| CSOs/NGOs | Enhance service delivery and accountability | NGOs complement government and ensure citizen participation and access to services | Quarterly coordination meetings, reports, partnership frameworks |
| General Public | Improved livelihoods and services | Kitagwenda is committed to quality service delivery; citizens should participate and provide feedback | Local radios, barazas, LC letters, posters, IEC materials, district social media |

Roles/Responsibilities of Stakeholders of LG in communication and provision of feedback to stakeholders.

All offices of leadership from the higher local government to the lower local government including management committees of different institutions will have responsibilities according to their mandates to communicate to the community. The persons responsible for communication will include both political leaders as well as technical officers.

Table 6.3: Roles/Responsibilities of Stakeholders of LG in communication and provision of feedback to stakeholders

| Institution | Roles and responsibilities. |
| --- | --- |
| Office of LCV chairperson | - Popularising and publicising government programmes and projects |
| CAO’s office | - Popularising and publicising government programmes and projects |
| Office of District Information Officer | - Publicizing government programmes and projects - Establishing channels for communication - Management of the district website - Link the departments to the media houses |
| Heads of Departments. | - Publicising government programmes and projects - Participating in feedback meetings and Barazas |
| School head teachers and health unit managers | - Publicising government programmes and projects |
| School Management Committee members, Health Unit Management Committee members | - Publicising government programmes and projects |
| Project Management Committees. | - Publicising government programmes and projects |
| Sub-county chiefs | - Publicising government programmes and projects - Establishment of notice boards at the sub county - Posting of information on sub county notice boards |

6.2 Communication Plan

Effective implementation of the DDP IV requires structured communication that informs, educates, and engages stakeholders. A structured communication plan will ensure timely and consistent dissemination of information to stakeholders throughout the DDP IV implementation period.

Table 6.4: Communication Plan

| Communication | Audience | Type / Communication Channel | Objectives | Content | Responsibility |
| --- | --- | --- | --- | --- | --- |
| LG Vision, Goals, and Strategic Objectives | Community members, political leaders, technical staff, development partners, local authorities | Radio talk shows (e.g. Rukundo FM, Iraka Radio, VOT FM, Radio West), community meetings, district website, social media | Disseminate the aspirations and strategic direction of the district. | Mission, Vision, Development Goals | CAO, District Planner (DP), IT Officer (ITO), LCV Chairperson |
| Priority Investment Projects | Community, LLG leaders, political leadership, civil society | Barazas, radio programs, social media, parish noticeboards | Inform and update stakeholders on implementation progress | Project sites, timelines, status. | CAO, Heads of Departments (HoDs), ITO, Political Leadership |
| Dissemination of the Plan | All stakeholders including OPM, MoLG, NGOs, and citizens | District planning meetings, DTPC forums, website, IEC materials | Promote transparency; increase awareness of DDP IV interventions | Plan highlights, budget priorities | CAO, District Planner, ITO, Political Leadership |

6.3 Roles/Responsibilities of Stakeholders in LG Communication and Feedback

The communication and feedback strategy for Kitagwenda outlines clear roles and responsibilities to ensure a well-coordinated, inclusive, and effective flow of information during DDP IV implementation.

Table 6.4: Institutions and their Roles and Responsibilities

| Institution | Roles and Responsibilities |
| --- | --- |
| Office of the LCV Chairperson | • Communicate DDP IV priorities and implementation to the population • Provide political leadership and public policy guidance • Mobilize citizens for government programmes • Promote good governance through DEC meetings, annual State of the District address, and budget speeches • Advocate for ordinances/policies that encourage community participation and accountability • Provide regular updates on DDP progress |
| Chief Administrative Officer (CAO) | • Issue official communication • Enforce implementation of the communication policy • Disseminate government positions on DDP and service delivery • Coordinate access-to-information requests |
| District Information Officer (DIO) | • Lead media and public relations • Ensure uniform messaging • Produce communication materials with HoDs and partners • Organize press briefings and monitor local media • Update/manage district website and social media • Handle crisis communication |
| Heads of Departments (HoDs) | • Implement sector-specific policies • Develop/disseminate departmental communication materials • Clarify technical content • Provide reports to CAO • Host events and manage guest relations |
| Heads of Service Units (Health Units, Schools) | • Inform staff/clients about new services and events • Submit regular reports to HoDs • Communicate service availability and receive feedback |
| Service Management Committees (SMCs, HUMCs, WSCCs) | • Report accountability to PTAs/community • Mobilize/sensitize communities on their roles • Manage local contributions (e.g., water sources, schools) |
| Project Management Committees | • Secure project resources at community level • Monitor implementation and report progress • Mobilize additional resources • Participate in evaluations |
| Lower Local Government (LLG) Councils | • Mobilize/sensitize communities on DDP IV priorities • Support community-led planning and prioritization • Allocate local resources and conduct oversight • Discuss implementation reports and make recommendations |
| Sub-county Chiefs | • Support LLG planning/budgeting • Monitor local projects and prepare progress reports • Manage and account for resources under their jurisdiction |
| Community Development Officers (CDOs) | • Mobilize/sensitize communities • Support needs assessments and project planning • Support implementation and community-based monitoring • Guide community reporting and feedback collection |

CHAPTER SEVEN: RISKS MANAGEMENT AND MITIGATION MEASURES

The objectives of this Risk Management Strategy are to enable the District Local Government to deal better with the risks in achieving each objective as provided for in the District Strategic Plan. Section 45(2) of Public Finance Management (PFM) Act 2015 also demands for ever government entity to prepare a risk register. It’s a management tool that explains the local government’s underlying approach to risk management, documents the roles and responsibilities of various responsible officers, and the risk management principles.

Risk management is critical to the successful implementation of the Kitagwenda District Development Plan IV (DDP IV). It ensures that potential threats to plan implementation are systematically identified, assessed, and mitigated to safeguard the District’s development objectives and long-term transformation agenda.

The risks considered under this Plan are categorized into three broad groups including: - Internal, External, Strategic and operational.

7.1 Risks Management and Anticipated Impacts

Table 7.1: Anticipated Risks and Mitigation Measures

| No. | Type of risks | Category | Causes of the risks | Likelihood of occurrence | Impacts (1=low, 2- | Mitigation | Lead Agency |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1= Low | 1= Low, |  |  |
|  |  |  |  | 2=Intermediate | 2=intermediate |  |  |
|  |  |  |  | 3= High | 3= High |  |  |
| 1. | Risk under stores | operational | Failure to supply the actual number of items specified on the Local Purchase Order |  | High | Verification of all deliveries to stores to avoid fictitious deliveries | Internal Audit Department |
| 2. | Increased climate change and environmental challenges | External Risk | Global warming, deforestation, wetland encroachment around Buhanda, Mahyooro |  |  | Implement climate adaptation strategies; enforce environmental regulations; promote sustainable practices and wetland restoration | Natural Resources Dept |
| 3 | Health risks | External Risk | Outbreaks, inadequate infrastructure/equipment, limited community awareness |  |  | Strengthen PHC, surveillance, and community health education; stock essential medicines | Health Dept |
| 4. | Low total factor productivity and utilization | Strategic Risk | Limited technology adoption, low extension coverage, skills gaps |  |  | Upskill workforce, expand extension, support value addition (coffee, fish, dairy) | Production Dept |
| 5. | Risk under procurement | operational | Failure to award competent firms /companies for supply of goods & services |  |  | Pre-qualification, evaluation of firms, due diligence & contract management | Procurement Department, |
| 6. | Inadequate locally raised revenue | Strategic Risk | Narrow tax base, weak administration, informality of businesses in the district. |  |  | Update revenue registers, automate collection, expand sources (market dues, landing site fees) | Finance Dept, Trade/Industry |
| 7. | Risk under works | operational | Failure by engineer to supervise the ongoing works which results in shoddy work. |  |  | Adequate supervision of ongoing works to realize value for money. | Mgt, Internal Audit, works Dept, political leadership |
| 8. | Risk under water | compliance | Failure by the water officer to implement the water projects in line with the conditions of the grant |  |  | Strict adherence to conditional requirements attached to the grant by the implementer. | Water officer, Internal Audit |
| 9. | Risk under production | compliance | Failure by the DPO to comply to the program (ACDP, UGIFT) requirements underlying the department |  |  | Strict adherence to the program requirements/conditions | DPO, Internal Audit |
| 10. | Risk under Education | compliance | Failure by the District Education officer (DEO) to adequately supervise the infrastructure under construction & operations of education institutions under his docket |  |  | Effective supervision of the on going construction & frequent inspection of education institutions | DEO, internal Audit, management, political leadership |
| 11. | Risk under Finance | Operational | Failure to adequately mobilize, collect ample locally raised revenue & failure to process payments coupled with remittances of un absorbed funds back to the consolidated fund |  |  | Intensive mobilization & collection of local revenue, full absorption of central government grants | Finance, management, Internal Audit |
| 12. | Risk under natural Resources | compliance | Encroachment on the forests, wetlands & the destruction of the ecosystem coupled with harsh climatic conditions (long dry spells, hailstorms, floods) |  |  | Conservation of the ecosystem by the community coupled with routine inspection by natural resources office to foster compliance | Natural resources office |
| 13. | Risk under human resource | Operational | Failure to process staff salaries, gratuity & pension on time coupled with ghost staff |  |  | Automation of the human resource management system (HCM), cleaning of personnel information | Management, Internal Audit |
| 14. | Risk under District Service commission | compliance | Failure to appropriately carry out the recruitment process through advertising, short listing & interviewing |  |  | Compliance to the recruitment procedures, processes & systems. | Management, District Service commission, Internal Audit |

Risk Monitoring and Management

The District will institutionalize continuous risk monitoring through the Monitoring, Evaluation, and Learning (MEL) framework.

Risk reviews will be conducted annually and integrated into performance reviews to enable adaptive planning and timely mitigation.

Risk Governance and Accountability.

The District Internal Auditor will coordinate risk monitoring, while sector departments will implement mitigation measures. The District Internal Audit will consolidate risk reports and provide updates to Council, the Office of the Prime Minister, and the National Planning Authority.

CHAPTER EIGHT: MONITORING, EVALUATION AND LEARNING (MEL)

This chapter articulates the Monitoring and Evaluation (M&E) framework; M&E roles and responsibilities of key actors; and major monitoring and evaluation events for Kitagwenda District DDP IV (FY2025/26–2029/30).

8.1 Monitoring and Evaluation (M&E) Framework

The Development Plan reflects the aspirations of the people of Kitagwenda, aligned to national strategic direction. A comprehensive M&E strategy is required to ensure that projects are implemented to deliver planned outputs and outcomes efficiently and effectively.

Monitoring and Evaluation of DDP implementation is the responsibility of the Council, executed through the District Executive Committee (DEC) and Sectoral Committees. On the technical side, the Chief Administrative Officer Coordinates M&E by technical staff. Funds for M&E are allocated across actors.

The MEL framework will enable the District and its partners to systematically track and report on:

- Overall programme implementation progress and adherence to planned activities;

- Availability, adequacy, and timeliness of financial, material, and human resources;

- Deviations from approved plans and performance against planned outputs and outcomes;

- Achievement of programme objectives and relevance of interventions to district development priorities.

The MEL framework is aligned to the NDP IV Results Framework to facilitate vertical reporting and national performance aggregation.

8.1.1 Progress Reporting

Progress reporting will be conducted through quarterly and annual performance reports covering both physical and financial performance of all programmes and projects under the DDP IV. All District departments, Lower Local Governments (Sub-counties and Town Councils), development partners, CSOs, and private sector actors will contribute to performance reporting based on the DDP IV Results Matrix.

Reports will be informed by:

    - Field monitoring visits and supervision reports

    - Spot checks and technical audits

    - Budget performance reports generated from PBS

    - Citizen feedback (Baraza’s) and participatory monitoring

Consolidated reports will be submitted to NPA, MoFPED, OPM, MoLG, and relevant Sector MDAs for national reporting and oversight.

8.1.2 Quarterly Progress Report

District Physical Performance and Budget Performance Reports will be produced quarterly by the Planning Department and shared with stakeholders. These track progress against annual targets of the DDP IV.

Non-state actors will submit reports as guided by Memoranda of Understanding (MoUs) aligned to the DDP IV Results Matrix.

8.1.3 Reviews

Joint Annual Review

The District will conduct Joint Annual Reviews/ Conferences to asses overall programme performance including the contribution of the private sector and non-state actors. The findings will be disseminated through an annual forum to inform the subsequent year’s prioritization and budgeting.

Participants in these reviews will include: - District political and technical leadership, Lower Local Government representatives, Development partners and NGOs, Private sector and civil society and Special interest groups (youth, women, PWDs, elderly).

Mid-term Evaluation

A mid-term review will be conducted midway through the implementation of the DDP IV objectives aligned to the NDPIV MidTerm Review (MTR). It will bring together stakeholders (FBOs, CBOs, PSOs, DPs, opinion leaders). The report will document challenges, lessons learnt, and inform implementation adjustments for the remaining period. Reports will be presented to DTPC, DEC, and Council, and shared with NPA and sector ministries.

8.1.5 End of Term Evaluation

At the end of the DDP IV period, an end-term evaluation will be conducted to assess achievement of results, sustainability of interventions, and emerging impacts and lessons for the next DDP cycle. Reports will be presented to district leadership and discussed in joint annual LGDP review meetings; copies will be shared with NPA and sector MDAs.

8.2 M&E Roles and Responsibilities of Key Actors

Stakeholders and their roles in M&E during and after plan implementation include: -

Table 8.1: M&E Roles and Responsibilities of Key Actors

| Stakeholder | Roles | M &E outputs |
| --- | --- | --- |
| Ministries and MDAs | Provide guidance and direction in the implementation of government programs. Provider minimum service delivery standards | - Review progress in the implementation of government programmes in Local Government - Assess adhere to the minimum service delivery standards |
| District Council | Oversight and corrective action | - Council monitoring reports |
| District executive committee | Conduct quarterly monitoring visits | - Ownership enhanced for government programmes implemented |
| District technical planning committee | Discussion of findings of M&E reports | - Progress tracked on the implementation of government programmes - Remedial actions recommend on implementation of government programmes |
| District (HLG) Departments | Conduct quarterly monitoring visits | - Track implementation of government programmes - Identification of hiccups on the implementation of government programmes |
| Planning department | Conduct and document findings of joint quarterly monitoring visits | - Track implementation of government programmes - Identification of hiccups on the implementation of government programmes |
| District Statistical Committee | Generate data for planning | - Statistical abstracts. |
| Community members | Monitor government programs taking place in their areas on a day to-day basis Provide security to project implementation sites | - Track implementation of government programmes - Strengthen ownership of government programmes |

8.3 Major Monitoring and Evaluation Events

MEL will be anchored in periodic events that promote accountability, learning, and adaptive management across the DDP IV cycle.

Table 8.1: LGDP Main M&E Events Timeframe

| Main M&E Events | Purpose and Description | Output | Lead Agency | Actors | Time frame |
| --- | --- | --- | --- | --- | --- |
| Programme/Sub-programme Quarterly Progress Report | Document implementation progress, drivers, challenges, and recommendations | Quarterly Programme Progress Report | LG Programme/Sub-programme Heads | Other LG actors, NGOs & DPs | Quarterly |
| LGDP Annual Performance Review | Internal review of LGDP implementation (programmes, interventions, projects) | Local Government Annual Performance Report | HLG | LG Stakeholders | Annually, September |
| Alignment of BFPs and Budgets to the LGDP | Align BFP with LGDP following the 1st BCC to HoDs & LLGs | BFP | Accounting Officer, Planning Dept | MoFPED, NPA, TPC members & stakeholders | Oct–Nov |
| Budgeting and Financial Planning | Circulate 2nd BCC to commence budget preparation | Annual Budget Estimates; Performance Contracts; Annual Workplan | Accounting Officer; Planning & Finance Depts/Units | MoFPED, NPA, TPC members & stakeholders | Mar–May (annual) |
| Statistics Production & Use | Basis for baseline, midterm, end line assessments | Statistical Abstracts; Quarterly Progress Reports | UBOS, MoFPED | OPM, NPA, MDAs & LGs | Annually; Quarterly |
| LGDP Mid-Term Review | Assess mid-term progress and consistency with objectives | LGDP Mid-Term Review Report | HLG | NPA, MDAs, MoFPED, OPM, LGs, private sector, CSOs | Jan–Jun 2028 |
| LGDP End Evaluation | Assess end-term performance of LGDP | LGDP End Evaluation Report | HLG | MDAs, MoFPED, OPM, LGs, private sector, CSOs | Apr–Jun 2030 |

ANNEXES

| No. | Project Profile Component | Details |
| --- | --- | --- |
| 1. | Project Summary | Project Title: District Administrative Offices Construction Project. Project Programme: Public Sector Transformation. Vote Code: Kitagwenda District Local Government. Implementing Agency: Kitagwenda District Local Government – Administration Department. Location: Kitagwenda Town Council – District Headquarters. Estimated Project Cost: Current Stage of Implementation: Roofing Stage Funding gap: Project Duration: FY2025/26 – FY2029/30 Officer Responsible: Chief Administrative Officer |
|  | Problem Statement | Several local government administrative units in Kitagwenda District operate without adequate office infrastructure. This affects effective coordination of government programmes, service delivery and administrative operations. Causes of the problem: • Limited infrastructure development. • Inadequate funding for construction of administrative offices • Increasing demand for government services at local levels |
|  | Situation Analysis | The existing office accommodation at Kitagwenda District Local Government is inadequate to support the growing administrative functions and increasing staffing levels. Most departments operate from congested, shared, or temporary office spaces, resulting in poor working conditions, inefficient coordination, inadequate records management, and limited space for public service delivery. The current facilities also lack sufficient meeting rooms, ICT infrastructure, storage space, accessibility for persons with disabilities, and adequate security. The construction of a modern District Administration Block will provide adequate office space and essential administrative facilities, improve staff productivity and coordination, enhance records management, and strengthen the district's capacity to deliver efficient and quality services to the people of Kitagwenda. |
|  | Cross-Cutting Issues | Good Governance: Improved office infrastructure enhances transparency, accountability and coordination of government programmes. ICT Integration: Modern administrative buildings will support installation of ICT systems for public service delivery. Public Service Delivery: Improved infrastructure enhances citizen access to government services. |
|  | Relevance of the Project | The project strengthens administrative capacity and improves coordination of government programmes, thereby enhancing effective service delivery across Kitagwenda District. |
|  | Stakeholders | Direct Beneficiaries: District administrative staff, local government officials and public service providers. Indirect Beneficiaries: Residents and communities who access government services through the administrative offices. |
|  | Project Objectives, Outcomes and Outputs | Project Objective: To improve administrative efficiency and service delivery through construction of modern administrative offices in Kitagwenda District. Expected Outcomes: - Improved working environment for government staff. - Enhanced coordination of government programmes. - Improved public access to administrative services. |
|  | Project Outputs: | Construction of district administration offices including office spaces, meeting rooms, records management facilities and service delivery counters. |
|  | Inputs | Inputs: Financial resources, construction materials, architectural designs and technical personnel. Activities: Architectural design and planning, procurement of contractors, construction of administrative buildings, installation of office infrastructure and supervision of construction works. |
|  | Strategic Options and Coordination | Strategic Options: Mobilization of funding through government infrastructure programmes and district development funds. Coordination with Agencies: Ministry of Local Government, Ministry of Finance Planning and Economic Development and National Planning Authority. |
|  | Project Annualized Targets and Costs |  |

| No. | Project Profile Component | Details |
| --- | --- | --- |
| 1. | Project Summary | Project Title: Primary School Infrastructure Improvement. Project Programme: Human Capital Development. Vote Code: Kitagwenda District Local Government. Implementing Agency: Kitagwenda District Local Government - Department of Education and Sports. Location: Primary and Secondary schools across the 13 Lower Local Governments. Estimated Project Cost: Project Duration: FY2025/26 – FY2029/30 Officer Responsible: District Education Officer |
|  | Problem Statement | Many primary schools in Kitagwenda District operate with inadequate classroom infrastructure, insufficient teachers’ accommodation, inadequate sanitation facilities and shortage of school furniture. This situation results in overcrowded classrooms, poor learning conditions and low learner retention. |
|  | Situation Analysis | Several schools require construction of new classroom blocks, teachers’ houses, pit latrines and provision of desks. Existing classrooms in some schools are dilapidated and require renovation. Enrolment has increased due to Universal Primary Education, placing pressure on existing facilities. |
|  | Cross-Cutting Issues | Gender-responsive infrastructure, sanitation improvements, disability access provisions and environmental safeguards in construction. |
|  | Relevance of the Project | The project will improve access to quality education and support implementation of Universal Primary Education in Kitagwenda District. |
|  | Stakeholders | Pupils, teachers, school management committees, parents, local government and Ministry of Education and Sports. |
|  | Project Objectives, Outcomes and Outputs | Objective: Improve learning infrastructure and teaching conditions in primary schools across Jinja District. Expected Outcomes: Improved learning environment, improved pupil retention and improved teacher welfare. |
|  | Project Outputs: |  |
|  | Inputs | Construction materials, financial resources, procurement of contractors, construction supervision and installation of school furniture. |
|  | Strategic Options and Coordination | Coordination with Ministry of Education and Sports and Ministry of Finance Planning and Economic Development. |
|  | Project Annualized Targets and Costs |  |

| No. | Project Profile Component | Details |
| --- | --- | --- |
| 1. | Project Summary | Project Title: Rural Water Supply Development Project. Project Programme: Natural Resources, Environment, Climate Change, Land and Water Management Programme . Vote Code: Kitagwenda District Local Government. Implementing Agency: Kitagwenda District Local Government – Water Department Location: Rural communities across Kitagwenda District including Buhanda S/C, Mahyoro S/C, Kicheche S/C, Kakasi S/C, Ruhunga S/C, Ntara S/C and Rwenjaza S/C Estimated Project Cost: Project Duration: FY2025/26 – FY2029/30 Officer Responsible: District Water Officer |
|  | Problem Statement | Many rural communities in Kitagwenda District continue to face limited access to safe and reliable water sources. Some households rely on unsafe water sources such as unprotected wells, ponds and surface water. Long distances, travelled to fetch water disproportionately affect women and children and contribute to poor sanitation and health outcomes. |
|  | Situation Analysis | Several schools require construction of new classroom blocks, teachers’ houses, pit latrines and provision of desks. Existing classrooms in some schools are dilapidated and require renovation. Enrolment has increased due to Universal Primary Education, placing pressure on existing facilities. |
|  | Cross-Cutting Issues | Gender-responsive infrastructure, sanitation improvements, disability access provisions and environmental safeguards in construction. |
|  | Relevance of the Project | The project will improve access to quality education and support implementation of Universal Primary Education in Kitagwenda District. |
|  | Stakeholders | Pupils, teachers, school management committees, parents, local government and Ministry of Education and Sports. |
|  | Project Objectives, Outcomes and Outputs | Objective: Improve learning infrastructure and teaching conditions in primary schools across Jinja District. Expected Outcomes: Improved learning environment, improved pupil retention and improved teacher welfare. |
|  | Project Outputs: |  |
|  | Inputs | Construction materials, financial resources, procurement of contractors, construction supervision and installation of school furniture. |
|  | Strategic Options and Coordination | Coordination with Ministry of Education and Sports and Ministry of Finance Planning and Economic Development. |
|  | Project Annualized Targets and Costs |  |